## Out Going Letters
REHABILITATION / IMPROVEMENT AND MAINTENANCE OF 74.38 KM RURAL ROADS IN TRINCOMALEE DISTRICT IN EASTERN PROVINCE – PACKAGE 1 CONTRACT NO: RDA/ADB/iROAD-2(EP)/ICB/TR-01
SN | Subject | Road ID | CR | Date | Letter No | Description | Reply Date | Reply Letters | Remarks
1 | Calibration | No | RE | 29.08.2019 | PM/iRoad/TR-1/RE/GEN/001 | Calibration Report for Laboratory Equipment | 12.09.2019 | S-9-TR-0018/RE
2 | Vehicle | Type - 2 | RE | 30.08.2019 | PM/iRoad/TR-1/RE/GEN/002 | Vehicle Supply Type - 2 for Engineer - WP 7606 | 03.09.2019 | S-9-TR-0003/RE
3 | Vehicle | Type - 2 | RE | 03.09.2019 | PM/iRoad/TR-1/RE/GEN/002 | Vehicle Supply Type - 2 for Engineer - WP 7601 | 06.09.2019 | S-9-TR-0011/RE
4 | Crack Survey | No | RE | 05.09.2019 | PM/iRoad/TR-1/RE/GEN/004 | Submission of Format for Crack Survey | 14.09.2019 | S-9-TR-0019/RE
5 | Company Approval | No | RE | 06.09.2019 | PM/iRoad/TR-1/RE/GEN/005 | Submission of Company Approval Certificate for Laboratory Equipment Calibration | 12.09.2019 | S-9-TR-0018/RE
6 | GPS | No | RE | 06.09.2019 | PM/iRoad/TR-1/RE/GEN/006 | Rectification Method Statement for GPS Monuments Steel Bar | 19.09.2019 | S-9-TR-0032/RE
7 | GPS | No | RE | 11.09.2019 | ENC/PM/RE/TR-1/GEN/0007 | Submission of GPS Report |  | S-9-TR-0019/RE S-9-TR-0054/RE
8 | Laboratory | No | RE | 18.09.2019 | ENC/PM/RE/TR-1/GEN/0008 | Field Laboratory ar Serunuwara | 20.09.2019 | S-9-TR-0033/RE
9 | Laboratory | No | RE | 18.09.2019 | ENC/PM/RE/TR-1/GEN/0009 | Field Laboratory ar Mutur | 20.09.2019 | S-9-TR-0033/RE
10 | Vehicle | Type - 2 | RE | 20.09.2019 | ENC/PM/RE/TR-1/GEN/0010 | Vehicle Supply Type - 2 for Engineer | 20.09.2019 | S-9-TR-0034/RE
11 | Method Statement | No | RE | 21.09.2019 | ENC/PM/RE/TR-1/GEN/0011 | Submission of Method Statement for Soil Investigation | 05.10.2019 | S-9-TR-0056/RE
12 | Calibration | No | RE | 21.09.2019 | ENC/PM/RE/TR-1/GEN/0012 | Calibration Report for Laboratory Survey Equipment | 24.09.2019 | S-9-TR-0038/RE
13 | Control Point | No | RE | 21.09.2019 | ENC/PM/RE/TR-1/GEN/0013 | Control Point Detail | 24.09.2019 | S-9-TR-0040/RE
14 | Engineer's Staff | No | RE | 23.09.2019 | ENC/PM/RE/TR-1/GEN/0014 | Provision of Operatives for the Engineer's Staff | 26.09.2019 | S-9-TR-0042/RE
15 | Furniture | Type - 2 | RE | 24.09.2019 | ENC/PM/RE/TR-1/GEN/0015 | Provide fully furnished House Type - 2 | 02.10.2019 | S-9-TR-0050/RE
16 | Joint Inspection | 6 | RE | 26.09.2019 | ENC/PM/RE/TR-1/GEN/0016 | Request for Joint Inspection for Thopur Kaddaiparichan Idimanthurai Road ETR006 |  | NNR | NNR
17 | Vehicle | Type - 4 | RE | 01.10.2019 | ENC/PM/RE/TR-1/GEN/0017 | Vehicle Supply Type - 4 for Engineer CP BIF-0199 | 07.10.2019 | S-9-TR-0062/RE
18 | Engineer's Staff | No | RE | 07.10.2019 | ENC/PM/RE/TR-1/GEN/0019 | Provision of Operatives for the Engineer's Staff (Mr.ZA.Irsath Ali) |  | NNR | NNR
19 | Topo | No | RE | 07.10.2019 | ENC/PM/RE/TR-1/GEN/0020 | Topographical Survey of Roads |  | pending | NNR
20 | Initial Maintenance | No | RE | 08.10.2019 | ENC/PM/RE/iRd/TR-1/GEN/0021 | Submission of cost Estimate for Initial Maintenance |  | S-9-0357/DTL
21 | Vehicle | Type - 4 | RE | 08.10.2019 | ENC/PM/RE/TR-1/GEN/0022 | Vehicle Supply Type - 4 for Engineer (BIE-8576, BIE-8569, BIE-8557) | 12.10.2019 | S-9-TR-0064/RE
22 | Method Statement | No | RE | 10.10.2019 | ENC/PM/RE/TR-1/GEN/0023 | Submission of method statement for Initial Road Maintenance | 15.10.2019 | S-9-TR-0078/RE
23 | Source Approval | No | RE | 10.10.2019 | ENC/PM/RE/TR-1/GEN/0024 | Submission for Source Approval of Cold Mix Material at Edward and Christie Badalsama Plant | 14.10.2019 | S-9-TR-0075/RE
24 | Source Approval | No | RE | 10.10.2019 | ENC/PM/RE/TR-1/GEN/0025 | Submission for Source Approval of ABC Material at Edward and Christie Badalsama Plant | 14.10.2019 | S-9-TR-0076/RE
25 | Source Approval | No | RE | 10.10.2019 | ENC/PM/RE/TR-1/GEN/0026 | Submission for source Approval of Lanwa Reinforcement Material | 18.10.2019 | S-9-TR-0087/RE
26 | Source Approval | No | RE | 10.10.2019 | ENC/PM/RE/TR-1/GEN/0027 | Submission for source Approval of Melwa Reinforcement Material | 18.10.2019 | S-9-TR-0087/RE
27 | Source Approval | No | RE | 10.10.2019 | ENC/PM/RE/TR-1/GEN/0028 | Submission for source Approval of GTB Reinforcement Material | 18.10.2019 | S-9-TR-0087/RE
28 | Source Approval | No | RE | 10.10.2019 | ENC/PM/RE/TR-1/GEN/0029 | Subrnission for Source Approval of Tokyo Super Cement | 19.10.2019 | S-9-TR-0092/RE
29 | Method Statement | No | RE | 12.10.2019 | ENC/PM/RE/TR-1/GEN/0030 | Submission of Method Statement | 18.11.2019 | S-9-TR-0173/RE
30 | Furniture | Type - 2 | RE | 14.10.2019 | ENC/PM/RE/TR-1/GEN/0031 | Provide fully furnished office Tvpe - 2 (CE Office at Muthur) | 18.10.2019 | S-9-TR-0082/RE
31 | Method Statement | No | RE | 14.10.2019 | ENC/PM/RE/TR-1/GEN/0032 | Submission of Method Statement for Crack Survrey |  | S-9-TR-0370/JR
32 | Site Clarence | 171 | RE | 15.10.2019 | ENC/PM/RE/TR-1/GEN/0033 | Issues of site clarence for Land Mines in A15 Road |  | S-9-TR-0102/RE S-9-0321/DTL
33 | Source Approval | No | RE | 17.10.2019 | ENC/PM/RE/TR-1/GEN/0034 | Re-Submission for Source Approval of Cold Mix Material at Edward and Christie Wadakada Plant | 26.10.2019 | S-9-TR-0123/RE
34 | Source Approval | No | RE | 17.10.2019 | ENC/PM/RE/TR-1/GEN/0035 | Re-Submission for Source Approval of ABC Material at Edward and Christie Badakada Plant | 26.10.2019 | S-9-TR-0122/RE
35 | Source Approval | No | RE | 17.10.2019 | ENC/PM/RE/TR-1/GEN/0036 | Submission for Source Approval of CRSI. CSS1. MC-30 and 60-70Pen Bitumen of Bitumix Brand | 06.11.2019 | S-9-TR-0142/RE
36 | Conditional Report | No | RE | 22.10.2019 | ENC/PM/RE/TR-1/GEN/0037 | Submission of Conditional Report for Already Constructed Road |  | NNR | NNR
37 | Furniture | Type - 2 | RE | 24.10.2019 | ENC/PM/RE/TR-1/GEN/0038 | Provide Fully Furnished House Type -2 (RE's Accommodation) | 23.11.2019 | S-9-TR-0212/RE
38 | Site Clarence | 171 | RE | 25.10.2019 | ENC/PM/RE/TR-1/GEN/0039 | Issues of site clarence for Land Mines in A15 Road at CH 81+800km | 01.11.2019 | S-9-TR-0131/RE
39 | Source Approval | 171 | RE | 25.10.2019 | ENC/PM/RE/TR-1/GEN/0040 | Increasing the Cold Mix Thickness from 35mm to 50mm for the A15 Road | 26.10.2019 | S-9-TR-0114/RE
40 | Engineer's Staff | No | RE | 25.10.2019 | ENC/PM/RE/TR-1/GEN/0041 | Provision of Operatives for the Engineer's Staff (Mr.V.Teleephhumar) | 26.10.2019 | S-9-TR-0120/RE
41 | Engineer's Staff | No | RE | 29.10.2019 | ENC/PM/RE/TR-1/GEN/0042 | Provision of Operatives for the Engineer's Staff (Mr.Bandara/Mr.Dhanusshian/Mr.Hathee) | 06.11.2019 | S-9-TR-0147/RE
42 | Method Statement | No | RE | 28.10.2019 | ENC/PM/RE/TR-1/GEN/0043 | Resubmission of Method Statement and formats for Crack Survey |  | S-9-TR-0407/JR
43 | IPA | No | RE | 05.11.2019 | ENC/PM/RE/TR-1/GEN/0044 | Interim Payment Applicaation - 02 for the Month Octomber 2019 | 13.11.2019 | S-9-TR-0169/RE
44 | Name Board | No | RE | 05.11.2019 | ENC/PM/RE/TR-1/GEN/0045 | Project Name Board Bill: 1A, Bill Item. 11 Pay Item. 118(1) | 13.11.2019 | S-9-TR-0175/RE
45 | Engineer's Staff | No | RE | 07.11.2019 | ENC/PM/RE/TR-1/GEN/0046 | Provision of Operatives for the Engineer's Staff (Mr.PJ. Saththyanayagam) | 08.11.2019 | S-9-TR-0154/RE
46 | Weather | No | RE | 07.11.2019 | ENC/PM/RE/TR-1/GEN/0047 | Weather Record for the Month of Sept & October 2019 | 08.11.2019 | S-9-TR-0153/RE
47 | Variation | No | RE | 07.11.2019 | ENC/PM/RE/TR-1/GEN/0048 | Variation No 01 (Type 2 House) |  | NNR | NNR
48 | Weather | No | RE | 07.11.2019 | ENC/PM/RE/TR-1/GEN/0049 | Notice of Claim for affected the work due to Heavy / Continuous Rain |  | NNR | NNR
49 | Calibration | No | RE | 08.11.2019 | ENC/PM/RE/TR-1/GEN/0050 | Calibration Report for Survey Equipment | 13.11.2019 | S-9-TR-0176/RE
50 | Progress Report | No | RE | 08.11.2019 | ENC/PM/RE/TR-1/GEN/0051 | Monthly Progress Report - 01 (October-2019) | 26.11.2019 | S-9-TR-0217/RE
51 | Lum | No | RE | 11.11.2019 | ENC/PM/RE/TR-1/GEN/0052 | Lum Sum Breakdown |  | pending | NNR
52 | Vehicle | Type - 2 | RE | 12.11.2019 | PM/iRoad/TR1/RE/GEN/053 | Vehicle Supply Type -2 for Engineer (PH-9072) | 14.11.2019 | S-9-TR-0182/RE
53 | Shut Down | No | RE | 12.11.2019 | PM/iRoad/TR1/RE/GEN/054 | Temporary Site Shut Down due to President Election | 13.11.2019 | S-9-TR-0171/RE
54 | Engineer's Staff | No | RE | 13.11.2019 | ENC/PM/RE/TR-1/GEN/0055 | Provision of Operatives for the Engineer's Staff | 14.11.2019 | S-9-TR-0181/RE
55 | Stationary | Type - 2 | RE | 13.11.2019 | ENC/PM/RE/TR-1/GEN/0056 | Stationary item provided for Office Type - 02 |  | NNR | NNR
56 | Shut Down | No | RE | 13.11.2019 | ENC/PM/RE/TR-1/GEN/0057 | Temporary Site Shut Down due to President Election | 14.11.2019 | S-9-TR-0180/RE
57 | Furniture | Type - 2 | RE | 13.11.2019 | ENC/PM/RE/TR-1/GEN/0058 | Furniture and Equipment Supplied to Type - 2 (CE's) Office | 22.11.2019 | S-9-TR-0203/RE
58 | Source Approval | No | RE | 13.11.2019 | ENC/PM/RE/TR-1/GEN/0059 | Submission for Source Approval of CRSI. CSS1. MC-30 and 60-70Pen Bitumen of Bitumix Brand | 21.11.2019 | S-9-TR-0198/RE
59 | Vehicle | No | RE | 14.11.2019 | ENC/PM/RE/TR-1/GEN/0060 | Request to Approve the Vehicle Type - 5 for Engineer (PH-7056) | 22.11.2019 | S-9-TR-0202/RE
60 | Laboratory | No | RE | 22.11.2019 | ENC/TR01/PM/RE/0062 | Main Laboratory at Muthur | 29.11.2019 | S-9-TR-0237/RE
61 | Vehicle | Type - 5 | RE | 22.11.2019 | ENC/TR01/PM/RE/0063 | Vehicle Supply Type - 5 for Engineer (PH-7056) | 22.11.2019 | S-9-TR-0202/RE
62 | Engineer's Staff | No | RE | 25.11.2019 | ENC/TR01/PM/RE/0064 | Provision of Operatives for the Engineer's Staff AQS | 27.11.2019 | S-9-TR-0225/RE
63 | Method Statement | No | RE | 26.11.2019 | ENC/TR01/PM/RE/0067 | Submission of Method Statement for Soil Investigation | 07.12.2019 | S-9-TR-0266/RE
64 | Accommodation | Type - 2 | RE | 26.11.2019 | ENC/TR01/PM/RE/0069 | Engineer's House Type - 2 at Mutur | 29.11.2019 | S-9-TR-0238/RE
65 | IPA | No | RE | 26.11.2019 | ENC/TR01/PM/RE/0070 | Re Submission of Interim Payment Application - 02 for the Month Octomber 2019 | 02.12.2019 | S-9-TR-0242/RE
66 | Source Approval | No | RE | 26.11.2019 | ENC/TR01/PM/RE/0071 | Submission of Source Approval of Ultra Tech Cement | 29.11.2019 | S-9-TR-0236/RE
67 | Other ORG | 133 | RE | 26.11.2019 | ENC/TR01/PM/RE/0072 | Newly Constructed Road by Other Organization ETR133 | 14.12.2019 | S-9-TR-0296/RE
68 | Design | 171 | RE | 28.11.2019 | ENC/TR01/PM/RE/0074 | Design Issues on the Road ID ETR171, Batticaloa Thirukondiyamadu Trincomalee Road (A15) | 09.01.2020 | S-9-TR-0440/RE
69 | Furniture | Type - 1 | RE | 28.11.2019 | ENC/TR01/PM/RE/0075 | Request to Confirm the List of Furniture for Employer's House Type-1 |  | NNR | NNR
70 | Source Approval | No | RE | 28.11.2019 | ENC/TR01/PM/RE/0076 | Submission for Source Approval of NP2 Hume Pipe - ICC | 07.12.2019 | S-9-TR-0254/RE
71 | Source Approval | No | RE | 28.11.2019 | ENC/TR01/PM/RE/0077 | Submission for Source Approval of Captain Steel | 03.12.2019 | S-9-TR-0253/RE
72 | Topo | 171 | RE | 28.11.2019 | ENC/TR01/PM/RE/0078 | Submission of Topograpghy, Survey Drawing from 94+000 to 96+000 (ETR171) | 10.12.2019 | S-9-TR-0283/RE | Accepted
73 | Source Approval | No | RE | 29.11.2019 | ENC/TR01/PM/RE/0081 | Submission for Source Aproval of Sub base & Embankment Material | 09.12.2019 | S-9-TR-0261/RE
74 | Secondary Survey | 171 | RE | 30.11.2019 | ENC/TR01/PM/RE/0082 | Resubmission of Secondary Survey Control and Leveling Details Report from CH 96+000 to 100+000km (ETR171) | 07.12.2019 | S-9-TR-0257/RE
75 | HA | 171 | RE | 30.11.2019 | ENC/TR01/PM/RE/0083 | Submission of Horizontal Alignment Drawing from 82+500 to 88+500 (ETR171) | 10.12.2019 | S-9-TR-0282/RE
76 | HA | 171 | RE | 30.11.2019 | ENC/TR01/PM/RE/0084 | Submission of Horizontal Alignment Drawing from 88+500 to 93+300 (ETR171) | 17.12.2019 | S-9-TR-0307/RE
77 | Topo | 171 | RE | 30.11.2019 | ENC/TR01/PM/RE/0085 | Submission of Topography Drawing from 100+000 to 105+300 (ETR171) | 16.12.2019 | S-9-TR-0298/RE | Accepted
78 | Name Board | No | RE | 02.12.2019 | ENC/TR01/PM/RE/0086 | Submission of Project Name Board | 14.12.2019 | S-9-TR-0294/RE
79 | Method Statement | No | RE | 02.12.2019 | ENC/TR01/PM/RE/0087 | Resubmission of Method Statement | 04.01.2020 | S-9-TR-0403/RE
80 | Method Statement | No | RE | 02.12.2019 | ENC/TR01/PM/RE/0088 | Submission of Method Statement for Base Failure Section | 10.12.2019 | S-9-TR-0275/RE
81 | Source Approval | No | RE | 03.12.2019 | ENC/TR01/PM/RE/0089 | Submission for approval of ready mix Concete (Tokyo Supermix) and Concerete Admixtures |  | S-9-TR-0291/RE S-9-TR-0308/RE
82 | HA | 171 | RE | 03.12.2019 | ENC/TR01/PM/RE/0090 | Resubmission of Horizontal Alignement Drawing from 78+300 to 82+500 ETR171 | 07.12.2019 | S-9-TR-0270/RE
83 | Vehicle | Type - 4 | RE | 03.12.2019 | ENC/TR01/PM/RE/0091 | Vehcile Supply Type - 4 for Engineer (BII-2094) | 07.12.2019 | S-9-TR-0267/RE
84 | Culvert Report | 171 | RE | 04.12.2019 | ENC/TR01/PM/RE/0092 | Culvert Conditional Report for the Road ETR171 | 21.12.2019 | S-9-TR-0331/RE
85 | Engineer's Staff | No | RE | 05.12.2019 | ENC/TR01/PM/RE/0095 | Provision of Operatives for the Engineer's Staff CAD Operator | 07.12.2019 | S-9-TR-0263/RE
86 | Source Approval | No | RE | 05.12.2019 | ENC/TR01/PM/RE/0096 | Submission for Source Approval of ABC & 20mm Aggregate |  | S-9-TR-0301/RE S-9-TR-0303/RE
87 | Source Approval | No | RE | 05.12.2019 | ENC/TR01/PM/RE/0097 | Submission for Source Approval of Embankment Material at Kumara Barrow pit Peeliyadi | 16.12.2019 | S-9-TR-0302/RE
88 | Secondary Survey | 166 | RE | 07.12.2019 | ENC/TR01/PM/RE/0098 | Submission of Secondary Survey Control and Leveling Details Report for the Road ID ETR166 and CH 0+000 to 4+220km | 19.12.2019 | S-9-TR-0315/RE
89 | Engineer's Staff | No | RE | 07.12.2019 | ENC/TR01/PM/RE/0099 | Appointment of Operatives for the Engineer's Staff AQS | 09.12.2019 | S-9-TR-0272/RE
90 | Progress Report | No | RE | 09.12.2019 | ENC/TR01/PM/RE/0100 | Monthly Progress Report - 02 (November-2019) | 20.12.2019 | S-9-TR-0327/RE
91 | Initial Maintenance | No | RE | 09.12.2019 | ENC/TR01/PM/RE/0101 | Initial Maintenance Completed Roads | 18.12.2019 | S-9-TR-0313/RE
92 | Secondary Survey | 57 | RE | 09.12.2019 | ENC/TR01/PM/RE/0102 | Submission of Secondary Survey Control and Leveling Details Report from CH 0+000 to 0+500km (ETR057) | 19.12.2019 | S-9-TR-0317/RE
93 | Engineer's Staff | No | RE | 09.12.2019 | ENC/TR01/PM/RE/0103 | Appointment for the Engineer's Staff AQS | 27.11.2019 | S-9-TR-0225/RE
94 | Insurance | No | TL | 12.12.2019 | ENC/TR01/PM/TL/0104 | Extended Insurance Policy for Maintenance Period | 20.02.2020 | S-20-1010/JR
95 | Secondary Survey | 6 | RE | 12.12.2019 | ENC/TR01/PM/RE/0105 | Submission of Secondary Survey Control and Leveling Details Report from CH 0+000 to 7+170 km ETR006 | 19.12.2019 | S-9-TR-0316/RE
96 | Secondary Survey | 70 | RE | 12.12.2019 | ENC/TR01/PM/RE/0106 | Submission of Secondary Survey Control and Leveling Details Report from CH 0+000 to 1+480 km | 14.01.2020 | S-9-TR-0457/RE
97 | Source Approval | No | RE | 12.12.2019 | ENC/TR01/PM/RE/0107 | Submission for Source Approval of River Sand at Mahaweli River Alla-Kantale | 18.12.2019 | S-9-TR-0310/RE
98 | Source Approval | No | RE | 12.12.2019 | ENC/TR01/PM/RE/0108 | Submission for Source Approval of Sub-Base & Embankment at Ganesh Barrow Pit | 18.12.2019 | S-9-TR-0309/RE
99 | Source Approval | No | RE | 12.12.2019 | ENC/TR01/PM/RE/0109 | Submission for Source Approval of Rubble at Parakrama Quarry | 18.12.2019 | S-9-TR-0314/RE
100 | Source Approval | No | RE | 12.12.2019 | ENC/TR01/PM/RE/0110 | Submission for Source Approval of ABC Material from Edward and Christie Wadakada Crusher Plan | 23.12.2019 | S-9-TR-0334/RE
101 | Topo | 171 | RE | 12.12.2019 | ENC/TR01/PM/RE/0111 | Submission of Topography Survey Drawing from CH 96+000 to 100+000(ETR171) | 28.12.2019 | S-9-TR-0367/RE | Accepted
102 | IPA | No | RE | 12.12.2019 | ENC/TR01/PM/RE/0112 | Interim Payment Application - 03 for the Month November 2019 |  | pending | NNR
103 | Topo | 171 | RE | 12.12.2019 | ENC/TR01/PM/RE/0113 | Submission of Topography Survey Drawing from 105+300 to 108+519 ETR171 | 17.01.2020 | S-9-TR-0464/RE | Accepted
104 | Crack Survey | 171 | RE | 13.12.2019 | ENC/TR01/PM/RE/0114 | Submission of Crack Survey Report from 78+300 to 79+685 (ETR171) | 28.12.2019 | S-9-TR-0369/RE
105 | Secondary Survey | 130 | RE | 16.12.2019 | ENC/TR01/PM/RE/0115 | Submission of Secondary Survey Control and Leveling Details Report from CH 0+000 to 0+960 km (ETR130) | 19.12.2019 | S-9-TR-0319/RE
106 | Secondary Survey | 127 | RE | 16.12.2019 | ENC/TR01/PM/RE/0116 | Submission of Secondary Survey Control and Leveling Details Report from CH 0+000 to 0+960 km (ETR127) | 19.12.2019 | S-9-TR-0318/RE
107 | Secondary Survey | 132 | RE | 16.12.2019 | ENC/TR01/PM/RE/0118 | Submission of Secondary Survey Control and Leveling Details Report from CH 0+000 to 0+510 km (ETR132) | 14.01.2020 | S-9-TR-0456/RE
108 | Secondary Survey | 053 & 134 | RE | 16.12.2019 | ENC/TR01/PM/RE/0119 | Submission of Secondary Survey Control and Leveling Details Report for the Road ID ETR053 & ETR134 | 14.01.2020 | S-9-TR-0455/RE
109 | Topo | 57 | RE | 16.12.2019 | ENC/TR01/PM/RE/0121 | Submission of Topography Survey Drawing from CH 0+000 to 0+500 km (ETR057) | 01.01.2020 | S-9-TR-0384/RE | Accepted
110 | Source Approval | No | RE | 18.12.2019 | ENC/TR01/PM/RE/0123 | Resubmission for Source Approval of Sub Base & Embankment Material | 23.12.2019 | S-9-TR-0335/RE
111 | Progress Report | No | RE | 18.12.2019 | ENC/TR01/PM/RE/0124 | Resubmission of Monthly Progress Report-01 for October 2019 | 24.12.2019 | S-9-TR-0345/RE
112 | Name Board | No | RE | 18.12.2019 | ENC/TR01/PM/RE/0126 | Submission of Public Notice | 17.01.2020 | S-9-TR-0466/RE
113 | ICS | 171 | RE | 19.12.2019 | ENC/TR01/PM/RE/0127 | Submission of Initial Cross Section Drawing from 78+300 to 79+000 (ETR171) | 03.01.2020 | S-9-TR-0398/RE | Resubmit
114 | Furniture | Type - 1 | RE | 20.12.2019 | ENC/TR01/PM/RE/0129 | Provide Fully furnished House Type - 1 at Sivapuri , Trincomalee | 08.01.2020 | S-9-TR-0420/RE
115 | Topo | 166 | RE | 26.12.2019 | ENC/TR01/PM/RE/0133 | Submission of Topography Survey Drawing CH 0+000 to 4+220km ETR166 | 06.01.2020 | S-9-TR-0413/RE | Accepted
116 | Engineer's Staff | No | RE | 26.12.2019 | ENC/TR01/PM/RE/0134 | Submission of Operatives for the Engineer's Staff (LT, Mr. SMIPB. Sakalasooriya) | 31.12.2019 | S-9-TR-0375/RE
117 | Furniture | Type - 2 | RE | 27.12.2019 | ENC/TR01/PM/RE/0135 | Furniture and Equipment Lab | 09.01.2020 | S-9-TR-0444/RE
118 | Source Approval | No | RE | 27.12.2019 | ENC/TR01/PM/RE/0137 | Resubmission for Approval of Ready Mix Concrete (Tokyo Supermix), Ecomix and Concera Concrete Admixtures | 14.01.2020 | S-9-TR-0409/RE
119 | HA | 171 | RE | 29.12.2019 | ENC/TR01/PM/RE/0138 | Resubmission of Horizontal Alignment Drawing from CH 88+500 to 92+400km (ETR171) | 01.01.2020 | S-9-TR-0390/RE
120 | Topo | 127 | RE | 30.12.2019 | ENC/TR01/PM/RE/0139 | Submission of Topography Survey Drawing CH 0+000 to 0+960km (ETR127) | 06.01.2020 | S-9-TR-0412/RE | Accepted
121 | GSMB | No | PE | 31.12.2019 | ENC/TR01/PM/PE/0140 | Letter to GSMB Describing Scope of Work |  | pending
122 | Source Approval | No | RE | 31.12.2019 | ENC/TR01/PM/RE/0141 | Submission for Source Approval of ABC Material from Edward and Christie Wadakada Crusher Plant | 09.01.2020 | S-9-TR-0435/RE
123 | HA | 171 | RE | 31.12.2019 | ENC/TR01/PM/RE/0142 | Resubmission of Horizontal Alignment Drawing from CH 92+400 to 98+400km | 14.01.2020 | S-9-TR-0458/RE
124 | Initial Maintenance | 166 | RE | 04.01.2020 | ENC/TR01/PM/RE/0143 | Request for Rock Filling Under Initial Maintenance for the Road ETR166 | 17.01.2020 | S-9-TR-0462/RE
125 | HA | 171 | RE | 06.01.2020 | ENC/TR01/PM/RE/0144 | Approval of Horizontal Alignment Drawing from CH 88+500 to 92+400km on the road ID ETR171, Batticaloa Thirukondiyamadu Trincomalee Road (A15) | 09.01.2020 | S-9-TR-0440/RE
126 | Progress Report | No | RE | 06.01.2020 | ENC/TR01/PM/RE/0145 | Monthly Progress Report -02 for the Month of Novmber - 2019 (Rev-02) | 17.01.2020 | S-9-TR-0467/RE
127 | Secondary Survey | 6 | RE | 07.01.2020 | ENC/TR01/PM/RE/0146 | Resubmission of Secondary Survey Control and Leveling Details Report from CH 0+000 to 7+170 (ETR006) Rev-01 |  | S-9-TR-0545/RE
128 | ICS | 171 | RE | 07.01.2020 | ENC/TR01/PM/RE/0149 | Resubmission of Initial Cross Section Drawing from CH 78+300 to 79+000 (ETR171) | 09.01.2020 | S-9-TR-0442/RE | Accepted
129 | Furniture | Type - 2 | RE | 08.01.2022 | ENC/TR01/PM/RE/0151 | Provide Fully furnished House Type - 2 at Alim Nagar Mutur - 02 | 13.01.2020 | S-9-TR-0446/RE
130 | Crack Survey | 171 | RE | 09.01.2025 | ENC/TR01/PM/RE/0154 | Submission of Soft Version of Crack Survey Report from CH 78+300 to 79+685 (ETR171) | 15.02.2020 | S-9-TR-0541/RE S-9-TR-0685/RE | Accepted
131 | Enviromental | No | RE | 09.01.2025 | ENC/TR01/PM/RE/0155 | Monthly Social & Enviromental Safeguard Monitoring Reports -2 for the month of Nov 2019 | 29.02.2020 | S-9-TR-0822/RE
132 | ICS | 171 | RE | 09.01.2025 | ENC/TR01/PM/RE/0156 | Submission of Initial Cross Section Drawing from 79+010 to 80+000 (ETR171) | 25.01.2020 | S-9-TR-0529/RE | Accepted
133 | ICS | 171 | RE | 09.01.2025 | ENC/TR01/PM/RE/0157 | Submission of Initial Cross Section Drawing from 81+000 to 82+000 (ETR171) | 06.02.2020 | S-9-TR-0606/RE | Accepted
134 | Topo | 57 | RE | 11.01.2020 | ENC/TR01/PM/RE/0158 | Submission of Topography Survey Drawing from CH 0+500 to 0+620 km (ETR057) |  | S-9-TR-0544/RE | Accepted
135 | ICS | 171 | RE | 11.01.2020 | ENC/TR01/PM/RE/0159 | Submission of Initial Cross Section Drawing for CH 83+000 to 84+000 (ETR171) | 25.01.2020 | S-9-TR-0528/RE | Accepted
136 | Initial Maintenance | No | RE | 12.01.2020 | ENC/TR01/PM/RE/0160 | Initial Maintenance Competed Roads | 20.01.2020 | S-9-TR-0476/RE
137 | Culvert Report | 6 | RE | 12.01.2020 | ENC/TR01/PM/RE/0161 | Culvert Conditional Report for the Road ETR006 |  | S-9-TR-0587/RE
138 | HA | 171 | RE | 13.01.2020 | ENC/TR01/PM/RE/0162 | Resubmission of Horizontal Alignment Drawing from CH 92+400 to 98+400km ETR171 | 14.01.2020 | S-9-TR-0458/RE
139 | Topo | 70 | RE | 13.01.2020 | ENC/TR01/PM/RE/0163 | Submission of Topography Survey Drawing from 0+000 to 1+600 ETR070 |  | S-9-TR-0582/RE | Accepted
140 | Weather | No | RE | 14.01.2020 | ENC/TR01/PM/RE/0166 | Monthly Test Summary & Weather Record for the Month of Dec 2019 | 20.01.2020 | S-9-TR-0474/RE
141 | Secondary Survey | 165 &131 | RE | 14.01.2020 | ENC/TR01/PM/RE/0167 | Submission of Secondary Survey Control and Leveling Details Report for the Road ID ETR165 & ETR131 |  | S-9-TR-0548/RE
142 | Secondary Survey | 018 & 164 | RE | 14.01.2020 | ENC/TR01/PM/RE/0168 | Submission of Secondary Survey Control and Leveling Details Report for the Road ID ETR018 & ETR164 | 18.01.2020 | S-9-TR-0469/RE
143 | Secondary Survey | 170 | RE | 14.01.2020 | ENC/TR01/PM/RE/0169 | Submission of Secondary Survey Control and Leveling Details Report for the Road ID ETR170 | 15.02.2020 | S-9-TR-0680/RE | Accepted
144 | Topo | 130 | RE | 17.01.2020 | ENC/TR01/PM/RE/0171 | Submission of Topography Survey Drawing from 0+000 to 1+650 ETR 130 |  | S-9-TR-0581/RE | Accepted
145 | HA | 171 | RE | 17.01.2020 | ENC/TR01/PM/RE/0173 | Submission of Horizontal Alignment Drawing from CH 96+000 to 102+000km ETR171 | 28.02.2020 | S-9-TR-0794/RE | Approved as noted
146 | Progress Report | No | RE | 17.01.2020 | ENC/TR01/PM/RE/0174 | Monthly Progress Report - 02 for the Month of October -2019 (Rev02) | 25.01.2020 | S-9-TR-0521/RE
147 | Topo | 132 | RE | 17.01.2020 | ENC/TR01/PM/RE/0175 | Submission of Topography Survey Drawing from 0+000 to 1+560 ETR 132 |  | S-9-TR-0566/RE | Accepted
148 | Pavement Design | 171 | RE | 18.01.2020 | ENC/TR01/PM/RE/0179 | Submission of Pavement Design for CH 78+240 to 88+500 ETR171 |  | S-9-TR-0536/RE
149 | Progress Report | No | RE | 18.01.2020 | ENC/TR01/PM/RE/0180 | Monthly Progress Report - 02 for the Month of Novemeber - 2019 (Rev-02) |  | 467
150 | Secondary Survey | 58 | RE | 18.01.2020 | ENC/TR01/PM/RE/0181 | Submission of Secondary Survey Control and Leveling Details Report ETR058 | 15.02.2020 | S-9-TR-0684/RE | Accepted
151 | Source Approval | No | RE | 18.01.2020 | ENC/TR01/PM/RE/0182 | Submission for Source Approval of Embankment Material at Kumara Barrow pit, Peeliyadi |  | S-9-TR-0525/RE
152 | Source Approval | No | RE | 18.01.2020 | ENC/TR01/PM/RE/0183 | Resubmission for Source Approval of ABC & 20mm Aggregate |  | S-9-TR-0527/RE
153 | Crack Survey | 130 | RE | 18.01.2020 | ENC/TR01/PM/RE/0184 | Submission of Crack Survey Report from 0+000 to 1+410 ETR130 | 15.02.2020 | S-9-TR-0685/RE | Accepted
154 | Name Board | No | RE | 18.01.2020 | ENC/TR01/PM/RE/0185 | Submission of Details of Complaint Box |  | S-9-TR-0530/RE
155 | Culvert Report | 57 | RE | 18.01.2020 | ENC/TR01/PM/RE/0186 | Culvert Conditional Report for the Road ETR057 | 23.01.2020 | S-9-TR-0499/RE
156 | Culvert Drawing | 171 | RE | 18.01.2020 | ENC/TR01/PM/RE/0187 | Submission of Culvert Drawing 93-3 and 93-4 ETR171 | 24.01.2020 | S-9-TR-0519/RE
157 | Topo | 131 | RE | 21.01.2020 | ENC/TR01/PM/RE/0188 | Submission of Topography Survey Drawing from 0+000 to 1+120 (ETR131) |  | S-9-TR-0567/RE | Accepted
158 | Topo | 165 | RE | 21.01.2020 | ENC/TR01/PM/RE/0189 | Submission of Topography Survey Drawing from 0+000 to 1+360 (ETR165) |  | S-9-TR-0565/RE | Accepted
159 | Topo | 18 & 164 | RE | 21.01.2020 | ENC/TR01/PM/RE/0190 | Submission of Topography Survey Drawing for ETR018 CH 0+000 to 1+880km and ETR 164 CH 0+000 to 1+170km |  | S-9-TR-0564/RE | Accepted
160 | HA | 57 | RE | 21.01.2020 | ENC/TR01/PM/RE/0191 | Submission of Horizontal Alignment Drawing from 00+000 to 00+620 (ETR057) | 22.01.2020 | S-9-TR-0494/RE
161 | Source Approval | No | RE | 22.01.2020 | ENC/TR01/PM/GEN/0194 | Requesting for Testing of 20mm Aggregate from Shan Metal Crusher | 04.04.2020 | 1002
162 | Source Approval | No | RE | 22.01.2020 | ENC/TR01/PM/GEN/0195 | Requesting for Testing of Bitumen Emulsion - CSS1, SRS1, MC-30 from Bitumix |  | pending
163 | Source Approval | No | RE | 22.01.2020 | ENC/TR01/PM/GEN/0196 | Requesting for Testing River Sand |  | pending
164 | Source Approval | No | RE | 22.01.2020 | ENC/TR01/PM/GEN/0197 | Requesting for Material Testing for Lanwa Steel Bars of 10mm & 12mm dia. |  | pending
165 | Progress Report | No | RE | 22.01.2020 | ENC/TR01/PM/RE/0198 | Monthly Progress Report for the Month of December – 2019 |  | S-9-TR-0560/RE
166 | HA | 166 | RE | 22.01.2020 | ENC/TR01/PM/RE/0199 | Submission of Horizontal Alignment Drawing from CH 0+000 to 4+233.333km (ETR166) | 25.02.2020 | S-9-TR-0779/RE | Approved as noted
167 | Culvert Drawing | 57 | RE | 22.01.2020 | ENC/TR01/PM/RE/0200 | Submission of Culvert Drawing 11 at CH 0+287 (ETR057) | 25.01.2020 | S-9-TR-0514/RE
168 | ICS | 171 | RE | 22.01.2020 | ENC/TR01/PM/RE/0201 | Submission of Initial Cross Section Drawing for CH 80+000 to 81+000 (ETR171) | 22.02.2020 | S-9-TR-0742/RE | Accepted
169 | IPA | No | RE | 22.01.2020 | ENC/TR01/PM/RE/0202 | Interim Payment Application – 04 for the Month December 2019 | 18.02.2020 | S-9-TR-0692/RE | Return
170 | Topo | 58 | RE | 22.01.2020 | ENC/TR01/PM/RE/0203 | Submission of Topography Survey Drawing from 00+000 to 00+510 (ETR058) |  | S-9-TR-0569/RE | Accepted
171 | Pavement Design | 57 | RE | 22.01.2020 | ENC/TR01/PM/RE/0204 | Submission of Pavement Design for CH 0+000 to 0+620 (ETR057) | 24.01.2020 | S-9-TR-0507/RE
172 | Engineer's Staff | No | RE | 22.01.2020 | ENC/TR01/PM/RE/0205 | Submission of Operatives for the Engineer's Staff of Clerk Ms. H. Priyanghe |  | pending
173 | HA | 130 | RE | 22.01.2020 | ENC/TR01/PM/RE/0206 | Submission of Horizontal Alignment Drawing from CH 0+000 to 1+633.996km (ETR130) | 07.02.2020 | S-9-TR-0615/RE | Approved as noted
174 | Source Approval | No | RE | 23.01.2020 | ENC/TR01/PM/RE/0209 | Requesting for Quotation for River Sand for Concrete work |  | pending
175 | Source Approval | No | RE | 23.01.2020 | ENC/TR01/PM/RE/0212 | Submission for Source Approval of Shoulder Material of Piyal Barrow Pit at Iluppankulam. |  | S-9-TR-0554/RE
176 | Source Approval | No | RE | 23.01.2020 | ENC/TR01/PM/RE/0213 | Submission for Source Approval of Shoulder Material of Kumara Barrow Pit at Peeliyadi. |  | S-9-TR-0555/RE
177 | Enviromental | 57 | RE | 23.01.2020 | ENC/TR01/PM/RE/0214 | Submission of Activity Checklist Social Aspects (ACSA) ETR057. |  | pending
178 | Secondary Survey | 054, 059 & 066 | RE | 23.01.2020 | ENC/TR01/PM/RE/0215 | Submission of Secondary Survey Control and Leveling Details Report for the Road ID ETR056 & ETR059 & ETR066 |  | S-9-TR-0574/RE
179 | Source Approval | No | RE | 24.01.2020 | ENC/TR01/PM/RE/0217 | Submission for Source Approval of NP2 Hume Pipes of Diameter 45mm, 600mm, 900mm from ICC Madapatha Pre Cast Yard | 07.02.2020 | S-9-TR-0613/RE | Approved
180 | Source Approval | No | RE | 24.01.2020 | ENC/TR01/PM/RE/0218 | Submission for Source Approval of GTB Reinforcement Material |  | S-9-TR-0559/RE
181 | Source Approval | No | RE | 24.01.2020 | ENC/TR01/PM/RE/0219 | Submission for Source Approval of Melwa Reinforcement Material |  | S-9-TR-0559/RE
182 | Topo | 66 | RE | 24.01.2020 | ENC/TR01/PM/RE/0220 | Submission of Topography Survey Drawing from 00+000 to 00+610 (ETR066) |  | S-9-TR-0583/RE | Accepted
183 | Topo | 59 | RE | 24.01.2020 | ENC/TR01/PM/RE/0221 | Submission of Topography Survey Drawing from 00+000 to 00+560 (ETR059) |  | S-9-TR-0568/RE | Accepted
184 | Source Approval | No | RE | 24.01.2020 | ENC/TR01/PM/RE/0222 | Submission for Source Approval of Captain Steel |  | S-9-TR-0557/RE
185 | Culvert Drawing | 57 | RE | 25.01.2020 | ENC/TR01/PM/RE/0223 | Resubmission of Culvert Drawing 11 at CH 0+289.5 (ETR057) |  | S-9-TR-0535/RE
186 | Initial Maintenance | No | RE | 25.01.2020 | ENC/TR01/PM/RE/0224 | Initial Maintenance Completed Roads |  | S-9-TR-0537/RE
187 | Source Approval | No | RE | 25.01.2020 | ENC/TR01/PM/RE/0225 | Submission for Source Approval of Tokyo Super Cement | 11.02.2020 | S-9-TR-0635/RE | Approved
188 | Source Approval | No | RE | 25.01.2020 | ENC/TR01/PM/RE/0226 | Submission for Source Approval of NP2 Hume Pipe - ICC | 07.02.2020 | S-9-TR-0614/RE | Approved
189 | Source Approval | No | RE | 25.01.2020 | ENC/TR01/PM/RE/0227 | Submission for Source Approval of Cold Mix Material at Edward and Christie | 06.02.2020 | S-9-TR-0588/RE | Accepted
190 | HA | 127 | RE | 26.01.2020 | ENC/TR01/PM/RE/0228 | Submission of Horizontal Alignment Drawing from 00+000 to 1+022.170 (ETR127) | 11.02.2020 | S-9-TR-0646/RE | Approved as noted
191 | Engineer's Staff | No | RE | 27.01.2020 | ENC/TR01/PM/RE/0229 | Provision of Operatives for the Engineer’s Staff of Clerk, Ms. R. Rushanthika |  | S-9-TR-0539/RE
192 | ICS | 57 | RE | 27.01.2020 | ENC/TR01/PM/RE/0231 | Submission of Initial Cross Section Drawing from 00+000 to 00+621.51 (ETR057) | 15.02.2020 | S-9-TR-0683/RE | Accepted
193 | Pavement Design | 58 | RE | 27.01.2020 | ENC/TR01/PM/RE/0232 | Submission of Pavement Design Report for CH 0+000 to 0+520 (ETR058) | 07.02.2020 | S-9-TR-0618/RE | Approved
194 | Secondary Survey | 54 | RE | 27.01.2020 | ENC/TR01/PM/RE/0234 | Submission of Secondary Survey Control and Leveling Details Report (ETR054) |  | S-9-TR-0575/RE
195 | Pavement Design | 57 | RE | 27.01.2020 | ENC/TR01/PM/RE/0235 | Resubmission of Pavement Design for CH 0+000 to 0+620 (ETR057) | 06.02.2020 | S-9-TR-0592/RE | Re Submit
196 | Source Approval | No | RE | 27.01.2020 | ENC/TR01/PM/RE/0236 | Submission for Concrete Mix Design of Grade 25-20 |  | S-9-TR-0561/RE
197 | Source Approval | No | RE | 27.01.2020 | ENC/TR01/PM/RE/0237 | Submission for Source Approval of 20mm Aggregate from Edward and Christie- Wadakada crusher plant | 07.02.2020 | S-9-TR-0608/RE | Conditionally Approved
198 | Source Approval | 171 | RE | 27.01.2020 | ENC/TR01/PM/RE/0238 | Submission for Source Approval of Water Sample from Mutur National Water Supply Drainage Board and Mavilaru Water Channel at the location of 902 Culvert on A-15 Road |  | S-9-TR-0570/RE
199 | Sanitary | Type - 2 | RE | 27.01.2020 | ENC/TR01/PM/RE/0239 | Provided Sanitary items for Type 2 House |  | S-9-TR-0538/RE
200 | Source Approval | No | RE | 27.01.2020 | ENC/TR01/PM/RE/0240 | Submission for Source Approval of Rubble at Parakrama Quarry | 07.02.2020 | S-9-TR-0612/RE | Initial Approved
201 | Source Approval | No | RE | 27.01.2020 | ENC/TR01/PM/RE/0241 | Submission for Source Approval of Lanwa Reinforcement Material |  | S-9-TR-0559/RE
202 | Source Approval | No | RE | 28.01.2020 | ENC/TR01/PM/RE/0242 | Resubmission for Source Approval of CRSI. CSS1. MC-30 and 60-70Pen Bitumen of Bitumix Brand | 06.02.2020 | S-9-TR-0589/RE | Approved as noted
203 | Source Approval | No | RE | 28.01.2020 | ENC/TR01/PM/RE/0243 | Resubmission for Source Approval of CRSI. CSS1. MC-30 and 60-70Pen Bitumen of Bitulink Brand | 06.02.2020 | S-9-TR-0594/RE | Approved as noted
204 | Pavement Design | 130 | RE | 28.01.2020 | ENC/TR01/PM/RE/0244 | Submission of Pavement Design Report for CH 0+000 to 1+630 (ETR130) | 07.02.2020 | S-9-TR-0621/RE | Approved
205 | Secondary Survey | 133 | RE | 28.01.2020 | ENC/TR01/PM/RE/0245 | Submission of Secondary Survey Control and Leveling Details Report (ETR133) | 03.02.2020 | S-9-TR-0584/RE
206 | Source Approval | No | RE | 31.01.2020 | ENC/TR01/PM/RE/0247 | Requesting to Approval of Concrete Mix Design of Grade 15, 25, 30 from Tokyo Supermix-Trincomalee | 10.02.2020 | S-9-TR-0632/RE | Re Submit
207 | Source Approval | No | RE | 31.01.2020 | ENC/TR01/PM/RE/0248 | Submission for Concrete Mix Design of Grade 15(20) | 06.02.2020 | S-9-TR-0593/RE
208 | Source Approval | No | RE | 31.01.2020 | ENC/TR01/PM/RE/0249 | Submission for Concrete Mix Design of Grade 20/20 | 06.02.2020 | S-9-TR-0593/RE
209 | Source Approval | No | RE | 31.01.2020 | ENC/TR01/PM/RE/0251 | Submission for Source Approval of Sand from GSMB Stock Yard at Sooriyapura | 11.02.2020 | S-9-TR-0639/RE | Re Submit
210 | Secondary Survey | 67 | RE | 31.01.2020 | ENC/TR01/PM/RE/0252 | Submission of Secondary Survey Control and Leveling Details Report (ETR067) | 06.02.2020 | S-9-TR-0603/RE | Accepted
211 | Source Approval | No | RE | 31.01.2020 | ENC/TR01/PM/RE/0253 | Submission for Source Approval of Admixtures for Concreting from Chryso Lanka & Curing Agent | 11.02.2020 | S-9-TR-0638/RE | Re Submit
212 | Source Approval | No | RE | 31.01.2020 | ENC/TR01/PM/RE/0254 | Submission for Source Approval of Hume Pipe for the dia 300mm, 450mm, 600mm and 750mm from the source of Kavya Enterprises | 14.02.2020 | S-9-TR-0667/RE | Re Submit
213 | Source Approval | No | RE | 31.01.2020 | ENC/TR01/PM/RE/0255 | Submission for Source Approval of Admixtures for Concreting from Finex Engineering | 11.02.2020 | S-9-TR-0640/RE | Re Submit
214 | Topo | 56 | RE | 31.01.2020 | ENC/TR01/PM/RE/0256 | Submission of Topography Survey Drawing from 00+000 to 00+670 (ETR056) | 28.02.2020 | S-9-TR-0796/RE | Accepted
215 | Culvert Report | 127 | RE | 31.01.2020 | ENC/TR01/PM/RE/0257 | Culvert Conditional Report for the Road ETR127 | 05.02.2020 | S-9-TR-0586/RE
216 | Gentral | No | GEN | 31.01.2020 | ENC/TR01/PM/GEN/0258 | Request to permit to Barrow Gravel from your Land at Sumedhankarapura, Trincomalee |  | pending
217 | Crack Survey | 171 | RE | 31.01.2020 | ENC/TR01/PM/RE/0259 | Submission of Crack Survey Report from CH 79+685 to 79+870 km (ETR171) | 05.03.2020 | S-20-TR-0847/RE
218 | Crack Survey | 57 | RE | 02.01.2020 | ENC/TR01/PM/RE/0260 | Submission of Crack Survey Report from CH 0+000 to 0+620km (ETR057) | 29.04.2020 | S-20-TR-1011/RE | Conditionally Approved
219 | Road close | 57 | RE | 02.02.2020 | ENC/TR01/PM/RE/0261 | Request to close the road for a short period at the culvert 1/1 on ETR057 | 11.02.2020 | S-9-TR-0650/RE | DTL Comments with RE
220 | Source Approval | No | RE | 02.02.2020 | ENC/TR01/PM/RE/0262 | Request to permit to Barrow Gravel from your Land at Sumedhankarapura, Trincomalee |  | pending
221 | Culvert Report | 130 | RE | 02.02.2020 | ENC/TR01/PM/RE/0263 | Culvert Conditional Report for the Road ETR130 | 10.02.2020 | S-9-TR-0631/RE | Comments
222 | Secondary Survey | 60 | RE | 03.02.2020 | ENC/TR01/PM/RE/0264 | Submission of Secondary Survey Control and Leveling Details Report (ETR060) | 06.02.2020 | S-9-TR-0598/RE | Accepted
223 | Secondary Survey | 161 | RE | 03.02.2020 | ENC/TR01/PM/RE/0265 | Submission of Secondary Survey Control and Leveling Details Report (ETR061) | 06.02.2020 | S-9-TR-0602/RE | Accepted
224 | Secondary Survey | 69 | RE | 03.02.2020 | ENC/TR01/PM/RE/0266 | Submission of Secondary Survey Control and Leveling Details Report (ETR069) | 06.02.2020 | S-9-TR-0604/RE | Accepted
225 | Secondary Survey | 051 & 155 | RE | 03.02.2020 | ENC/TR01/PM/RE/0267 | Submission of Secondary Survey Control and Leveling Details Reports (ETR051 & ETR155) | 21.02.2020 | S-9-TR-0736/RE
226 | Secondary Survey | 55 | RE | 03.02.2020 | ENC/TR01/PM/RE/0268 | Submission of Secondary Survey Control and Leveling Details Report (ETR055) | 06.02.2020 | S-9-TR-0597/RE | Accepted
227 | Culvert Report | 166 | RE | 03.02.2020 | ENC/TR01/PM/RE/0269 | Culvert Conditional Report for the Road ETR166 | 11.02.2020 | S-9-TR-0648/RE | Approved
228 | Topo | 54 | RE | 03.02.2020 | ENC/TR01/PM/RE/0270 | Submission of Topography Survey Drawing from 00+000 to 00+490 (ETR054) | 28.02.2020 | S-9-TR-0799/RE | Accepted
229 | Culvert Drawing | 127 | RE | 03.02.2020 | ENC/TR01/PM/RE/0271 | Submission of Encasement Contraction Drawing at CH 0+818.30 (ETR127) |  | S-9-TR-0601/RE | Approved as noted
230 | Culvert Drawing | 57 | RE | 03.02.2020 | ENC/TR01/PM/RE/0272 | Submission of Box Culvert Reconstruction Drawing at CH 0+613.30 (ETR057) | 06.02.2020 | S-9-TR-0600/RE | Re Submit
231 | Insurance | No | TL | No Doc | ENC/PM/TL/TR-1/GEN/0002 | Constractor's Submittal of Draft Insurance Documents - Engineer's Review & Response |  | S-9-0124/JR
232 | Insurance | No | TL | 11.09.2019 | ENC/PM/TL/TR-1/GEN/0003 | Project Insurance |  | Pending
233 | SSEMAP | No | TL | 02.10.2019 | ENC/PM/TL/TR-1/GEN/0004 | Submission of Enviromental Management Action Plan (EMAP) |  | S-9-0313/JR
234 | Contractor's Staff | No | TL | 09.10.2019 | ENC/PM/TL/TR-1/GEN/0005 | Submission of Proposal for Material Engineer (Mr. NS. Liyanage) |  | S-9-0319/JR
235 | Contractor's Staff | No | TL | 10.10.2019 | ENC/PM/TL/TR-1/GEN/0006 | Submission of Proposal for Contractor's Staff |  | S-9-TR-0086/RE
236 | QAMP | No | TL | 12.10.2019 | ENC/PM/TL/TR-1/GEN/0007 | Submission of Quality Assurence Plan |  | S-9-0431/JR
237 | OH&STMP | No | TL | 06.09.2019 | ENC/PM/TL/TR-1/GEN/0008 | Submission of Health, Safty and Traffic Management Plan |  | S-9-0341/JR
238 | Contractor's Staff | No | TL | 01.11.2019 | ENC/PM/TL/TR-1/GEN/0009 | Submission of Proposal for Material Engineer (Mr. NS. Liyanage) |  | S-9-0319/JR
239 | TW | No | TL | 04.11.2019 | ENC/PM/TL/TR-1/GEN/0010 | Submission of Transect Walk Records |  | Want to Reply RE
240 | Contractor's Staff | No | TL | 07.11.2019 | ENC/PM/TL/TR-1/GEN/0011 | Submission of Proposal for Contractor's Staff (Stuctural Enagineer) |  | S-9-0467/JR
241 | Contractor's Staff | No | TL | 08.11.2019 | ENC/PM/TL/TR-1/GEN/0012 | Submission of Proposal for Contractor's Staff (Highway Enagineer) |  | S-9-0468/JR
242 | Contractor's Staff | No | TL | 10.11.2019 | ENC/PM/TL/TR-1/GEN/0013 | Submission of Proposal for Contractor's Staff |  | S-9-0484/DTL
243 | Variation | No | TL | 14.11.2019 | ENC/PM/TL/TR-1/GEN/0014 | Confirmation of Quantity Variation |  | Want to Reply RE
244 | OH&STMP | No | TL | 14.11.2019 | ENC/PM/TL/TR-1/GEN/0015 | Resubmission of Occupational Health and Safety & Traffic Management Plan |  | S-9-0539/JR
245 | SSEMAP | No | TL | 22.11.2019 | ENC/TR01/PM/TL/0061 | Resubmission of Enviromental Management Action Plan (EMAP) |  | S-9-0550/JR | Approved
246 | Office | No | TL | 25.11.2019 | ENC/TR01/PM/TL/0065 | Information of Contractor's Project Office Location Changed |  | NNR
247 | Yard | No | TL | 25.11.2019 | ENC/TR01/PM/TL/0066 | Submission of Stock Yard and Disposal Yard with Method Statement |  | S-9-TR-0362/RE
248 | QAMP | No | TL | 26.11.2019 | ENC/TR01/PM/TL/0068 | Submission of Quality Management Assurence System (Rev.01) | 11.01.2020 | S-9-TR-0760/DTL
249 | Insurance | No | TL | 29.11.2019 | ENC/TR01/PM/TL/0079 | Extended Insurance Policy | 20.02.2020 | S-20-1022/JR
250 | TW | No | TL | 29.11.2019 | ENC/TR01/PM/TL/0080 | Submission of Transect Walk Records [ETR171,ETR130] |  | Want to Reply RE
251 | Contractor's Staff | No | TL | 04.12.2019 | ENC/TR01/PM/TL/0093 | Submission of Proposal for Contractor's Staff (Mr. Navaneethan/ Mr. Anuruddha) |  | S-9-0629/DTL
252 | TW | 171 | TL | 04.12.2019 | ENC/TR01/PM/TL/0094 | Submission of Transect Walk Records [ETR171-6] |  | Want to Reply RE
253 | Pavement Design | No | TL | 16.12.2019 | ENC/TR01/PM/TL/0117 | List of Participant for Workshop on Machanistic-Empirical Pavement Design 17, 18, & 19 of Dec 2019 |  | NNR
254 | Pavement Design | No | TL | 16.12.2019 | ENC/TR01/PM/TL/0120 | List of Participant for Workshop on Mechanistic-Empirical Pavement Design 17, 18, & 19 of Dec 2019 |  | NNR
255 | Other ORG | 53 | TL | 17.12.2019 | ENC/TR01/PM/TL/0122 | Information of Constructed by Other Organizations of ETR053 |  | NNR
256 | TW | 171 | TL | 18.12.2019 | ENC/TR01/PM/TL/0125 | Submission of Transect Walk Records |  | Want to Reply RE
257 | Contractor's Staff | No | TL | 19.12.2019 | ENC/TR01/PM/TL/0128 | Submission of Proposal for Contractor's Staff (SDE Mr.Kajanthan) | 20.12.2019 | S-9-0671/DTL
258 | Emergency | 171 | TL | 24.12.2019 | ENC/TR01/PM/TL/0130 | Information of Emergency Work due to the flood on A15 Road |  | NNR
259 | SSEMAP | No | TL | 24.12.2019 | ENC/TR01/PM/TL/0131 | Submission of Site Specific Enviromental Management Action Plan (SSEMAP) |  | S-9-0824/JR
260 | Contractor's Staff | No | TL | 26.12.2019 | ENC/TR01/PM/TL/0132 | Submission of proposal for Contractor's Staff ESO QS |  | pending
261 | Work Program | No | TL | 27.12.2019 | ENC/TR01/PM/TL/0136 | Contractor’s Approved Work Program (Rev 03) - Comments for Agreement of Planned S- Curve for Monitoring |  | pending
262 | Progress Report | No | TL | 06.01.2020 | ENC/TR01/PM/TL/0145 | Monthly Progress Report -02 for the Month of Novmber - 2019 (Rev-02) |  | pending
263 | Contractor's Staff | No | TL | 07.01.2020 | ENC/TR01/PM/TL/0147 | Submission of Proposal for Contractor's Staff of HDE Mr. K. Apilas | 08.01.2020 | S-9-0736/DTL
264 | Contractor's Staff | No | TL | 07.01.2020 | ENC/TR01/PM/TL/0148 | Submission of Proposal for Contractor's Staff |  | pending
265 | Contractor's Staff | No | TL | 08.01.2020 | ENC/TR01/PM/TL/0150 | Submission of Degree & Experience Certificates for Contractor's Staff of Mr. A.Sadiq HDE |  | pending
266 | Yard | No | TL | 08.01.2020 | ENC/TR01/PM/TL/0152 | Submission of Stock Yard and Disposal Yard with method statement | 19.02.2020 | S-9-TR-0702/RE
267 | SSEMAP | No | TL | 09.01.2020 | ENC/TR01/PM/TL/0153 | Submission of Site Specific Enviromental Management Action Plan (SSEMAP) |  | S-9-0824/JR
268 | OH&STMP | No | TL | 14.01.2020 | ENC/TR01/PM/TL/0164 | Resubmission of Health, Safety and Traffic Management Plan (Rev-2) |  | S-9-0816/JR
269 | Baseline | No | TL | 14.01.2020 | ENC/TR01/PM/TL/0165 | Submission of Baseline Monitoring Data |  | pending
270 | SSEMAP | No | TL | 16.01.2020 | ENC/TR01/PM/TL/0170 | Submission of Site Specific Enviromental Management Action Plan (SSEMAP) |  | pending
271 | TW | 70, 154, 131, 051, 134 | TL | 17.01.2019 | ENC/TR01/PM/TL/0172 | Submission of Transect Walk Records ETR 070,154,131,051,134 |  | Want to Reply RE
272 | SSEMAP | No | TL | 17.01.2019 | ENC/TR01/PM/TL/0176 | Submission of Copies of Enviromental Mangement Action Plan EMAP |  | pending
273 | Work Program | No | TL | 17.01.2019 | ENC/TR01/PM/TL/0177 | Submission of 04 CDs of Work Program |  | pending
274 | OH&OHSTM | No | TL | 18.01.2020 | ENC/TR01/PM/TL/0178 | Submission of Copies of Occupational Health, Safety and Traffic Mnanagment Plan |  | pending
275 | TW | 171, 057 | TL | 22.01.2020 | ENC/TR01/PM/TL/0192 | Submission of Transect Walk Records ETR 171,057 |  | Want to Reply RE
276 | Culvert Drawing | No | TL | 22.01.2020 | ENC/TR01/PM/TL/0193 | Requesting for Approval of Typing Culvert Drawing | 25.01.2020 | S-9-0828/DTL | No Objection
277 | SSEMAP | 57 | TL | 23.01.2020 | ENC/TR01/PM/TL/0207 | Submission of Site Specific Environmental Management Action Plan (SSEMAP) ETR057 |  | pending
278 | SSEMAP | 130 | TL | 23.01.2020 | ENC/TR01/PM/TL/0208 | Submission of Site Specific Environmental Management Action Plan (SSEMAP) ETR130 |  | pending
279 | EMC | 57 | TL | 23.01.2020 | ENC/TR01/PM/TL/0210 | Submission of Environmental Monitoring Checklist (EMC) ETR057 |  | pending
280 | EMC | 130 | TL | 23.01.2020 | ENC/TR01/PM/TL/0211 | Submission of Environmental Monitoring Checklist (EMC) ETR130 |  | pending
281 | TW | 060, 054, 156, 069, 055, 063, 068 | TL | 24.01.2020 | ENC/TR01/PM/TL/0216 | Submission of Transect Walk Records |  | Want to Reply RE
282 | QAMP | No | TL | 27.01.2020 | ENC/TR01/PM/TL/0230 | Resubmission of Quality Management Assurance System (Rev-01) | 11.01.2020 | S-9-TR-0760/DTL
283 | Baseline | No | TL | 30.01.2020 | ENC/TR01/PM/TL/0246 | Submission of Quotation for Baseline Survey | 10.02.2020 | S-9-0934/DTL | Accepted for use
284 | Control Traverse | 171 | RE | 03.09.2019 | PM/iRd/TR-1/RE/GEN/002 | Control Travers Surveying (ETR171) |  | S-9-TR-0013/RE
285 | Investigation | 6 | RE | 29.08.2019 | PM/iRd/TR-1/RE/GEN/001 | Current Status of Geotechnical Investigation (ETR006) | NNR | TL/DTL
286 | Contractor's Staff | No | TL | 16.02.2020 | ENC/TR01/PM/TL/0333 | Submission of Proposal for Contractor’s Staff (Robin/Jatheesan) | 22.02.2020 | S-20-1039/DTL | Non-Key Position Ofc.Engi
287 | Contractor's Staff | No | TL | 16.02.2020 | ENC/TR01/PM/TL/0328 | Submission of Educational Certificates & Experience Certificates for Contractor’s Staffs |  | Pending
288 | TW | 18164133 | TL | 10.02.2020 | ENC/TR01/PM/TL/0300 | Submission of Transect Walk Records |  | pending
289 | TW | Some | TL | 06.02.2020 | ENC/TR01/PM/TL/0279 | Submission of Transect Walk Records |  | Want to Reply RE
290 | VA | 171 | RE | 18.02.2020 | ENC/TR01/PM/RE/0345 | Submission of Vertical Alignment Drawing from 83+200 to 84+600 (ETR171) | 25.02.2020 | S-9-TR-0780/RE | Approved
291 | VA | 57 | RE | 18.02.2020 | ENC/TR01/PM/RE/0344 | Submission of Vertical Alignment Drawing from 0+000 to 0+613.30 (ETR057) | 28.02.2020 | S-9-TR-0789/RE | Approved as noted
292 | Topo | 170 | RE | 18.02.2020 | ENC/TR01/PM/RE/0343 | Submission of Topography Survey Drawing from 0+000 to 4+520 (ETR170) | 11.03.2020 | S-20-TR-0869/RE | Accepted
293 | Gentral | No | RE | 18.02.2020 | ENC/TR01/PM/RE/0342 | Requesting the quotation for Replaced the Damaged Electric Post (Support post) |  | Pending
294 | Topo | 16 | RE | 18.02.2020 | ENC/TR01/PM/RE/0341 | Submission of Topography Survey Drawing from 0+000 to 4+600 (ETR016) | 21.02.2020 | S-9-TR-0734/RE
295 | DCS | 130 | RE | 18.02.2020 | ENC/TR01/PM/RE/0340 | Submission of Design Cross Section Drawings from CH 1+000 to 1+440km (ETR130) | 13.03.2020 | S-9-TR-0910/RE | App/ReSub
296 | Pavement Design | 59 | RE | 17.02.2020 | ENC/TR01/PM/RE/0339 | Submission of Pavement Design Report for CH 0+000 to 0+530 (ETR059) | 24.02.2020 | S-9-TR-0767/RE
297 | Pavement Design | 60 | RE | 17.02.2020 | ENC/TR01/PM/RE/0338 | Submission of Pavement Design Report for CH 0+000 to 0+470 (ETR060) | 24.02.2020 | S-9-TR-0768/RE
298 | DCS | 130 | RE | 17.02.2020 | ENC/TR01/PM/RE/0337 | Submission of Design Cross Section Drawings from CH 0+030 to 1+000km (ETR130) | 21.02.2020 | S-9-TR-0728/RE
299 | Drain Schedule | 57 | RE | 16.02.2020 | ENC/TR01/PM/RE/0336 | Drain Schedule for Kiliveddy West Road (ETR 057) | 27.02.2020 | S-9-TR-0791/RE | Comments
300 | Crack Survey | 131 | RE | 16.02.2020 | ENC/TR01/PM/RE/0335 | Submission of Crack Survey Report from CH 0+000 to 1+120km (ETR131) | 05.03.2020 | S-20-TR-0847/RE
301 | Culvert Report | 130 | RE | 16.02.2020 | ENC/TR01/PM/RE/0334 | Conditional Report of Existing Culverts on ETR130, Mankala Bokku Road | 22.02.2020 | S-20-1041/DTL
302 | Source Approval | No | RE | 16.02.2020 | ENC/TR01/PM/RE/0332 | Submission for Source Approval of ABC & 20mm Aggregate from Southern Group Metal Crusher at Welgamwehara | 20.02.2020 | S-9-TR-0717/RE
303 | Increase Road | 130 | RE | 16.02.2020 | ENC/TR01/PM/RE/0331 | Request to Increase Road Length from 1.410 km to 1.644 km of the Road ETR130, Mankala Bokku Road, Seruvila P.S | 22.02.2020 | S-20-1040/DTL
304 | HA | 164 | RE | 16.02.2020 | ENC/TR01/PM/RE/0330 | Submission of Horizontal Alignment Drawings from 00+000 to 1+500.000km (ETR164) | 27.04.2020 13.06.2020 | S-20-TR-1087/RE S-20-TR-1496/RE | Approved as noted
305 | HA | 18 | RE | 16.02.2020 | ENC/TR01/PM/RE/0329 | Submission of Horizontal Alignment Drawing from 00+000 to 1+901.477km (ETR018) | 09.05.2020 | S-20-TR-1147/RE S-20-TR-1505/RE | Approved as noted
306 | Source Approval | No | RE | 15.02.2020 | ENC/TR01/PM/RE/0327 | Submission for Source Approval of 20mm Aggregate from Edward and Christie- Wadakada Crusher Plant | 22.02.2020 | S-9-TR-0741/RE
307 | Source Approval | No | RE | 15.02.2020 | ENC/TR01/PM/RE/0326 | Submission for Concrete Mix Design of Grade 15, 25 & 20 from Tokyo Supermix -Trincomalee | 22.02.2020 | S-9-TR-0757/RE
308 | Progress Report | No | RE | 15.02.2020 | ENC/TR01/PM/RE/0324 | Monthly Progress Report for the Month of January – 2020 | 25.02.2020 | S-9-TR-0774/RE
309 | Pavement Design | 127 | RE | 14.02.2020 | ENC/TR01/PM/RE/0323 | Submission of Pavement Design Report for CH 0+000 to 0+984 (ETR127) | 18.02.2020 | S-9-TR-0698/RE | Approved
310 | HA | 70 | RE | 14.02.2020 | ENC/TR01/PM/RE/0322 | Submission of Horizontal Alignment Drawing from 0+000 to 1+595km (ETR070) | 18.05.2020 | S-20-TR-1215/RE S-20-TR-1455/RE | Approved as noted
311 | Road close | 127 | RE | 14.02.2020 | ENC/TR01/PM/RE/0321 | Request to close the road for a short period at the culvert 1/3 on ETR127 | 24.02.2020 | S-9-TR-0763/RE
312 | Source Approval | No | RE | 14.02.2020 | ENC/TR01/PM/RE/0320 | Submission for ABC from Gagana Metal Crusher at Padhaviya | 20.02.2020 | S-9-TR-0719/RE
313 | Crack Survey | 127 | RE | 13.02.2020 | ENC/TR01/PM/RE/0319 | Submission of Crack Survey Report from CH 0+000 to 0+984 km (ETR0127) | 15.04.2020 | S-9-TR-1030/RE
314 | Topo | 67 | RE | 14.02.2020 | ENC/TR01/PM/RE/0318 | Submission of Topography Survey Drawing from 0+000 to 0+580 (ETR067) | 21.02.2020 | S-9-TR-0730/RE
315 | Topo | 6 | RE | 14.02.2020 | ENC/TR01/PM/RE/0317 | Submission of Topography Survey Drawing from 0+000 to 7+200 (ETR006) | 28.02.2020 | S-9-TR-0801/RE | Accepted
316 | Method Statement | No | RE | 14.02.2020 | ENC/TR01/PM/RE/0316 | Submission of Method Statement for Base Failure Section of Compactable, Suitable sub grade | 20.02.2020 | S-9-TR-0722/RE | Re Submit
317 | Pavement Design | 131 | RE | 12.02.2020 | ENC/TR01/PM/RE/0315 | Submission of Pavement Design Report for ETR131 of Section I&II from CH 0+000 to 0+630 and 0+000 to 0+270km | 11.03.2020 | S-9-TR-0872/RE | Approved
318 | Topo | 64 | RE | 12.02.2020 | ENC/TR01/PM/RE/0314 | Submission of Topography Survey Drawing from 0+000 to 0+361 (ETR064) | 21.02.2020 | S-9-TR-0733/RE | Accepted
319 | HA | 58 | RE | 12.02.2020 | ENC/TR01/PM/RE/0313 | Submission of Horizontal Alignment Drawing from 0+000 to 0+542.765km (ETR058) | 26.02.2020 | S-9-TR-0781RE | Approved as noted
320 | Pavement Design | 57 | RE | 12.02.2020 | ENC/TR01/PM/RE/0312 | Resubmission of Pavement Desgin ETR057 for 0+000 to 0+620km | 13.02.2020 | S-9-TR-0656/RE | Approved
321 | Topo | 60 | RE | 11.02.2020 | ENC/TR01/PM/RE/0311 | Submission of Topography Survey Drawing from 0+000 to 0+700 (ETR060) | 28.02.2020 | S-9-TR-0798/RE | Accepted
322 | VA | 130 | RE | 11.02.2020 | ENC/TR01/PM/RE/0310 | Submission of Vertical Alignment Drawing from 0+000 to 1+644.8 (ETR130) | 15.02.2020 | S-9-TR-0673/RE | Approved as noted
323 | Pavement Design | 171 | RE | 11.02.2020 | ENC/TR01/PM/RE/0309 | Resubmission of Pavement Design for CH 78+240 to 88+500 (ETR171) | 15.02.2020 22.02.2020 | S-20-0986/JR S-20-1037/JR
324 | Pavement Design | 171 | RE | 11.02.2020 | ENC/TR01/PM/RE/0308 | Resubmission of Pavement Design for CH 78+240 to 88+500 (ETR171) |  | pending
325 | ICS | 130 | RE | 11.02.2020 | ENC/TR01/PM/RE/0307 | Submission of Initial Cross Section Drawing from 0+000 to 1+664.8 (ETR130) | 13.02.2020 | S-9-TR-0659/RE | Accepted
326 | Road close | 57 | RE | 11.02.2020 | ENC/TR01/PM/RE/0306 | Minutes of the Meeting to Close the Road ETR057 from CH 0+200 to 0+380km Temporarily | 19.02.2020 | S-9-TR-0700/RE | No Objection
327 | Forest Dept | No | GEN | 11.02.2020 | ENC/TR01/PM/RE/0305 | Request for approval to use forest land for temporary Stock yard at 88th km post on Batticaloa Thirukondiyadimadu Trincomalee Road in Verugal DS Division |  | pending
328 | Topo | 133 | RE | 11.02.2020 | ENC/TR01/PM/RE/0304 | Submission of Topography Survey Drawing from 0+000 to 1+220 (ETR133) | 21.02.2020 | S-9-TR-0732/RE
329 | Secondary Survey | 154 | RE | 11.02.2020 | ENC/TR01/PM/RE/0303 | Submission of Secondary Survey Control and Leveling Details Report (ETR154) | 28.02.2020 | S-9-TR-0795/RE | Accepted
330 | Secondary Survey | 156064 | RE | 11.02.2020 | ENC/TR01/PM/RE/0302 | Submission of Secondary Survey Control and Leveling Details Reports | 28.02.2020 | S-9-TR-0800/RE | Accepted
331 | HA | 132 | RE | 11.02.2020 | ENC/TR01/PM/RE/0301 | Submission of Horizontal Alignment Drawing from 0+000 to 0+513.644 (ETR132) | 26.02.2020 | S-9-TR-0782/RE | Approved as noted
332 | Secondary Survey | 63 | RE | 10.02.2020 | ENC/TR01/PM/RE/0299 | Submission of Secondary Survey Control and Leveling Details Report (ETR063) | 28.02.2020 | S-9-TR-0797/RE | Accepted
333 | Crack Survey | 18 | RE | 09.02.2020 | ENC/TR01/PM/RE/0298 | Submission of Crack Survey Report from CH 0+000 to 1+880 km (ETR018) | 05.03.2020 | S-20-TR-0847/RE
334 | Crack Survey | 164 | RE | 09.02.2020 | ENC/TR01/PM/RE/0297 | Submission of Crack Survey Report from CH 0+000 to 1+170 km (ETR164) | 05.03.2020 | S-20-TR-0847/RE
335 | ICS | 171 | RE | 08.02.2020 | ENC/TR01/PM/RE/0296 | Submission of Initial Cross Section Drawing from 84+000 to 85+000 (ETR171) | 27.02.2020 | S-9-TR-0745/RE | Accepted
336 | IPA | No | RE | 08.02.2020 | ENC/TR01/PM/RE/0295 | Interim Payment Application - 05 for the Month January 2020 |  | pending
337 | ICS | 171 | RE | 08.02.2020 | ENC/TR01/PM/RE/0294 | Submission of Initial Cross Section Drawing from 85+000 to 86+000 (ETR171) | 22.02.2020 | S-9-TR-0744/RE | Accepted
338 | ICS | 171 | RE | 08.02.2020 | ENC/TR01/PM/RE/0293 | Submission of Initial Cross Section Drawing from 82+000 to 83+000 (ETR171) | 22.02.2020 | S-9-TR-0750/RE | Accepted
339 | Secondary Survey | 68 | RE | 08.02.2020 | ENC/TR01/PM/RE/0292 | Submission of Secondary Survey Control and Leveling Details Report (ETR068) | 21.02.2020 | S-9-TR-0735/RE
340 | Topo | 134 | RE | 08.02.2020 | ENC/TR01/PM/RE/0291 | Submission of Topography Survey Drawing from 0+000 to 1+115 (ETR134) | 21.02.2020 | S-9-TR-0731/RE
341 | HA | 57 | RE | 07.02.2020 | ENC/TR01/PM/RE/0290 | Resubmission of Horizontal Alignment Drawing from 00+000 to 00+620 (ETR057) | 09.06.2020 | S-20-TR-1435/RE
342 | Pavement Design | 166 | RE | 07.02.2020 | ENC/TR01/PM/RE/0289 | Submission of Pavement Design Report for CH 0+110 to 4+230 (ETR166) | 20.02.2020 | S-9-TR-0704/RE | Approved
343 | Culvert Drawing | 57 | RE | 07.02.2020 | ENC/TR01/PM/RE/0288 | Resubmission of Culvert Construction Drawing of 1/1 (CH 0+613.30) - ETR057 | 15.02.2020 | S-9-TR-0671/RE | Approved as noted
344 | HA | 131 | RE | 07.02.2020 | ENC/TR01/PM/RE/0287 | Submission of Horizontal Alignment Drawing Section-1 CH: 00+000 to 0+630.073 & Section-2 CH: 00+000 to 0+265.638 (ETR131) | 17.07.2020 | 1854
345 | Source Approval | No | RE | 07.02.2020 | ENC/TR01/PM/RE/0286 | Submission for Source Approval of Hume Pipe Dia 450mm, 600mm and 900mm from Dilani Concrete Work | 15.02.2020 | S-9-TR-0689/RE | Accepted
346 | Source Approval | No | RE | 07.02.2020 | ENC/TR01/PM/RE/0285 | Submission for Source Approval of Hume Pipe Dia 450mm, 600mm and 900mm from State Development & Construction Corporation | 15.02.2020 | S-9-TR-0675/RE | Approved
347 | Secondary Survey | 16 | RE | 07.02.2020 | ENC/TR01/PM/RE/0284 | Submission of Secondary Survey Control and Leveling Details Report (ETR016) | 21.02.2020 | S-9-TR-0737/RE | Accepted
348 | Furniture | Type - 2 | RE | 06.02.2020 | ENC/TR01/PM/RE/0283 | Provided Furniture and Equipment items for Type 2 House | 13.02.2020 | S-9-TR-0660/RE | Not Provided
349 | Furniture | Type - 1 | RE | 06.02.2020 | ENC/TR01/PM/RE/0282 | Provided Furniture and Equipment items for Type 1 House | 22.02.2020 | S-9-TR-0746/RE
350 | Calibration | No | RE | 06.02.2020 | ENC/TR01/PM/RE/0281 | Instrument Calibration Report for Total Station and Auto Level | 22.02.2020 | S-9-TR-0752/RE | Accepted
351 | HA | 165 | RE | 06.02.2020 | ENC/TR01/PM/RE/0280 | Submission of Horizontal Alignment Drawing from 00+000 to 1+357.839 (ETR165) | 27.04.2020 12.06.2020 | S-20-TR-1088/RE S-20-TR-1483/RE | Approved as noted
352 | VA | 57 | RE | 05.02.2020 | ENC/TR01/PM/RE/0275 | Submission of Vertical Alignment Drawing from 00+000 to 00+621.505 (ETR057) | 07.02.2020 | S-9-TR-0616/RE | Re Submit
353 | Source Approval | No | RE | 05.02.2020 | ENC/TR01/PM/RE/0274 | Submission for Source Approval of Tokyo Super Cement |  | pending
354 | Source Approval | No | RE | 05.02.2020 | ENC/TR01/PM/RE/0273 | Submission for Source Approval of Asphalt Wearing Course from Access Plant Ketadeniyawa | 11.02.2020 | S-9-TR-0641/RE | No Objection
355 | University of Peradeniya-OIC | No | RE | 15.02.2020 | ENC/TR01/PM/GEN/0325 | Requesting for Testing of Compressive Strength for these Core Samples |  | Pending
356 | PE | No | PE | 05.02.2020 | ENC/TR01/PM/GEN/0278 | See General File - 1 |  | pending
357 | Forest Dept | No | GEN | 05.02.2020 | ENC/TR01/PM/GEN/0277 | See General File - 1 |  | pending
358 | Forest Dept | No | GEN | 05.02.2020 | ENC/TR01/PM/GEN/0276 | See General File - 1 |  | pending
359 | Traffic Count | 171 | RE | 19.11.2019 | ENC/PM/RE/TR-1/DES/019 | Requesting for full traffic count for Batticaloa Thrirukondiyamadu Trincomalee Road from the CH 78+250 to 108+540km |  | Pending
360 | HA | 171 | RE | 14.11.2019 | ENC/PM/RE/TR-1/DES/018 | Submission of Horizontal Alignment Drawing from 78+300 to 82+500 (ETR-171) |  | S-9-TR-0232/RE
361 | Design | 171 | RE | 13.11.2019 | ENC/PM/RE/TR-1/DES/017 | Design Issues on the Road ID ETR171, Batticaloa Thirukondiyadimadu Trincomalee |  | S-9-TR-0188/RE
362 | Design | 6 | RE | 14.11.2019 | ENC/PM/RE/TR-1/DES/016 | Design Issues on the Road ETR006 |  | S-9-TR-0216/RE
363 | Topo | 171 | RE | 01.11.2019 | ENC/PM/RE/TR-1/DES/015 | Submission of Topography Survey Drawing from 89+020 to 94+000 (ETR171) |  | S-9-TR-0216/RE
364 | GPS | No | RE | 04.11.2019 | ENC/PM/RE/TR-1/DES/014 | Submission of GPS Report 02 |  | S-9-TR-0167/RE
365 | Traffic Count | 171 | RE | 29.10.2019 | ENC/PM/RE/TR-1/DES/013 | Request for Full Traffic Count for Batticaloa - Thirukondiyamadu - Trincomalee Road from CH78+240 to 105+540km |  | NNR
366 | Secondary Survey | 171 | RE | 29.10.2019 | ENC/PM/RE/TR-1/DES/012 | Submission of Secondary Survey Control and Leveling Detail Report from CH96+000 to 100+000km (ETR.171) |  | S-9-TR-0211/RE
367 | Secondary Survey | 171 | RE | 21.10.2019 | ENC/PM/RE/TR-1/DES/011 | Submission of Secondary Survey Control and Leveling Detail Report (ETR171) |  | S-9-TR-0136/RE
368 | Road Width | 171 | RE | 19.10.2019 | ENC/PM/RE/TR-1/DES/010 | Submission of Proposed Road Width |  | S-9-TR-0132/RE-S-9-TR-0162/RE
369 | Topo | 171 | RE | 18.10.2019 | ENC/PM/RE/TR-1/DES/009 | Submission of Topography. Survey Drawingfrom 82+500 to 88+070 (ETR171) |  | S-9-TR-0186/RE
370 | Secondary Survey | 171 | RE | 14.10.2019 | ENC/PM/RE/TR-1/DES/008 | Submission of Secondary, Survey Control and Leveling Detail Report from 87+000 to 92+000 (ETR171) |  | S-9-TR-0135/RE
371 | Topo | 171 | RE | 14.10.2019 | ENC/PM/RE/TR-1/DES/007 | Submission of Topography, Survey Drawing from 77+500 to 82+500 (ETR171) |  | S-9-TR-0124/RE
372 | Secondary Survey | No | RE | 06.09.2019 | ENC/PM/RE/TR-1/DES/006 | Submission of Secondary Survey Control and Levelling Detail Report from GPS TROL-02 to GPS TRO1:03 (ETR171) |  | S-9-TR-0094/RE
373 | Secondary Survey | 171 | RE | 06.09.2019 | ENC/PM/RE/TR-1/DES/005 | Submission of Secondary Survey Control and Levelling Detail Repprt (ETR171) |  | S-9-TR-0093/RE
374 | Road Width | No | RE | 05.09.2019 | ENC/PM/RE/TR-1/DES/004 | Request to Confirm the Road Width |  | S-9-TR-0103/RE
375 | Secondary Survey | 171 | RE | 18.09.2019 | ENC/PM/RE/TR-1/DES/003 | Submission of Secondary Survey Control and Levelling Detail Report (ETR171) |  | S-9-TR-0055/RE
376 | HA | 59 | RE | 19.02.2020 | ENC/TR01/PM/RE/0346 | Submission of Horizontal Alignment Drawing from CH 0+000 to 0+530.27km at Manachenai Peruvely Central Road (ETR059) | 12.03.2020 | S-9-TR-0895/RE | Approved as noted
377 | Topo | 69 | RE | 19.02.2020 | ENC/TR01/PM/RE/0347 | Submission of Topography Survey Drawing from 0+000 to 0+306 (ETR069) | 11.03.2020 | S-20-TR-0870/RE
378 | Progress Report | No | RE | 19.02.2020 | ENC/TR01/PM/RE/0348 | Resubmission Monthly Progress Report for the Month of December – 2019 | 27.02.2020 | S-9-TR-0786/RE | Accepted with comments
379 | TW | No | TL | 20.02.2020 | ENC/TR01/PM/TL/0349 | Submission of Transect Walk Records |  | pending
380 | HA | 166 | RE | 22.01.2020 | ENC/TR01/PM/RE/0350 | Resubmission of Horizontal Alignment Drawing from CH 0+000 to 4+233.333km (ETR166) | 25.02.2020 | S-9-TR-0779/RE | Approved as noted
381 | SSEMAP | No | TL | 21.02.2020 | ENC/TR01/PM/TL/0351 | Submission of Site Specific Environmental Management Action Plan (SSEMAP) | 29.02.2020 | S-20-1088/JR | Approved
382 | Topo | 154 | RE | 21.02.2020 | ENC/TR01/PM/RE/0352 | Submission of Topography Survey Drawing from 0+000 to 1+430km (ETR154) | 28.02.2020 | S-9-TR-0802/RE | Accepted
383 | Topo | 51151 | RE | 21.02.2020 | ENC/TR01/PM/RE/0353 | Submission of Topography Survey Drawings (ETR051 & ETR151) | 28.02.2020 | S-9-TR-0803/RE | Accepted
384 | Topo | 156 | RE | 21.02.2020 | ENC/TR01/PM/RE/0354 | Submission of Topography Survey Drawing from 0+000 to 0+182km (ETR156) | 28.02.2020 | S-9-TR-0804/RE | Accepted
385 | ICS | 127 | RE | 21.02.2020 | ENC/TR01/PM/RE/0355 | Submission of Initial Cross Section Drawing from 0+000 to 1+000 (ETR127) | 18.03.2020 | S-20-TR-0943/RE | Accepted
386 | Name Board | No | RE | 21.02.2020 | ENC/TR01/PM/RE/0356 | Resubmission of Public Notice | 11.03.2020 | S-20-TR-0893/RE | Accepted with comments
387 | Source Approval | No | RE | 21.02.2020 | ENC/TR01/PM/RE/0357 | Resubmission of EPL & TL for Source Approval of ABC & 20mm Aggregate | 05.03.2020 | S-20-TR-0846/RE
388 | Pavement Design | 133 | RE | 21.02.2020 | ENC/TR01/PM/RE/0358 | Submission of Pavement Design Report for CH 0+000 to 1+050 (ETR133) | 24.02.2020 | S-9-TR-0766/RE
389 | HA | 58 | RE | 22.02.2020 | ENC/TR01/PM/RE/0359 | Submission of Horizontal Alignment Drawing from 0+000 to 0+542.765km (ETR058) | 26.02.2020 | S-9-TR-0781/RE | Approved as noted
390 | HA | 132 | RE | 22.02.2020 | ENC/TR01/PM/RE/0360 | Submission of Horizontal Alignment Drawing from 0+000 to 0+513.644 (ETR132) | 26.02.2020 | S-9-TR-0782/RE | Approved as noted
391 | HA | 66 | RE | 22.02.2020 | ENC/TR01/PM/RE/0361 | Submission of Horizontal Alignment Drawings from 00+000 to 0+581.510km (ETR066) | 27.04.2020 11.06.2020 | S-20-TR-1085/RE S-20-TR-1472/RE | Approved as noted
392 | Meeting | No | RE | 22.02.2020 | ENC/TR01/PM/RE/0362 | Confirmation of Discussion at the Fortnight Meeting held on 19 Feb 2020 |  | pending
393 | Topo | 63 | RE | 22.02.2020 | ENC/TR01/PM/RE/0363 | Submission of Topography Survey Drawings from 0+000 to 0+514km (ETR063) | 28.02.2020 | S-9-TR-0805/RE | Accepted
394 | ICS | 171 | RE | 22.02.2020 | ENC/TR01/PM/RE/0364 | Submission of Initial Cross Section Drawing from 86+000 to 87+000 (ETR171) | 10.03.2020 | S-9-TR-0856/RE | Accepted
395 | Topo | 53 | RE | 24.02.2020 | ENC/TR01/PM/RE/0365 | Submission of Topography Survey Drawings from 0+000 to 1+028km (ETR053) | 28.02.2020 | S-9-TR-0810/RE | Accepted
396 | Pavement Design | 70 | RE | 24.02.2020 | ENC/TR01/PM/RE/0366 | Submission of Pavement Design Report for CH 0+000 to 1+480 (ETR070) | 22.05.2020 | S-9-TR-1288/RE | Approved as noted
397 | HA | 134 | RE | 24.02.2020 | ENC/TR01/PM/RE/0367 | Submission of Horizontal Alignment Drawings from 00+000 to 01+122km (ETR134) | 06.05.2020 | S-20-TR-1134/RE S-20-TR-1459/RE | Approved as noted
398 | ICS | 171 | RE | 24.02.2020 | ENC/TR01/PM/RE/0368 | Submission of Initial Cross Section Drawing from 89+000 to 90+000 (ETR171) | 18.03.2020 | S-20-TR-0952/RE | Accepted
399 | HA | 171 | RE | 25.02.2020 | ENC/TR01/PM/RE/0369 | Resubmission of Horizontal Alignment Drawing CH 96+000 to 102+000 (ETR171) | 28.02.2020 | S-9-TR-0794/RE | Approved as noted
400 | HA | 171 | RE | 25.02.2020 | ENC/TR01/PM/RE/0370 | Submission of Horizontal Alignment Drawing CH 102+000 to 108+416.37 km (ETR171) | 22.05.2020 | S-9-TR-1286/RE | Re Submit
401 | Design | 171 | RE | 25.02.2020 | ENC/TR01/PM/TL/0371 | Trial Section for Potential Alternative Design to ETR 171 (A15) Road |  | pending
402 | Investigation | All | RE | 25.02.2020 | ENC/TR01/PM/RE/0372 | Summary of Existing Road Investigation Test Reports for 34 Roads | 29.02.2020 | S-9-TR-0816/RE | No Objection
403 | Topo | 68 | RE | 25.02.2020 | ENC/TR01/PM/RE/0373 | Submission of Topography Survey Drawings from 0+000 to 0+265km (ETR068) | 28.02.2020 | S-9-TR-0809/RE | Accepted
404 | Yard | Gen | RE | 27.02.2020 | ENC/TR01/PM/GEN/0374 | Request for Approval of Disposal Yard at Dharussalam Arabic College, Mutur |  | pending
405 | Traffic Count | No | RE | 25.02.2020 | ENC/TR01/PM/RE/0375 | Summary of Traffic Survey Reports for 32 Roads | 18.03.2020 | S-20-TR-0949/RE | No Objection
406 | DCS | 171 | RE | 25.02.2020 | ENC/TR01/PM/RE/0376 | Submission of Design Cross Section Drawings from CH 83+200 to 84+600 (ETR171) | 27.02.2020 | S-9-TR-0793/RE | Approved as noted
407 | SESMR | No | RE | 26.02.2020 | ENC/TR01/PM/RE/0377 | Monthly Social & Environmental Safeguard Monitoring Reports for the Month of Dec–2019 | 29.02.2020 | S-9-TR-0822/RE
408 | SESMR | No | RE | 26.02.2020 | ENC/TR01/PM/RE/0378 | Monthly Social & Environmental Safeguard Monitoring Reports for the Month of Jan–2020 | 29.02.2020 | S-9-TR-0822/RE
409 | Topo | 61 | RE | 26.02.2020 | ENC/TR01/PM/RE/0379 | Submission of Topography Survey Drawings from 0+000 to 0+600km (ETR061) |  | pending
410 | Topo | 55 | RE | 26.02.2020 | ENC/TR01/PM/RE/0380 | Submission of Topography Survey Drawings from 0+000 to 0+800km (ETR055) | 04.04.2020 | 998 | Accepted
411 | Culvert Drawing | 127 | RE | 26.02.2020 | ENC/TR01/PM/RE/0381 | Submission of Culvert Widening Drawing at CH 0+495 (ETR127) | 06.03.2020 | S-20-TR-0879/RE | Approved as noted
412 | Pavement Design | 54 | RE | 27.02.2020 | ENC/TR01/PM/RE/0382 | Submission of Pavement Design Report for CH 0+000 to 0+320 (ETR054) | 11.03.2020 | S-20-TR-0885/RE | Re Submit
413 | Pavement Design | 56 | RE | 27.02.2020 | ENC/TR01/PM/RE/0383 | Submission of Pavement Design Report for CH 0+000 to 0+440 (ETR056) | 11.03.2020 | S-20-TR-0890/RE | Approved
414 | Pavement Design | 51 | RE | 27.02.2020 | ENC/TR01/PM/RE/0384 | Submission of Pavement Design Report for CH 0+000 to 0+490 (ETR051) | 11.03.2020 | S-20-TR-0885/RE | Re Submit
415 | Yard | No | GEN | 27.02.2020 | ENC/TR01/PM/GEN/0385 | Request for Approval of Disposal Yard |  | pending
416 | Source Approval | No | RE | 27.02.2020 | ENC/TR01/PM/RE/0386 | Submission for Source Approval of Asphalt Plant at Kalawawa, Sun Contraction’s Plant | 05.03.2020 | S-9-TR-0843/RE
417 | Source Approval | No | RE | 27.02.2020 | ENC/TR01/PM/RE/0387 | Submission for Source Approval of Bonding Agent Chryso Struco Latex from Chryso Lanka | 05.03.2020 | S-20-TR-0845/RE
418 | Source Approval | No | RE | 27.02.2020 | ENC/TR01/PM/RE/0388 | Submission for Source Approval of Bonding Agent Master Emaco P158, Emaco 157D Primer from Finex Engineering | 05.03.2020 | S-20-TR-0845/RE
419 | QAMP | No | TL | 27.02.2020 | ENC/TR01/PM/TL/0389 | Submission of Quality Management Assurance System (Rev-02) | 11.01.2020 | S-9-TR-0760/DTL
420 | VA | 127 | RE | 27.02.2020 | ENC/TR01/PM/RE/0390 | Submission of Vertical Alignment Drawing from 0+000 to 1+000 (ETR127) | 12.03.2020 | S-20-TR-0894/RE
421 | DCS | 57 | RE | 28.02.2020 | ENC/TR01/PM/RE/0391 | Submission of Design Cross Section Drawings from CH 00+080 to 00+620 (ETR057) | 07.03.2020 | S-20-TR-0848/RE
422 | ICS | 166 | RE | 28.02.2020 | ENC/TR01/PM/RE/0392 | Submission of Initial Cross Section Drawing from 0+000 to 1+000 (ETR166) | 18.03.2020 | S-20-TR-0975/RE | Accepted
423 | Pavement Design | 53 | RE | 28.02.2020 | ENC/TR01/PM/RE/0393 | Submission of Pavement Design Report for CH 0+000 to 0+420 (ETR053) | 11.03.2020 | S-20-TR-0885/RE | Re Submit
424 | Culvert Drawing | 127 | RE | 29.02.2020 | ENC/TR01/PM/RE/0394 | Submission of Pipe Culvert Drawing at CH 0+718.6km (ETR127) |  | S-9-TR-0833/RE
425 | Culvert Drawing | 166 | RE | 29.02.2020 | ENC/TR01/PM/RE/0395 | Submission of Pipe Culvert Drawing at CH 02+043.9 (ETR166) | 03.03.2020 | S-9-TR-0831/RE
426 | Culvert Drawing | 166 | RE | 29.02.2020 | ENC/TR01/PM/RE/0396 | Submission of Box Culvert Drawing at CH 01+880.00 (ETR166) |  | S-9-TR-0832/RE
427 | Yard | No | GEN | 29.02.2020 | ENC/TR01/PM/GEN/0397 | Request for Approval of Disposal Yard |  | pending
428 | HA | 60 | RE | 29.02.2020 | ENC/TR01/PM/RE/0398 | Submission of Horizontal Alignment Drawings from 00+000 to 00+710km (ETR060) | 23.05.2020 | S-20-TR-1306/RE | Approved as noted
429 | Culvert Drawing | 130 | RE | 29.02.2020 | ENC/TR01/PM/RE/0399 | Confirmation of Site Decisions for the Construction of Culverts at the CH 0+354km and 0+772km and Type of Road Surface from the Ch 1+205 to 1+644km on ETR130, Mankala Bokku Road |  | S-9-TR-0828/RE
430 | Safety Audit | 57 | RE | 05.03.2020 | ENC/TR01/PM/RE/0400 | Submission of Road Safety Audit Report for ETR 057 | 11.03.2020 | S-9-TR-0864/RE
431 | Safety Audit | 127 | RE | 05.03.2020 | ENC/TR01/PM/RE/0401 | Submission of Road Safety Audit Report for ETR 127 | 11.03.2020 | S-9-TR-0865/RE
432 | EMC | 130 | RE | 02.03.2020 | ENC/TR01/PM/RE/0402 | Submission of Environmental Monitoring Checklist for ETR 130 | 11.03.2020 | S-20-1137/JR
433 | EMC | 57 | RE | 02.03.2020 | ENC/TR01/PM/RE/0403 | Submission of Environmental Monitoring Checklist for ETR 057 | 11.03.2020 | S-20-1135/JR
434 | ICS | 171 | RE | 02.03.2020 | ENC/TR01/PM/RE/0404 | Submission of Initial Cross Section Drawing from 87+000 to 88+000 (ETR171) | 10.04.2020 | S-20-TR-1020/RE | Accepted
435 | ICS | 166 | RE | 02.03.2020 | ENC/TR01/PM/RE/0405 | Submission of Initial Cross Section Drawing from 01+000 to 02+000 (ETR166) | 18.03.2020 | S-20-TR-0974/RE | Accepted
436 | Request | No | RE | 03.03.2020 | ENC/TR01/PM/RE/0406 | Requesting for duplicate copy of Environmental protection license (EPL) and Trade license (TL) |  | pending
437 | Deport Tray | No | RE | 03.03.2020 | ENC/TR01/PM/RE/0407 | Submission of Deport Tray Results carried out to Binder Distributor - BS 05 | 13.03.2020 | S-20-TR-0904/RE
438 | HA | 67 | RE | 03.03.2020 | ENC/TR01/PM/RE/0408 | Submission of Horizontal Alignment Drawings from 00+000 to 00+564km (ETR067) | 06.05.2020 | S-20-TR-1130/RE
439 | HA | 16 | RE | 03.03.2020 | ENC/TR01/PM/RE/0409 | Submission of Horizontal Alignment Drawings from 00+000 to 04+522km (ETR016) | 06.05.2020 | S-20-TR-1129/RE S-20-TR-1458/RE
440 | HA | 133 | RE | 03.03.2020 | ENC/TR01/PM/RE/0410 | Submission of Horizontal Alignment Drawings from 00+000 to 01+212km (ETR133) | 06.05.2020 | S-20-TR-1135/RE S-20-TR-1457/RE | Approved as noted
441 | HA | 56 | RE | 03.03.2020 | ENC/TR01/PM/RE/0411 | Submission of Horizontal Alignment Drawings from 00+000 to 00+664.184km (ETR056) | 06.05.2020 | S-20-TR-1131/RE S-20-TR-1456/RE | Approved as noted
442 | Contractor's Staff | No | TL | 03.03.2020 | ENC/TR01/PM/TL/0412 | Submission of Proposal for Contractor’s Staff of HDE Mr.M.M.N.Marasinghe | 10.03.2020 | S-20-1130/DTL
443 | GSMB | No | PE | 03.03.2020 | ENC/TR01/PM/PE/0413 | Letter to GSMB Describing Scope of Work |  | pending
444 | Subgrade Layer | 171 | RE | 03.03.2020 | ENC/TR01/PM/RE/0414 | Proposal for Alternative Improved Subgrade Layer by Pulverization of Exiting Carriageway Top Layers of A15 Road |  | pending
445 | DCS | 171 | RE | 03.03.2020 | ENC/TR01/PM/RE/0415 | Submission of Typical Design Cross Section Drawings from CH 86+000 to 86+200 (ETR171) |  | pending
446 | Pavement Design | 61 | RE | 03.03.2020 | ENC/TR01/PM/RE/0416 | Submission of Pavement Design Report for CH 0+000 to 0+500 (ETR061) | 11.03.2020 | S-20-TR-0885/RE | Re Submit
447 | ICS | 166 | RE | 04.03.2020 | ENC/TR01/PM/RE/0417 | Submission of Initial Cross Section Drawing from 2+000 to 3+000 (ETR166) | 18.03.2020 | S-20-TR-0973/RE | Accepted
448 | ICS | 166 | RE | 04.03.2020 | ENC/TR01/PM/RE/0418 | Submission of Initial Cross Section Drawing from 3+000 to 4+252.45 (ETR166) | 06.05.2020 | S-20-TR-1127/RE | Accepted
449 | HIV/AIDS | No | RE | 04.03.2020 | ENC/TR01/PM/RE/0419 | Submission of Proposal for HIV/AIDS Prevention and Health Awareness Program | 15.05.2020 | S-20-TR-1207/RE
450 | EMC | 127 | RE | 04.03.2020 | ENC/TR01/PM/RE/0420 | Submission of Environmental Monitoring Checklist for ETR 127 | 11.02.2020 | S-20-1136/JR
451 | S Curve | No | RE | 05.03.2020 | ENC/TR01/PM/RE/0421 | Resubmission of Financial S curve |  | pending
452 | Progress Report | No | RE | 05.03.2020 | ENC/TR01/PM/RE/0422 | Submission of Monthly Progress Report No - 03 for the Month of December - 2019 |  | pending
453 | Culvert Drawing | 166 | RE | 05.03.2020 | ENC/TR01/PM/RE/0423 | Submission of Box Culvert Drawing at CH 0+558 (ETR166) | 11.03.2020 | S-9-TR-0877/RE | Re Submit
454 | Culvert Drawing | 166 | RE | 05.03.2020 | ENC/TR01/PM/RE/0424 | Submission of Box Culvert Drawing at CH 02+245 (ETR166) | 11.03.2020 | S-9-TR-0878/RE | Re Submit
455 | Culvert Drawing | 171 | RE | 05.03.2020 | ENC/TR01/PM/RE/0425 | Submission of Widening Culvert Drawing at CH 92+739 (ETR171) | 19.05.2020 | S-20-TR-1240/RE
456 | HA | 59 | RE | 07.03.2020 | ENC/TR01/PM/RE/0426 | Resubmission of Horizontal Alignment Drawing from CH 0+000 to 0+530.288 (ETR059) | 12.03.2020 | S-9-TR-0895/RE | Approved as noted
457 | Culvert Drawing | 166 | RE | 06.03.2020 | ENC/TR01/PM/RE/0427 | Submission of Reconstruction of Box Culvert Drawing at CH 02+795 (ETR166) | 06.03.2020 | S-20-TR-0876/RE | Approved as noted
458 | Meeting | 57 | RE | 07.03.2020 | ENC/TR01/PM/RE/0428 | Verbal Instruction Confirmation of Design Width of Asphalt Surfacing & Soft Shoulder on ETR057 discussed at the Monthly Progress Review Meeting held on 06 March 2020 | 14.03.2020 | S-20-TR-0923/RE
459 | Source Approval | No | RE | 07.03.2020 | ENC/TR01/PM/RE/0429 | Submission of Trade License for 20mm Aggregate from Edward and Christie- Wadakada crusher plant - Source Approval | 04.04.2020 | 1003 | Accepted
460 | Source Approval | No | RE | 07.03.2020 | ENC/TR01/PM/RE/0430 | Submission of EPL for CRS1, CSS1, MC-30 and 60-70Pen Bitumen of Bitulink Brand - Source Approval | 11.04.2020 | S-20-TR-1024/RE
461 | Source Approval | No | RE | 07.03.2020 | ENC/TR01/PM/RE/0431 | Submission of EPL for Melwa Reinforcement Material - Source Approval | 24.03.2020 | S-20-TR-0984/RE
462 | Source Approval | No | RE | 07.03.2020 | ENC/TR01/PM/RE/0432 | Submission of EPL for Lanwa Reinforcement Material - Source Approval | 11.04.2020 | S-20-TR-1025/RE
463 | Progress Report | No | RE | 07.03.2020 | ENC/TR01/PM/RE/0433 | Resubmission of Monthly Progress Report No-04 for the Month of January - 2020 | 14.03.2020 | S-9-TR-0920/RE
464 | Progress Report | No | RE | 07.03.2020 | ENC/TR01/PM/RE/0434 | Submission of Monthly Progress Report No-05 for the Month of February - 2020 | 14.03.2020 | S-9-TR-0921/RE
465 | Source Approval | No | RE | 07.03.2020 | ENC/TR01/PM/RE/0435 | Submission of EPL & TL for ABC & 20mm Aggregate - Source Approval | 04.04.2020 | 1002
466 | Road Length | 57 | TL | 07.03.2020 | ENC/TR01/PM/TL/0436 | Confirm the Addition of Road Length 121.5m from CH 0+500 to 0+621.5 km of the Road ID ETR057, Kiliveddy West Road |  | pending
467 | Meeting | 171 | RE | 07.03.2020 | ENC/TR01/PM/RE/0437 | Verbal Instruction Confirmation of Design width of Asphalt Surfacing & Soft Shoulder on ETR171 discussed at the Monthly Progress Review Meeting held on 06 March 2020 |  | pending
468 | Culvert Report | 58 | RE | 08.03.2020 | ENC/TR01/PM/RE/0438 | Culvert Conditional Report for the Road ETR058 |  | pending
469 | Culvert Report | 59 | RE | 08.03.2020 | ENC/TR01/PM/RE/0439 | Culvert Conditional Report for the Road ETR059 |  | pending
470 | Culvert Report | 133 | RE | 08.03.2020 | ENC/TR01/PM/RE/0440 | Culvert Conditional Report for the Road ETR133 | 23.06.2020 | S-20-TR-0980/RE
471 | Pavement Design | 134 | RE | 09.03.2020 | ENC/TR01/PM/RE/0441 | Submission of Pavement Design Report for CH 0+000 to 1+050 (ETR134) | 25.03.2020 | 988
472 | EMC | 166 | RE | 11.03.2020 | ENC/TR01/PM/RE/0442 | Submission of Environmental Monitoring Checklist for ETR 166 |  | pending
473 | Safety Audit | 130 | RE | 11.03.2020 | ENC/TR01/PM/RE/0443 | Submission of Road Safety Audit Report for ETR 130 | 13.03.2020 | S-9-TR-902/RE
474 | Safety Audit | 166 | RE | 11.03.2020 | ENC/TR01/PM/RE/0444 | Submission of Road Safety Audit Report for ETR 166 | 13.03.2020 | S-9-TR-902/RE
475 | Safety Audit | 171 | RE | 11.03.2020 | ENC/TR01/PM/RE/0445 | Submission of Road Safety Audit Report from CH 82+000 to 87+000 (ETR 171) | 13.03.2020 | S-9-TR-902/RE
476 | Crack Survey | 166 | RE | 11.03.2020 | ENC/TR01/PM/RE/0446 | Submission of Crack Survey Report from CH 0+000 to 1+370km (ETR166) | 26.03.2020 | S-20-TR-0992/RE
477 | Crack Survey | 166 | RE | 11.03.2020 | ENC/TR01/PM/RE/0447 | Submission of Crack Survey Report from CH 1+370 to 1+860 km (ETR166) | 20.05.2020 | S-20-TR-1228/RE
478 | ICS | 171 | RE | 11.03.2020 | ENC/TR01/PM/RE/0448 | Submission of Initial Cross Section Drawing from 88+000 to 89+000 (ETR171) | 10.04.2020 | S-9-TR-1021/RE | Accepted
479 | Road close | 57 | RE | 12.03.2020 | ENC/TR01/PM/RE/0449 | Request to close the road for a short period at the culvert 1/2 on ETR057 |  | pending
480 | Furniture | No | RE | 12.03.2020 | ENC/TR01/PM/RE/0450 | Furniture and Equipment for Main Laboratory Mutur | 14.05.2020 | S-20-TR-1189/RE
481 | ICS | 58 | RE | 11.03.2020 | ENC/TR01/PM/RE/0451 | Submission of Initial Cross Section Drawing from 0+000 to 0+542. 5 (ETR058) | 28.04.2020 | S-20-TR-1098/RE | Accepted
482 | Trail Section | 171 | RE | 12.03.2020 | ENC/TR01/PM/RE/0452 | Submission of Employer Design Proposal Drawings for Trail Section from CH 86+000 to 86+200 (ETR171) |  | pending
483 | Furniture | No | RE | 12.03.2020 | ENC/TR01/PM/RE/0453 | Furniture and Equipment for Field Laboratory - Serunuwara | 15.05.2020 | S-20-TR-1210/RE
484 | ICS | 59 | RE | 13.03.2020 | ENC/TR01/PM/RE/0454 | Submission of Initial Cross Section Drawing from 0+000 to 0+530 (ETR059) | 28.04.2020 | S-20-TR-1100/RE | Accepted
485 | VA | 166 | RE | 13.03.2020 | ENC/TR01/PM/RE/0455 | Submission of Vertical Alignment Drawing from 0+000 to 4+252.453km (ETR166) |  | 939
486 | HA | 66 | RE | 13.03.2020 | ENC/TR01/PM/RE/0456 | Submission of Horizontal Alignment Drawing from 0+000 to 0+566.799km (ETR066) | 27.04.2020 11.06.2020 | S-20-TR-1085/RE S-20-TR-1472/RE | Approved as noted
487 | ICS | 132 | RE | 13.03.2020 | ENC/TR01/PM/RE/0457 | Submission of Initial Cross Section Drawing from 0+000 to 0+514 (ETR132) | 04.05.2020 | S-20-TR-1116/RE | Accepted
488 | Culvert Drawing | 166 | RE | 13.03.2020 | ENC/TR01/PM/RE/0458 | Submission of Box Culvert Drawing at CH 01+607.3 (ETR166) | 18.03.2020 | S-20-TR-0953/RE | Approved as noted
489 | Culvert Drawing | 58 | RE | 13.03.2020 | ENC/TR01/PM/RE/0459 | Submission of Box Culvert Drawing at CH 0+037 (ETR058) | 18.03.2020 | S-20-TR-0955/RE | Approved as noted
490 | U-Drain | No | RE | 13.03.2020 | ENC/TR01/PM/RE/0460 | Submission of U-Drain Detail Drawings | 18.03.2020 | S-20-TR-0977/RE | Approved as noted
491 | Culvert Drawing | 171 | RE | 13.03.2020 | ENC/TR01/PM/RE/0461 | Submission of Widening Culvert Drawing at CH 92+933 (ETR171) | 18.03.2020 | S-20-TR-0957/RE | Re Submit
492 | EMC | No | RE | 13.03.2020 | ENC/TR01/PM/RE/0462 | Monthly Social & Environmental Safeguard Monitoring Reports for the Month of February–2020 |  | pending
493 | Source Approval | No | RE | 13.03.2020 | ENC/TR01/PM/RE/0463 | Submission for Source Approval of E&C Asphalt Plant at Badalgama | 24.03.2020 | 985
494 | Source Approval | No | RE | 13.03.2020 | ENC/TR01/PM/RE/0464 | Submission for Source Approval of E&C Asphalt Plant at Kalanchiya - Mihinthala | 24.03.2020 | 985
495 | Crack Survey | 166 | RE | 13.03.2020 | ENC/TR01/PM/RE/0465 | Submission of Crack Survey Report from CH 1+860 to 2+640km (ETR166) | 11.05.2020 | S-20-TR-1156/RE
496 | Crack Survey | 66 | RE | 13.03.2020 | ENC/TR01/PM/RE/0466 | Submission of Crack Survey Report from CH 0+000 to 0+560km (ETR066) | 25.03.2020 | S-20-TR-0987/RE
497 | Yard | No | GEN | 14.03.2020 | ENC/TR01/PM/GEN/0467 | Request for Approval of Disposal Yard |  | pending
498 | Yard | No | GEN | 14.03.2020 | ENC/TR01/PM/GEN/0468 | Request for Approval of Disposal Yard |  | pending
499 | Crack Survey | 166 | RE | 15.03.2020 | ENC/TR01/PM/RE/0469 | Submission of Crack Survey Report from CH 2+640 to 2+960km (ETR166) | 20.05.2020 | S-20-TR-1257/RE
500 | ICS | 171 | RE | 15.03.2020 | ENC/TR01/PM/RE/0470 | Submission of Initial Cross Section Drawing from 90+000 to 91+000 (ETR171) | 08.04.2020 | 1015 | Accepted
501 | ICS | 171 | RE | 15.03.2020 | ENC/TR01/PM/RE/0471 | Submission of Initial Cross Section Drawing from 91+000 to 92+000 (ETR171) | 28.04.2020 | S-20-TR-1099/RE | Accepted
502 | Culvert Report | 165 | RE | 15.03.2020 | ENC/TR01/PM/RE/0472 | Culvert Conditional Report for the Road ETR165 | 22.04.2020 | S-20-TR-1059/RE
503 | Culvert Report | 18 | RE | 15.03.2020 | ENC/TR01/PM/RE/0473 | Culvert Conditional Report for the Road ETR018 | 22.04.2020 | S-20-TR-1060/RE
504 | Culvert Report | 51 | RE | 15.03.2020 | ENC/TR01/PM/RE/0474 | Culvert Conditional Report for the Road ETR051 | 22.04.2020 | S-20-TR-1061/RE
505 | Culvert Report | 55 | RE | 15.03.2020 | ENC/TR01/PM/RE/0475 | Culvert Conditional Report for the Road ETR055 Section 1 & 2 | 22.04.2020 | S-20-TR-1062/RE
506 | Culvert Report | 68 | RE | 15.03.2020 | ENC/TR01/PM/RE/0476 | Culvert Conditional Report for the Road ETR068 | 22.04.2020 | S-20-TR-1063/RE
507 | Culvert Report | 132 | RE | 15.03.2020 | ENC/TR01/PM/RE/0477 | Culvert Conditional Report for the Road ETR132
508 | Culvert Drawing | 166 | RE | 16.03.2020 | ENC/TR01/PM/RE/0478 | Resubmission of Reconstruction of Box Culvert Drawing at CH 02+795 (ETR166) | 18.03.2020 | S-20-TR-0954/RE | Approved as noted
509 | Culvert Drawing | 166 | RE | 16.03.2020 | ENC/TR01/PM/RE/0479 | Resubmission of Box Culvert Drawing at CH 0+558 (ETR166) | 18.03.2020 | S-20-TR-0956/RE | Approved as noted
510 | HA | 70 | RE | 16.03.2020 | ENC/TR01/PM/RE/0480 | Resubmission of Horizontal Alignment Drawing from 0+000 to 1+572.303km (ETR070) | 23.05.2020 | S-20-TR-1305/RE | Approved as noted
511 | Road close | 127 | RE | 17.03.2020 | ENC/TR01/PM/RE/0481 | Request for Road closing for a short period on ETR127 for the culvert ½ at CH 0+718km |  | pending
512 | Road close | 166 | RE | 17.03.2020 | ENC/TR01/PM/RE/0482 | Request for Road closing for a short period on ETR166 for the culvert 2/4 and 3/1 |  | pending
513 | DCS | 171 | RE | 17.03.2020 | ENC/TR01/PM/RE/0483 | Resubmission of Design Cross Section Drawings from CH 83+200 to 84+600 (ETR171) |  | pending
514 | Initial Maintenance | No | RE | 17.03.2020 | ENC/TR01/PM/RE/0484 | Initial Maintenance Completed Roads | 02.04.2020 | 994
515 | VA | 57 | RE | 17.03.2020 | ENC/TR01/PM/RE/0485 | Resubmission of Vertical Alignment Drawing from 0+000 to 0+613.30 (ETR057) |  | pending
516 | Gentral | No | GEN | 17.03.2020 | ENC/TR01/PM/GEN/0486 | Wildlife |  | NNR
517 | HIV/AIDS | No | RE | 17.03.2020 | ENC/TR01/PM/RE/0487 | Request to Postpone the HIV/AIDS Awareness Programme |  | pending
518 | IPA | No | RE | 18.03.2020 | ENC/TR01/PM/RE/0488 | Interim Payment Application - 06 for the Month February 2020 |  | pending
519 | EMC | 171 | RE | 18.03.2020 | ENC/TR01/PM/RE/0489 | Submission of Environmental Monitoring Checklist at CH 78+240 to 88+240km (ETR 171) |  | pending
520 | Covid19 | No | TL | 13.03.2020 | ENC/TR01/PM/TL/0490 | Notice of Preventing Contract Obligations due to Outbreak of New Corona-virus (COVID 19) | 06.04.2020 | S-20-1193/JR
521 | Covid19 | No | GEN | 18.03.2020 | ENC/TR01/PM/RE/0491 | Requesting for COVID-19 Awareness Programme |  | pending
522 | Covid19 | No | TL | 13.03.2020 | ENC/TR01/PM/RE/0492 | Notice of temporary termination of crack survey due to Outbreak of New Corona-virus (COVID 19) |  | pending
523 | Covid19 | No | TL | 19.03.2020 | ENC/TR01/PM/RE/0493 | Notice of Holding the Site Works due to No Engineer’s Site Supervision |  | pending
524 | Covid19 | No | RE | 19.03.2020 | ENC/TR01/PM/RE/0494 | Safety Arrangement at site during the Temporary Site Shut down due to New Corona-virus (COVID 19) |  | pending
525 | VA | 59 | RE | 23.03.2020 | ENC/TR01/PM/RE/0495 | Submission of Vertical Alignment Drawing from CH 0+000 to 0+542.483km on Manatchenai Peruvely Central Road (ETR059) | 20.04.2020 | S-20-TR-1051/RE | Approved
526 | VA | 58 | RE | 23.03.2020 | ENC/TR01/PM/RE/0496 | Submission of Vertical Alignment Drawing from CH 0+000 to 0+530.28km on Cooperative Road, Iruthayapuram (ETR058) | 20.04.2020 | S-20-TR-1050/RE | Approved
527 | HA | 6 | RE | 23.03.2020 | ENC/TR01/PM/RE/0497 | Submission of Horizontal Alignment Drawing from CH 0+000 to 7+148.821km on Thopur Kaddaiparichan Idimanthurai Road (ETR006) | 08.04.2020 09.06.2020 | S-20-TR-1018/RE S-20-TR-1442/RE
528 | HA | 170 | RE | 23.03.2020 | ENC/TR01/PM/RE/0498 | Submission of Horizontal Alignment Drawing from CH 0+000 to 3+819.347km on Sampoor Soodakkudah Road (ETR170) | 08.04.2020 09.06.2020 | S-20-TR-1014/RE S-20-TR-1441/RE
529 | HA | 61 | RE | 23.03.2020 | ENC/TR01/PM/RE/0499 | Submission of Horizontal Alignment Drawing from CH 0+000 to 0+463.226km on Bahiriya Road, Thakwa Nagar (ETR061) | 20.04.2020 09.06.2020 | S-20-TR-1045/RE S-20-TR-1444/RE
530 | HA | 69 | RE | 23.03.2020 | ENC/TR01/PM/RE/0500 | Submission of Horizontal Alignment Drawing on Central Road (Kovil Road), Section i & ii Muthur (ETR069) | 08.04.2020 10.06.2020 | S-20-TR-1460/RE S-20-TR-1012/RE
531 | HA | 55 | RE | 23.03.2020 | ENC/TR01/PM/RE/0501 | Submission of Horizontal Alignment Drawing from CH 0+000 to 0+775.294km on PDS Road, Thakwa Nagar (ETR055) | 08.04.2020 09.06.2020 | S-20-TR-1010/RE S-20-TR-1437/RE
532 | HA | 54 | RE | 24.03.2020 | ENC/TR01/PM/RE/0502 | Submission of Horizontal Alignment Drawing from CH 0+000 to 0+480.94km on PDS Road, Thakwa Nagar (ETR054) | 20.04.2020 09.04.2020 | S-20-TR-1046/RE S-20-TR-1445/RE | Approved as noted
533 | Pavement Design | 63 | RE | 25.03.2020 | ENC/TR01/PM/RE/0503 | Submission of Pavement Design Report for CH 0+000 to 0+510 (ETR063) | 28.04.2020 | S-20-TR-1093/RE | Approved as noted
534 | Pavement Design | 53 | RE | 25.03.2020 | ENC/TR01/PM/RE/0504 | Resubmission of Pavement Design Report for CH 0+000 to 0+420 (ETR053)
535 | Pavement Design | 54 | RE | 25.03.2020 | ENC/TR01/PM/RE/0505 | Resubmission of Pavement Design Report for CH 0+000 to 0+320 (ETR054) | 18.06.2020 | S-20-TR-1543/RE
536 | Pavement Design | 61 | RE | 25.03.2020 | ENC/TR01/PM/RE/0506 | Submission of Pavement Design Report for CH 0+000 to 0+500 (ETR061) | 28.04.2020 | S-20-TR-1097/RE | Approved as noted
537 | HA | 154 | RE | 26.03.2020 | ENC/TR01/PM/RE/0507 | Submission of Horizontal Alignment Drawing for Sec i CH 0+000 - 0+853.264km and Sec ii CH 0+000 – 0+443.859km on Alimchenai School Road (ETR154) | 18.04.2020 09.06.2020 | S-20-TR-1443/RE S-20-TR-1436/RE | Approved as noted
538 | HA | 051&155 | RE | 26.03.2020 | ENC/TR01/PM/RE/0508 | Submission of Horizontal Alignment Drawing for CH 0+000 - 0+540.935km on ETR051 and CH 0+000 – 0+330.977km on ETR155 | 18.04.2020 09.06.2020 | S-20-TR-1043/RE S-20-TR-1447/RE
539 | HA | 156 | RE | 26.03.2020 | ENC/TR01/PM/RE/0509 | Submission of Horizontal Alignment Drawing for CH 0+000 - 0+191.636km on ETR156 | 20.04.2020 09.06.2020 | S-20-TR-1044/RE S-20-TR-1443/RE
540 | HA | 53 | RE | 26.03.2020 | ENC/TR01/PM/RE/0510 | Submission of Horizontal Alignment Drawing for CH 0+000 - 0+468.502km on ETR053 | 08.04.2020 09.06.2020 | S-20-TR-1009/RE S-20-TR-1438/RE
541 | HA | 63 | RE | 26.03.2020 | ENC/TR01/PM/RE/0511 | Submission of Horizontal Alignment Drawing for CH 0+000 - 0+480.127km on ETR063 | 08.04.2020 09.06.2020 | S-20-TR-1011/RE S-20-TR-1439/RE
542 | HA | 64 | RE | 26.03.2020 | ENC/TR01/PM/RE/0512 | Submission of Horizontal Alignment Drawing for CH 0+000 - 0+338.989km on ETR064 | 08.04.2020 09.06.2020 | S-20-TR-1017/RE S-20-TR-1446/RE
543 | HA | 68 | RE | 26.03.2020 | ENC/TR01/PM/RE/0513 | Submission of Horizontal Alignment Drawing for CH 0+000 - 0+253.433km on ETR068 | 08.04.2020 01.07.2020 | S-20-TR-1016/RE S-20-TR-1691/RE
544 | Pavement Design | 16 | RE | 26.03.2020 | ENC/TR01/PM/RE/0514 | Submission of Pavement Design Report for CH 0+000 to 4+580 (ETR016) | 18.04.2020 | 1040
545 | Pavement Design | 68 | RE | 27.03.2020 | ENC/TR01/PM/RE/0515 | Submission of Pavement Design Report for CH 0+180 to 0+510 (ETR068) | 28.04.2020 | S-20-TR-1095/RE | Approved as noted
546 | ICS | 171 | RE | 27.03.2020 | ENC/TR01/PM/RE/0516 | Submission of Initial Cross Section Drawing from 96+000 to 97+000 (ETR171) | 01.06.2020 | S-20-TR-1387/RE | Accepted
547 | Pavement Design | 64 | RE | 27.03.2020 | ENC/TR01/PM/RE/0517 | Submission of Pavement Design Report for CH 0+000 to 0+300 (ETR064) | 28.04.2020 | S-20-TR-1094/RE | Approved as noted
548 | Pavement Design | 69 | RE | 28.03.2020 | ENC/TR01/PM/RE/0518 | Submission of Pavement Design Report for Sec-i CH 0+000 - 0+302km & Sec-ii 0+000 – 0+309km (ETR069) | 28.04.2020 | S-20-TR-1092/RE | Approved as noted
549 | Culvert | 171 | RE | 28.03.2020 | ENC/TR01/PM/RE/0519 | Defects on the Culvert No. 84/1 (CH 83+350) Road ID ETR171 |  | pending
550 | ICS | 171 | RE | 28.03.2020 | ENC/TR01/PM/RE/0520 | Submission of Initial Cross Section Drawing from 95+000 to 96+000 (ETR171) | 01.06.2020 | S-20-TR-1388/RE | Accepted
551 | ICS | 171 | RE | 28.03.2020 | ENC/TR01/PM/RE/0521 | Submission of Initial Cross Section Drawing from 94+000 to 95+000 (ETR171) | 28.05.2020 | S-20-TR-1357/RE | Accepted
552 | ICS | 66 | RE | 29.03.2020 | ENC/TR01/PM/RE/0522 | Submission of Initial Cross Section Drawing from 0+000 to 0+566.6 (ETR066) | 18.06.2020 | S-20-TR-1546/RE | Resubmit
553 | IPA | No | RE | 30.03.2020 | ENC/TR01/PM/RE/0523 | On-Account for Interim Payment Application – (February 2020) |  | pending
554 | ICS | 171 | RE | 31.03.2020 | ENC/TR01/PM/RE/0524 | Submission of Initial Cross Section Drawing from 93+000 to 94+000 (ETR171) | 28.05.2020 | S-20-TR-1360/RE | Accepted
555 | Pavement Design | 55 | RE | 31.03.2020 | ENC/TR01/PM/RE/0525 | Submission of Pavement Design Report for Sec-i CH 0+000 - 0+400km & Sec-ii 0+000 – 0+200km (ETR055) | 28.04.2020 | S-20-TR-1096/RE | Approved as noted
556 | Design | 57 | TL | 01.04.2020 | ENC/TR01/PM/TL/0526 | Notice of Claim for affected the work due to Design Change on Road ID ETR057 | 22.05.2020 | S-20-1323/JR
557 | ICS | 171 | RE | 02.04.2020 | ENC/TR01/PM/RE/0527 | Submission of Initial Cross Section Drawing from 98+000 to 99+000 (ETR171) | 04.06.2020 | S-20-TR-1426/RE | Accepted
558 | ICS | 171 | RE | 02.04.2020 | ENC/TR01/PM/RE/0528 | Submission of Initial Cross Section Drawing from 97+000 to 98+000 (ETR171) | 03.06.2020 | S-20-TR-1419/RE | Accepted
559 | VA | 127 | RE | 02.04.2020 | ENC/TR01/PM/RE/0529 | Submission of Vertical Alignment Drawing from CH 0+000 to 0+984km on Methagama Central Road, Somapura (ETR127) | 15.04.2020 11.06.2020 | S-20-TR-1031/RE S-20-TR-1475/RE | Approved
560 | ICS | 171 | RE | 03.04.2020 | ENC/TR01/PM/RE/0530 | Submission of Initial Cross Section Drawing and Levelling Sheet from 92+000 to 93+000 (ETR171) | 16.05.2020 | S-20-TR-1212/RE | Accepted
561 | VA | 57 | RE | 02.04.2020 | ENC/TR01/PM/RE/0531 | Submission of Vertical Alignment Drawing from CH 0+000 to 0+620km on Kiliveddi West Road (ETR057) |  | pending
562 | Pavement Design | 171 | TL | 03.04.2020 | ENC/TR01/PM/TL/0532 | Pavement Design Revised Proposal for Ch. 78+240 to 88+500km on Road ID ETR171 | 24.04.2020 | S-20-1213/JR
563 | Issues | No | TL | 05.04.2020 | ENC/TR01/PM/RE/0533 | Issues on Preparing DCSs and Construction of Embankment Type-1 | 08.06.2020 | S-20-TR-1432/RE
564 | Shutdown | No | TL | 05.04.2020 | ENC/TR01/PM/TL/0533 | Notice of Shut Down the Site Works due to Outbreak of New Corona-virus (COVID 19) |  | pending
565 | Pavement Design | 170 | RE | 05.04.2020 | ENC/TR01/PM/RE/0534 | Pavement Design 170 | 23.05.2020 | S-20-TR-1304/RE | Accepted
566 | Shutdown | No | TL | 06.04.2020 | ENC/TR01/PM/TL/0535 | Notice of Shut Down the Site Works due to Outbreak of New Coronavirus (COVID 19) and Consequence Curfew Prevailed |  | pending
567 | Work Program | No | TL | 06.04.2020 | ENC/TR01/PM/TL/0536 | Recommencement of Works |  | pending
568 | Pavement Design | 155 | RE | 08.04.2020 | ENC/TR01/PM/RE/0537 | Submission of Pavement Design Report for CH 0+000 to 0+335 (ETR155) | 23.05.2020 | S-20-TR-1307/RE | Approved as noted
569 | Employee List | No | TL | 12.04.2020 | ENC/TR01/PM/TL/0538 | Employee List for Curfew Passes |  | pending
570 | Pavement Design | 156 | RE | 16.04.2020 | ENC/TR01/PM/RE/0539 | Submission of Pavement Design Report for CH 0+000 to 0+180 (ETR156) | 19.05.2020 | S-20-TR-1239/RE | Approved as noted
571 | ESO Progress | No | RE | 16.04.2020 | ENC/TR01/PM/RE/0540 | Environmental and Social Monthly Progress Report for March 2020 |  | pending
572 | Pavement Design | 67 | RE | 16.04.2020 | ENC/TR01/PM/RE/0541 | Submission of Pavement Design Report for CH 0+000 to 0+480 (ETR067) | 19.05.2020 | S-20-TR-1238/RE | Approved as noted
573 | Pavement Design | 6 | RE | 17.04.2020 | ENC/TR01/PM/RE/0542 | Submission of Pavement Design Report for CH 0+000 to 7+150 (ETR006) | 18.05.2020 | S-20-TR-1224/RE | Approved as noted
574 | ICS | 171 | RE | 18.04.2020 | ENC/TR01/PM/RE/0543 | Submission of Initial Cross Section Drawing and Levelling Sheet from 100+000 to 101+000 (ETR171) | 23.06.2020 | S-20-TR-1585/RE | Accepted
575 | Pavement Design | 171 | RE | 18.04.2020 | ENC/TR01/PM/RE/0544 | Pavement Design Report for Ch. 78+240 to 88+500km on Road ID ETR171 (Revision 2) |  | pending
576 | Pavement Design | 66 | RE | 19.04.2020 | ENC/TR01/PM/RE/0545 | Submission of Pavement Design Report for CH 0+000 to 0+500 km on the Road ID ETR066 | 15.06.2020 | S-20-TR-1518/RE
577 | Employee List | No | RE | 20.04.2020 | ENC/TR01/PM/GEN/0546 | Employee List of the Project - Mutur |  | NNR
578 | Employee List | No | RE | 20.04.2020 | ENC/TR01/PM/GEN/0547 | Employee List of the Project - Seruvila |  | NNR
579 |  |  |  |  | ENC/TR01/PM/RE/0548 |  |  | pending
580 | Employee List | No | TL | 21.04.2020 | ENC/TR01/PM/TL/0549 | Employee List for Curfew Passes |  | pending
581 | Culvert Report | 170 |  | 23.04.2020 | ENC/TR01/PM/RE/0550 | Culvert Conditional Report for the Road ETR170 | 30.05.2020 | S-20-TR-1365/RE
582 | Curfew | No | GEN | 23.04.2020 | ENC/TR01/PM/GEN/0551 | Request Permission to Proceed the Survey Work at Site on Curfew Period |  | NNR
583 | Employee List | No | GEN | 23.04.2020 | ENC/TR01/PM/RE/0552 | Current Employees List of the Above Project |  | NNR
584 | Culvert Report | 156 | RE | 23.04.2020 | ENC/TR01/PM/RE/0553 | Culvert Conditional Report for the Road ETR156 (1) | 19.05.2020 | S-20-TR-1248/RE | Accepted
585 | Culvert Report | 154 | RE | 23.04.2020 | ENC/TR01/PM/RE/0554 | Culvert Conditional Report for the Road ETR154 (1&2) | 12.05.2020 | S-20-TR-1173/RE
586 | Pavement Design | 165 | RE | 23.04.2020 | ENC/TR01/PM/RE/0555 | Submission of Pavement Design Report for CH 0+000 to 1+350 km on the Road ID ETR165 | 23.05.2020 | S-20-TR-1303/RE | Approved as noted
587 | Pavement Design | 132 | RE | 23.04.2020 | ENC/TR01/PM/RE/0556 | Submission of Pavement Design Report for CH 0+000 to 0+510 km on the Road ID ETR132 | 19.06.2020 | S-20-TR-1583/RE
588 | Pavement Design | 154 | RE | 24.04.2020 | ENC/TR01/PM/RE/0557 | Submission of Pavement Design Report for ETR154 of Section I&II from CH 0+000 to 0+800 and 0+000 to 0+440Km | 23.05.2020 | S-20-TR-1302/RE | Approved as noted
589 | Crack Survey | 166 | RE | 24.04.2020 | ENC/TR01/PM/RE/0558 | Submission of Crack Survey Report from CH 2+960 to 4+220 km (ETR166) | 02.05.2020 | S-20-TR-1113/RE
590 |  |  |  |  | ENC/TR01/PM/RE/0559
591 | Curfew | No | RE | 24.04.2020 | ENC/TR01/PM/GEN/0560 | Request Permission to Proceed the Survey Work at Site on Curfew Period
592 | Employee List | No | RE | 24.04.2020 | ENC/TR01/PM/RE/0561 | Current Employees List of the Above Project
593 | DCS | 58 | RE | 28.04.2020 | ENC/TR01/PM/RE/0562 | Submission of Design Cross Section Drawings from CH 0+000 to 0+530km (ETR058) | 30.06.2020 | S-20-TR-1673/RE
594 | Covid19 | No | RE | 28.04.2020 | ENC/TR01/PM/TL/0563 | Health And Safety Emergency Covid-19 Safety Plan
595 | Cost Completion | No | RE | 28.04.2020 | ENC/TR01/PM/RE/0564 | Submission of Cost to Completion
596 | Culvert Report | 131 | RE | 30.04.2020 | ENC/TR01/PM/RE/0565 | Culvert Conditional Report for the Road ETR131 | 19.05.2020 | S-20-TR-1234/RE
597 | Progress Report | No | RE | 30.04.2020 | ENC/TR01/PM/RE/0566 | Monthly Progress Report – 06 for the Month of March – 2020 | 09.05.2020 | S-20-TR-1145/RE | Re Submit
598 | Culvert Report | 53 | RE | 30.04.2020 | ENC/TR01/PM/RE/0567 | Culvert Conditional Report for the Road ETR053 | 15.05.2020 | S-20-TR-1205/RE
599 | Culvert Report | 16 | RE | 30.04.2020 | ENC/TR01/PM/RE/0568 | Culvert Conditional Report for the Road ETR016 | 27.05.2020 | S-20-TR-1326/RE
600 | Culvert Report | 67 | RE | 30.04.2020 | ENC/TR01/PM/RE/0569 | Culvert Conditional Report for the Road ETR067 | 15.05.2020 | S-20-TR-1204/RE
601 | Culvert Report | 54 | RE | 30.04.2020 | ENC/TR01/PM/RE/0570 | Culvert Conditional Report for the Road ETR054 | 19.05.2020 | S-20-TR-1235/RE
602 | Culvert Report | 60 | RE | 30.04.2020 | ENC/TR01/PM/RE/0571 | Culvert Conditional Report for the Road ETR060 | 26.05.2020 | S-20-TR-1262/RE
603 | Culvert Report | 70 | RE | 30.04.2020 | ENC/TR01/PM/RE/0572 | Culvert Conditional Report for the Road ETR070 | 19.05.2020 | S-20-TR-1247/RE
604 | Culvert Report | 63 | RE | 30.04.2020 | ENC/TR01/PM/RE/0573 | Culvert Conditional Report for the Road ETR063 | 12.05.2020 | S-20-TR-1170/RE
605 | Culvert Report | 66 | RE | 30.04.2020 | ENC/TR01/PM/RE/0574 | Culvert Conditional Report for the Road ETR066 | 15.05.2020 | S-20-TR-1206/RE
606 | Culvert Report | 164 | RE | 30.04.2020 | ENC/TR01/PM/RE/0575 | Culvert Conditional Report for the Road ETR164 | 14.05.2020 | S-20-TR-1194/RE
607 | Culvert Report | 134 | RE | 30.04.2020 | ENC/TR01/PM/RE/0576 | Culvert Conditional Report for the Road ETR134 | 15.05.2020 | S-20-TR-1203/RE
608 | Culvert Report | 69 | RE | 30.04.2020 | ENC/TR01/PM/RE/0577 | Culvert Conditional Report for the Road ETR069 | 12.05.2020 | S-20-TR-1172/RE
609 | Layer Thickness | No | TL | 30.04.2020 | ENC/TR01/PM/TL/0578 | Request to Re-Access Determination of Sub-base Layer Thickness for Payment | 12.05.2020 | S-20-1265/JR
610 |  |  |  |  | ENC/TR01/PM/RE/0579 |  |  | pending
611 |  |  |  |  | ENC/TR01/PM/RE/0580 |  |  | pending
612 | Pavement Design | 18 | RE |  | ENC/TR01/PM/RE/0581 | Submission of Pavement Design Report for ETR018 from CH 0+000 – 1+800 Km | 22.05.2020 | S-20-TR-1289/RE | Approved as noted
613 | Covid19 | No | TL | 03.03.2020 | ENC/TR01/PM/RE/0582 | Resubmission of Method Statement for Health & Safety in Work Place and Work Site Under COVID 19 Outbreaks | 04.05.2020 | S-20-1235/JR
614 |  |  |  |  | ENC/TR01/PM/RE/0583 |  |  | pending
615 | DCS | 127 | RE | 04.05.2020 | ENC/TR01/PM/RE/0584 | Submission of Design Cross Section Drawings from CH 0+000 to 0+980km (ETR127) | 01.06.2020 | S-20-TR-1382/RE
616 | Pavement Design | 64 | RE | 04.05.2020 | ENC/TR01/PM/RE/0585 | Submission of Pavement Design Report for ETR64 from CH Km | 15.05.2020 15.05.2020 | S-20-1278/DTL S-20-1279/DTL
617 | Culvert Report | 56 | RE | 06.05.2020 | ENC/TR01/PM/RE/0586 | Culvert Conditional Report for the Road ETR056 |  | pending
618 | Road close | 127 | RE | 08.05.2020 | ENC/TR01/PM/RE/0587 | Request to Close the Road Temporarily for a short Period on ETR127 at the Culvert Location CH 0+718km | 14.05.2020 | S-20-TR-1187/RE
619 | Culvert Report | 56 | RE | 08.05.2020 | ENC/TR01/PM/RE/0588 | Culvert Conditional Report for the Road ETR056 | 12.05.2020 | S-20-TR-1171/RE
620 | Covid19 | No | RE | 09.05.2020 | ENC/TR01/PM/RE/0589 | COVID-19 Preventive Team | 13.05.2020 | S-20-TR-1180/RE
621 | Culvert Drawing | 166 | RE | 10.05.2020 | ENC/TR01/PM/RE/0590 | Submission of Half Encasement Culvert Drawing at CH 01+084Km (ETR166) | 22.05.2020 | S-20-TR-1287/RE | Approved as noted
622 | ICS | 6 | RE | 10.05.2020 | ENC/TR01/PM/RE/0591 | Submission of Initial Cross Section Drawing and Levelling Sheet from 02+000 to 03+000 (ETR006) | 06.07.2020 | 1749
623 | ESO Progress | No | RE | 11.05.2020 | ENC/TR01/PM/RE/0592 | Monthly Environmental & Social Progress Reports for the Month of April–2020 |  | pending
624 | Pavement Design | 171 | RE | 11.05.2020 | ENC/TR01/PM/RE/0593 | Submission of Pavement Design Report for ETR171 from CH 91+420 to 108+420Km | 22.05.2020 | S-20-TR-1308/RE | Re Submit
625 | Source Approval | No | RE | 11.05.2020 | ENC/TR01/PM/RE/0594 | Submission of 28 days Compressive Strength Test Report for Concrete Trail Mix of Grade 15 & 25 from Tokyo Super Ready Mix Concrete - Chinabay | 18.05.2020 | S-20-TR-1225/RE | Accepted
626 | Road close | No | RE | 12.05.2020 | ENC/TR01/PM/RE/0595 | Request for Road closing for a short period on ETR166 for the culvert 2/4 and 3/1 | 14.05.2020 | S-20-TR-1198/RE
627 | Road close | No | RE | 12.05.2020 | ENC/TR01/PM/RE/0596 | Request to Close the Road Temporarily for a short Period on ETR057 at the Culvert Location CH 0+613km | 14.05.2020 | S-20-TR-1197/RE
628 | ICS | 6 | RE | 12.05.2020 | ENC/TR01/PM/RE/0597 | Submission of Initial Cross Section Drawing from 0+000 to 1+000 (ETR006) | 27.05.2020 | S-20-TR-1335/RE | Accepted
629 | ICS | 6 | RE | 12.05.2020 | ENC/TR01/PM/RE/0598 | Submission of Initial Cross Section Drawing from 1+000 to 2+000 (ETR006) | 27.06.2020 | S-20-TR-1635/RE | Accepted
630 | VA | 171 | RE | 12.05.2020 | ENC/TR01/PM/RE/0599 | Submission of Vertical Profile Drawings from 78+300 to 82+500 Km (ETR171) | 23.05.2020 | S-20-TR-1345a/RE | Approved
631 | Notice | No | TL | 13.05.2020 | ENC/TR01/PM/TL/0600 | Notice of Claim: Disruption of Work due to Government Directives, Guide lines and Regulations | 01.07.2020 | S-20-1593/JR
632 | IPA | No | RE | 13.05.2020 | ENC/TR01/PM/RE/0601 | Interim Payment Application - 07 for the Month of March 2020
633 | Yard | No | GEN | 14.05.2020 | ENC/TR01/PM/GEN/0602 | Request for Approval of Disposal Yard
634 | Culvert Drawing | 6 | RE | 13.05.2020 | ENC/TR01/PM/RE/0603 | Submission of Reconstructions Box Culvert Drawing at CH 02+860Km (ETR006) | 27.05.2020 | S-20-TR-1328/RE
635 | Culvert Drawing | 6 | RE | 13.05.2020 | ENC/TR01/PM/RE/0604 | Submission of Reconstructions Box Culvert Drawing at CH 06+006Km (ETR006) | 27.05.2020 | S-20-TR-1329/RE
636 | Culvert Drawing | 6 | RE | 13.05.2020 | ENC/TR01/PM/RE/0605 | Submission of Reconstructions Box Culvert Drawing at CH 01+508Km (ETR006) | 27.05.2020 | S-20-TR-1330/RE
637 | Culvert Drawing | 6 | RE | 13.05.2020 | ENC/TR01/PM/RE/0606 | Submission of Reconstructions Box Culvert Drawing at CH 00+436.5Km (ETR006) | 27.05.2020 | S-20-TR-1331/RE
638 | Hygiene | No | TL | 14.05.2020 | ENC/TR01/PM/TL/0607 | Hygiene and Other items Requested | 18.05.2020 | S-20-1288/JR
639 | EMC | 171 | RE | 16.05.2020 | ENC/TR01/PM/RE/0608 | Submission of Environmental Monitoring Checklist for ETR 171
640 | Yard | 127 | RE | 14.05.2020 | ENC/TR01/PM/RE/0609 | Request for Approval of Disposal Yard at ETR127 Road
641 | IPA | No | RE | 14.05.2020 | ENC/TR01/PM/RE/0610 | Interim Payment Application - 08 for the Month of April 2020
642 | Contractor's Staff | No | TL | 15.05.2020 | ENC/TR01/PM/TL/0611 | Submission of Proposal for Contractor’s Staff (Site Engineer) | 18.05.2020 | S-20-1296/DTL
643 | Engineer's Staff | No | RE | 15.05.2020 | ENC/TR01/PM/RE/0612 | Appointment of Operatives for the Engineer’s Staff (Material Technician) | 23.05.2020 | S-20-TR-1312/RE
644 | SSEMAP | No | TL | 15.05.2020 | ENC/TR01/PM/TL/0613 | Submission of Site Specific Environmental Management Action Plan (SSEMAP) | 17.06.2020 | S-20-1478/JR
645 | Pavement Design | 164 | RE | 15.05.2020 | ENC/TR01/PM/RE/0614 | Submission of Pavement Design Report for CH 0+000 to 1+170 (ETR164) | 22.05.2020 | S-20-TR-1368/RE
646 | Source Approval | No | RE | 15.05.2020 | ENC/TR01/PM/RE/0615 | Submission for Source Approval of Sub Base Material – M.K.C.M. Jayalath’s Borrow Pit at Miriswewa, Rotawewa | 19.05.2020 | S-20-TR-1241/RE | Conditionally Approved
647 | Source Approval | No | RE | 15.05.2020 | ENC/TR01/PM/RE/0616 | Submission for Source Approval of 20mm Aggregate from E&C Mihinthale Crusher Plant |  | 1314
648 | Source Approval | No | RE | 15.05.2020 | ENC/TR01/PM/RE/0617 | Submission for Source Approval of Embankment and Sub Base Material from Nadauththu Borrow Pit at Kinniya |  | 1242
649 | Source Approval | No | RE | 15.05.2020 | ENC/TR01/PM/RE/0618 | Submission for Source Approval of Embankment Material from Ulpath Wewa Borrow pit at Thamplagamuwa
650 | Crack Survey | No | RE | 15.05.2020 | ENC/TR01/PM/RE/0619 | Submission of Crack Survey Report from CH 79+870 to 81+220 km (ETR171) | 23.06.2020 | S-20-TR-1584/RE | Resubmit
651 | Pavement Design | 51 | RE | 15.05.2020 | ENC/TR01/PM/RE/0620 | Submission of Pavement Design Report for ETR051 from CH 0+000 – 0+490 Km | 12.06.2020 | S-20-TR-1481/RE | Approved
652 | Issues | 171 | TL | 15.05.2020 | ENC/TR01/PM/TL/0621 | Issues on Preparing DCSs and Construction of Sub-base on ETR171 (A15) Road
653 | Conditional Report | 6 | RE | 15.05.2020 | ENC/TR01/PM/RE/0622 | Resubmission of Existing Culvert Condition Report ETR006 | 17.06.2020 | S-20-TR-1524/RE
654 | Crack Survey | 6 | RE | 16.05.2020 | ENC/TR01/PM/RE/0623 | Submission of Crack Survey Report from CH 0+000 to 0+325 km (ETR006) | 22.05.2020 | S-20-TR-1293/RE
655 |  |  |  |  | 624 | Requesting for Lab Verification of Asphalt Binder Course & Wearing Type 01&03 Courses |  | 1293
656 | Lab Verification | No | RE | 16.05.2020 | ENC/TR01/PM/RE/0625 | Requesting for Lab Verification of Asphalt Binder Course & Wearing Type 01&03 Courses
657 | EMC | 127 | RE | 16.05.2020 | ENC/TR01/PM/RE/0626 | Submission of Environmental Monitoring Checklist for ETR 127
658 | EMC | 130 | RE | 16.05.2020 | ENC/TR01/PM/RE/0627 | Submission of Environmental Monitoring Checklist for ETR 0130
659 | Covid19 | No | GEN | 16.05.2020 | ENC/TR01/PM/GEN/0628 | Request Clearance Certificate to Travel out of District due to their Official Work
660 | Covid19 | No | GEN | 16.05.2020 | ENC/TR01/PM/GEN/0629 | Request Curfew Pass to Travel from Muthur to out of Districts due to their Official Work
661 | Covid19 | No | GEN | 16.05.2020 | ENC/TR01/PM/RE/0630 | Request Curfew Pass for Material Transportation
662 | Issues | 171 | TL | 16.05.2020 | ENC/TR01/PM/TL/0631 | Issues on Preparing DCSs and Construction of DGAB on ETR171 (A15) Road
663 | Issues | 6 | TL | 18.05.2020 | ENC/TR01/PM/TL/0632 | Issues on Preparing Culvert Drawings on the Road ID ETR006 | 26.05.2020 | S-20-1334/JR
664 | Initial Maintenance | 6 | RE | 18.05.2020 | ENC/TR01/PM/RE/0633 | Request to do the Initial Maintenance on the Road ID ETR006 | 20.05.2020 | S-20-TR-1269/RE
665 | Progress Report | No | RE | 18.05.2020 | ENC/TR01/PM/RE/0634 | Submission of Monthly Progress Report No-07 for the Month of April - 2020 | 28.05.2020 | S-20-TR-1351/RE
666 | Source Approval | No | RE | 18.05.2020 | ENC/TR01/PM/RE/0635 | Submission for Concrete Mix Design of Grade 15(20) | 26.05.2020 | S-20-TR-1321/RE
667 | Source Approval | No | RE | 18.05.2020 | ENC/TR01/PM/RE/0636 | Submission for Concrete Mix Design of Grade 25/20 | 26.05.2020 | S-20-TR-1321/RE
668 | Proposal | 171 | RE | 18.05.2020 | ENC/TR01/PM/RE/0637 | Submitting the Proposal to Construct the Concrete Pitching to Protect the Embankment on the Road ID ETR171 | 28.05.2020 | S-20-TR-1358/RE
669 | Request | No | GEN | 18.05.2020 | ENC/TR01/PM/GEN/0638 | Request for opening savings accounts for our employees
670 | Public Request | 165 | RE | 18.05.2020 | ENC/TR01/PM/RE/0639 | Public Requests – Dehiwatta to 5th speel Road (ETR 165) | 19.06.2020 | S-20-TR-1523/RE
671 | Source Approval | No | RE | 19.05.2020 | ENC/TR01/PM/RE/0640 | Submission of 28 days Compressive Strength Test Report for Concrete Trail Mix of Grade 15 & 25 from Tokyo Super Ready Mix Concrete - Chinabay | 28.05.2020 | S-20-TR-1340/RE
672 | U-Drain | 171 | RE | 19.05.2020 | ENC/TR01/PM/RE/0641 | Submission of Drain Schedule from CH 78+300 – 84+400 on Batticaloa Thirukondiyadimadu Trincomalee Road (ETR 171) | 03.07.2020 | 1725
673 | Yard | No | RE | 20.05.2020 | ENC/TR01/PM/RE/0642 | Method Statement for the Operation of Stock Yard & Disposal Yard | 02.06.2020 | S-20-TR-1399/RE
674 | Deport Tray | No | RE | 23.05.2020 | ENC/TR01/PM/RE/0643 | Submission of Deport Tray Results carried out to Binder Distributor - BS 04 (wp LM-2298) | 28.05.2020 | S-20-TR-1356/RE
675 | Insurance Card | No | RE | 20.05.2020 | ENC/TR01/PM/RE/0644 | Extension of Insurance of Vehicle for Type 02 & Type 04
676 | Source Approval | No | RE | 20.05.2020 | ENC/TR01/PM/RE/0645 | Request to change the Grade of Concrete from Gr.30 to Gr. 25 on the Rural Road Box Culverts
677 | Road close | 130 | RE | 20.05.2020 | ENC/TR01/PM/RE/0646 | Request to Close the Road Temporarily for a couple of days on ETR130 at the Location CH 0+000 to 0+600km | 23.05.2020 | S-20-TR-1309/RE | No Objection
678 | Safety Audit | No | RE | 22.05.2020 | ENC/TR01/PM/RE/0647 | Submission of Road Safety Audit Reports | 27.05.2020 | S-20-TR-1324/RE
679 | Crack Survey | 6 | RE | 22.05.2020 | ENC/TR01/PM/RE/0648 | Submission of Crack Survey Report from CH 0+325 to 1+555 km (ETR006) | 12.06.2020 | S-20-TR-1486/RE | Resubmit
680 | VA | 6 | RE | 22.05.2020 | ENC/TR01/PM/RE/0649 | Submission of Vertical Alignment Drawing from CH 00+000 to 03+900km (ETR006) | 04.06.2020 | S-20-TR-1421/RE
681 | ICS | 164 | RE | 22.05.2020 | ENC/TR01/PM/RE/0650 | Submission of Initial Cross Section Drawing from 0+000 to 1+470 (ETR164) | 15.06.2020 | S-20-TR-1516/RE | Accepted
682 | VA | 171 | RE | 22.05.2020 | ENC/TR01/PM/RE/0651 | Submission of Vertical Profile Drawings from 82+500 to 88+500 Km (ETR171) | 01.06.2020 | S-20-TR-1392/RE | Approved as noted
683 | IPA | No | RE | 22.05.2020 | ENC/TR01/PM/RE/0652 | Resubmission of Interim Payment Supporting - 07 for the Month of March 2020
684 | Progress Report | No | RE | 22.05.2020 | ENC/TR01/PM/RE/0653 | Submission of Monthly Progress Report No - 04 for the Month of January - 2020
685 | Progress Report | No | RE | 22.05.2020 | ENC/TR01/PM/RE/0654 | Submission of Monthly Progress Report No - 05 for the Month of February - 2020
686 | Contractor's Staff | No | TL | 25.05.2020 | ENC/TR01/PM/TL/0655 | Key Staff - DPM (Eng. Dissnayake) | 28.05.2020 | S-20-1342/DTL
687 | Culvert Drawing | 166 | RE | 23.05.2020 | ENC/TR01/PM/RE/0656 | Resubmission of Reconstruction of Box Culvert Drawing at CH 02+815Km - ETR166 | 03.06.2020 | S-20-TR-1418/RE | Approved as noted
688 | Culvert Drawing | 57 | RE | 23.05.2020 | ENC/TR01/PM/RE/0657 | Resubmission of Culvert Construction Drawing of 1/2 (CH 0+613.30) - ETR057 | 02.06.2020 | S-20-TR-1398/RE | Approved as noted
689 | Covid19 | No | RE | 23.05.2020 | ENC/TR01/PM/RE/0658 | Proposed Isolation Room for a suspected Patient with Symptoms of COVID-19 | 27.05.2020 | S-20-TR-1343/RE
690 | Curfew | No | GEN | 24.05.2020 | ENC/TR01/PM/GEN/0659 | Request Curfew Pass to Travel from Muthur to out of Districts due to their Official Work
691 | Road close | 130 | RE | 25.05.2020 | ENC/TR01/PM/RE/0660 | Request to Close the Road Temporarily for a couple of days on ETR130 at the Location CH 0+000 to 1+180 km | 27.05.2020 | S-20-TR-1345/RE
692 | Road close | 130 | RE | 25.05.2020 | ENC/TR01/PM/RE/0661 | Request to Close the Road Temporarily on ETR166 at the Location CH 1+000 to 01+185 km | 27.05.2020 | S-20-TR-1344/RE
693 | Variation | No | TL | 25.05.2020 | ENC/TR01/PM/TL/0662 | Variation to the Works under subclause 13.1 (c), (e), and (f) of GCoC
694 | Cost Estimation | No | RE | 25.05.2020 | ENC/TR01/PM/RE/0663 | Submission of Cost Estimation for ETR006 | 13.06.2020 | S-20-TR-1494/RE
695 | DCS | 57 | RE | 25.05.2020 | ENC/TR01/PM/RE/0664 | Resubmission of Design Cross Section Drawings from CH 0+080 to 0+621.51km (ETR057) | 10.06.2020 | S-20-TR-1461/RE
696 | DCS | 59 | RE | 25.05.2020 | ENC/TR01/PM/RE/0665 | Resubmission of Design Cross Section Drawings from CH 0+000 to 0+530 km (ETR059) | 13.06.2020 | S-20-TR-1497/RE
697 | VA | 155 | RE | 25.05.2020 | ENC/TR01/PM/RE/0666 | Submission of Vertical Profile Drawings from 0+000 to 0+330.982 Km on ETR155 Section 1 | 04.06.2020 | S-20-TR-1422/RE
698 | VA | 6 | RE | 25.05.2020 | ENC/TR01/PM/RE/0667 | Submission of Vertical Profile Drawings from 3+900 to 7+150 Km on ETR006 | 04.06.2020 | S-20-TR-1423/RE
699 | VA | 64 | RE | 25.05.2020 | ENC/TR01/PM/RE/0668 | Submission of Vertical Profile Drawings from 0+000 to 0+338.989 Km on ETR064 | 04.06.2020 | S-20-TR-1424/RE
700 | ICS | 155 | RE | 26.05.2020 | ENC/TR01/PM/RE/0669 | Submission of Initial Cross Section Drawing from 0+000 to 0+331 (ETR155) | 20.06.2020 | S-20-TR-1572/RE | Accepted
701 | ICS | 6 | RE | 26.05.2020 | ENC/TR01/PM/RE/0670 | Submission of Initial Cross Section Drawing from 3+000 to 4+000 (ETR006) | 06.07.2020 | 1748
702 | Progress Report | No | RE | 26.05.2020 | ENC/TR01/PM/RE/0671 | Resubmission of Monthly Progress Report No-06 (Revision - 01) for the Month of March - 2020 | 13.06.2020 | S-20-TR-1489/RE | Accepted With Comments
703 | EMC | 70 | RE | 26.05.2020 | ENC/TR01/PM/RE/0672 | Submission of Environmental Monitoring Checklist for ETR 070 | 22.06.2020 | S-20-1523/JR
704 | Public Request | 57 | RE | 26.05.2020 | ENC/TR01/PM/RE/0673 | Public Requests – Kiliveddy West Road (ETR 057) | 03.05.2020 | S-20-TR-1412/RE
705 | DCS | 166 | RE | 26.05.2020 | ENC/TR01/PM/RE/0674 | Submission of Design Cross Section Drawings from CH 00+110 to 01+000 km (ETR166) | 13.06.2020 | S-20-TR-1493/RE | Approved as noted
706 | DCS | 166 | RE | 26.05.2020 | ENC/TR01/PM/RE/0675 | Submission of Design Cross Section Drawings from CH 01+000 to 02+000 km (ETR166) | 24.07.2020 | 1939 | 3
707 | Culvert | No | RE | 26.05.2020 | ENC/TR01/PM/RE/0676 | Obstruction on the Culvert Construction due to the Water Pipes at the Culvert Locations on ETR166 | 24.06.2020 07.07.2020 | S-20-TR-1602/RE S-20-TR-1755/RE
708 | Monthly Work Program | No | TL | 27.05.2020 | ENC/TR01/PM/TL/0677 | Submission of Monthly Work Program - June 2020 | 03.06.2020 | S-20-TR-1414/RE
709 | HA | 171 | RE | 27.05.2020 | ENC/TR01/PM/RE/0678 | Resubmission of Horizontal Alignment Drawing from CH 102+000 to 108+416.37 Km (ETR171) | 30.05.2020 | S-20-TR-1361/RE
710 | ICS | 6 | RE | 27.05.2020 | ENC/TR01/PM/RE/0679 | Submission of Initial Cross Section Drawing from 4+000 to 5+000 (ETR006) | 06.07.2020 | 1747
711 | ICS | 64 | RE | 27.05.2020 | ENC/TR01/PM/RE/0680 | Submission of Initial Cross Section Drawing from CH 0+000 to 0+338.99 (ETR064) | 23.06.2020 | S-20-TR-1587/RE | Accepted
712 | Source Approval | No | RE | 27.05.2020 | ENC/TR01/PM/RE/0681 | Resubmission for Source Approval of Admixture for Concreting from Chryso Optima SL 1090 | 03.06.2020 | S-20-TR-1402/RE
713 | Pavement Design | 171 | RE | 27.05.2020 | ENC/TR01/PM/RE/0682 | Resubmission of Pavement Design Report for CH 91+420 to 108+420 (ETR171) | 28.05.2020 | S-20-TR-1359/RE
714 | Culvert Drawing | 166 | RE | 27.05.2020 | ENC/TR01/PM/RE/0683 | Resubmission of Reconstruction of Box Culvert Drawing at CH 02+815Km - ETR166 | 03.06.2020 | S-20-TR-1417/RE
715 | Culvert Drawing | 6 | RE | 27.05.2020 | ENC/TR01/PM/RE/0684 | Submission of Widening of Pipe Culvert Drawing at CH 01+572Km - ETR006 | 03.06.2020 | S-20-TR-1415/RE
716 | DCS | 58 | RE | 28.05.2020 | ENC/TR01/PM/RE/0685 | Resubmission of Design Cross Section Drawings from CH 0+000 to 0+530 km (ETR058) | 30.06.2020 | S-20-TR-1673/RE
717 | VA | 16 | RE | 28.05.2020 | ENC/TR01/PM/RE/0686 | Submission of Vertical Profile Drawings from 0+000 to 4+552.21 Km on ETR016
718 | DCS | 166 | RE | 28.05.2020 | ENC/TR01/PM/RE/0687 | Submission of Design Cross Section Drawings from CH 3+000 to 4+000km (ETR166) | 20.06.2020 | S-20-TR-1565/RE
719 | Calibration | No | RE | 29.05.2020 | ENC/TR01/PM/RE/0688 | Instrument Calibration for Total Station TN 0442 & IZ004883 Report | 03.06.2020 | S-20-TR-1415/RE
720 | Yard | No | RE | 29.05.2020 | ENC/TR01/PM/RE/0689 | Resubmission of Stock Yard and Disposal Yard | 15.07.2020 | 1828
721 | Contractor's Staff | No | TL | 29.05.2020 | ENC/TR01/PM/TL/0690 | Submission of Proposal for Contractor’s Staff (Ms.Sathya, Mr. Darshana, Mr. Wickramerathne) | 03.06.2020 | S-20-1393/DTL
722 | Source Approval | No | RE | 30.05.2020 | ENC/TR01/PM/RE/0691 | Submission for Approval of Concrete Mix Design Grade15,20 & 25 with Chriyso Optima SL1090 | 06.06.2020 | S-20-TR-1428/RE
723 | Source Approval | No | RE | 30.05.2020 | ENC/TR01/PM/RE/0692 | Resubmission for Source Approval of Admixtures for Concreting from Chryso Lanka & Curing Agent | 03.06.2020 | S-20-TR-1402/RE
724 | Covid19 | No | RE | 30.05.2020 | ENC/TR01/PM/RE/0693 | Proposed Isolation Room for a suspected Patient with Symptoms of COVID-19 at Project office | 15.06.2020 | S-20-TR-1507/RE
725 | DCS | 166 | RE | 01.06.2020 | ENC/TR01/PM/RE/0694 | Submission of Design Cross Section Drawings from CH 02+010 to 03+000km (ETR166) | 02.07.2020 | 1720
726 | ICS | 6 | RE | 01.06.2020 | ENC/TR01/PM/RE/0695 | Submission of Initial Cross Section Drawing from 05+000 to 06+000 (ETR006) | 06.07.2020 | 1746
727 | ICS | 6 | RE | 01.06.2020 | ENC/TR01/PM/RE/0696 | Submission of Initial Cross Section Drawing from 06+000 to 07+000 (ETR006) | 06.07.2020 | 1744
728 | ICS | 6 | RE | 01.06.2020 | ENC/TR01/PM/RE/0697 | Submission of Initial Cross Section Drawing from 07+000 to 07+147 (ETR006) | 06.07.2020 | 1745
729 | Road close | 166 | RE | 01.06.2020 | ENC/TR01/PM/RE/0698 | Request to Close the Road Temporarily on ETR166 at the Location CH 02+780 to 02+950 km | 03.06.2020 | S-20-TR-1404/RE
730 | Extension | No | TL | 01.06.2020 | ENC/TR01/PM/TL/0699 | Extension of Time
731 | HA | 57 | RE | 01.06.2020 | ENC/TR01/PM/RE/0700 | Resubmission of Horizontal Alignment Drawing (Revision – 02) from 00+000 to 00+620 (ETR057) | 09.06.2020 | S-20-TR-1435/RE
732 | ICS | 16 | RE | 02.06.2020 | ENC/TR01/PM/RE/0701 | Submission of Initial Cross Section Drawing from 0+000 to 1+000 (ETR016) | 27.06.2020 | S-20-TR-1637/RE | Accepted
733 | Yard | No | RE | 02.06.2020 | ENC/TR01/PM/RE/0702 | Method Statement for the Operation of Stock Yards & Disposal Yards | 13.06.2020 | S-20-TR-1499/RE
734 | Culvert Drawing | 6 | RE | 02.06.2020 | ENC/TR01/PM/RE/0703 | Submission of Reconstructions Box Culvert Drawing at CH 04+457Km (ETR006) | 19.06.2020 | S-20-TR-1542/RE
735 | Culvert Drawing | 166 | RE | 02.06.2020 | ENC/TR01/PM/RE/0704 | Submission of Reconstruction of Box Culvert Drawing at CH 01+616.4km (ETR166) | 10.06.2020 | S-20-TR-1462/RE
736 | Yard | No | GEN | 02.06.2020 | ENC/TR01/PM/GEN/0705 | Request for Approval of Disposal Yard
737 | Yard | No | GEN | 02.06.2020 | ENC/TR01/PM/GEN/0706 | Request for Approval of Disposal Yard
738 | DCS | 166 | RE | 03.06.2020 | ENC/TR01/PM/RE/0707 | Submission of Design Cross Section Drawings from CH 4+000 to 4+250km (ETR166) | 20.06.2020 | S-20-TR-1564/RE
739 | Yard | No | GEN | 03.06.2020 | ENC/TR01/PM/GEN/0708 | Request for Approval of Disposal Yard
740 | Road close | 166 | RE | 03.06.2020 | ENC/TR01/PM/RE/0709 | Request to Close the Road Temporarily on ETR166 at the Location CH 01+500 to 01+800 km | 06.06.2020 09.06.2020 | S-9-1403/DTL S-20-TR-1451/RE | Take NEC Action
741 | Culvert Drawing | 6 | RE | 03.06.2020 | ENC/TR01/PM/RE/0710 | Submission of Reconstructions Box Culvert Drawing at CH 00+507.5Km (ETR006) | 16.06.2020 | S-20-TR-1525/RE
742 | Culvert Drawing | 166 | RE | 03.06.2020 | ENC/TR01/PM/RE/0711 | Submission of Box Culvert Drawing at CH 02+259 (ETR166) | 19.06.2020 | S-20-TR-1559/RE
743 | Curfew | No | GEN | 04.06.2020 | ENC/TR01/PM/GEN/0712 | Request Curfew Pass to Travel Within the Worksite in Mutur, Serunuwara & Trincomalee
744 | Earth Trasporation | No | TL | 04.06.2020 | ENC/TR01/PM/TL/0713 | Restriction of Borrow Earth Transportation to Worksite
745 | Culvert Drawing | 6 | RE | 05.06.2020 | ENC/TR01/PM/RE/0714 | Submission of Reconstructions Slab Culvert Drawing at CH 00+436.5Km (ETR006) | 20.06.2020 | S-20-TR-1574/RE
746 | Culvert Drawing | 6 | RE | 05.06.2020 | ENC/TR01/PM/RE/0715 | Submission of Reconstructions Slab Culvert Drawing at CH 01+509Km (ETR006) | 19.06.2020 | S-20-TR-1561/RE
747 | Culvert Drawing | 6 | RE | 05.06.2020 | ENC/TR01/PM/RE/0716 | Submission of Reconstructions Slab Culvert Drawing at CH 02+860Km (ETR006) | 03.07.2020 | 1728
748 | NCR | No | RE | 05.06.2020 | ENC/TR01/PM/RE/0717 | Description of Non-Conformity
749 | Road Length | All | TL | 05.06.2020 | ENC/TR01/PM/TL/0718 | Road Length Changes with Horizontal Alignment (HA)
750 | HA | 127 | RE | 05.06.2020 | ENC/TR01/PM/RE/0719 | Resubmission of Horizontal Alignment Drawing from CH 00+000 to 01+026.778 Km (ETR127) | 11.06.2020 | S-20-TR-1474/RE | Approved
751 | VA | 70 | RE | 05.06.2020 | ENC/TR01/PM/RE/0720 | Submission of Vertical Profile Drawings from 0+000 to 1+575 Km on ETR070 | 11.06.2020 15.06.2020 | S-20-TR-1473/RE S-20-TR-1513/RE | Approved
752 | IPA | No | RE | 06.06.2020 | ENC/TR01/PM/RE/0721 | Interim Payment Application - 09 for the Month of May 2020
753 | EMC | 58 | RE | 06.06.2020 | ENC/TR01/PM/RE/0722 | Submission of Environmental Monitoring Checklist for ETR 058
754 | ESO Progress | No | RE | 06.06.2020 | ENC/TR01/PM/RE/0723 | Monthly Environmental & Social Progress Reports for the Month of May–2020
755 | Culvert | 171 | TL | 06.06.2020 | ENC/TR01/PM/TL/0724 | To Obtain Details of Existing Culvert Structures on BTT (A15) Road | 13.06.2020 | S-20-1452/DTL
756 | Road close | 166 | RE | 07.06.2020 | ENC/TR01/PM/RE/0725 | Request to Close the Road Temporarily on ETR166 at the Location CH 00+490 to 00+600 km | 09.06.2020 | S-20-TR-1450/RE
757 | Progress Report | No | RE | 07.06.2020 | ENC/TR01/PM/RE/0726 | Resubmission of Monthly Progress Report No-06 (Revision - 01) for the Month of April - 2020 | 18.06.2020 | S-20-TR-1544/RE
758 | Tree Removed | 127 | RE | 07.06.2020 | ENC/TR01/PM/RE/0727 | List of Trees to be removed on the road ID ETR 127 | 24.06.2020 | S-20-TR-1599/RE
759 | Yard | No | RE | 07.06.2020 | ENC/TR01/PM/GEN/0728 | Request for Approval of Disposal Yard
760 | Monthly Work Program | No | TL | 07.06.2020 | ENC/TR01/PM/TL/0729 | Resubmission of Monthly Work Program (Revision - 01) - June 2020
761 | ICS | 70 | RE | 08.06.2020 | ENC/TR01/PM/RE/0730 | Submission of Initial Cross Section Drawing from 00+000 to 01+572.3 (ETR070) | 12.06.2020 | S-20-TR-1485/RE | Accepted
762 | Yard | No | GEN | 09.06.2020 | ENC/TR01/PM/GEN/0731 | Request for approval of Stock Yard
763 | DCS | 70 | RE | 09.06.2020 | ENC/TR01/PM/RE/0732 | Submission of Design Cross Section Drawings from CH 0+000 to 1+000km (ETR070) | 13.06.2020 | S-20-TR-1500/RE
764 | Crack Survey | 171 | RE | 09.06.2020 | ENC/TR01/PM/RE/0733 | Submission of Crack Survey Report from CH 81+220 to 84+595 km (ETR171) | 28.07.2020 | 1936
765 | Yard | No | GEN | 09.06.2020 | ENC/TR01/PM/GEN/0734 | Request for approval of Stock Yard
766 | Yard | 70 | RE | 09.06.2020 | ENC/TR01/PM/RE/0735 | Method Statement for the Operation of Stock Yards & Disposal Yards | 13.06.2020 | S-20-TR-1498/RE | Approved
767 | Source Approval | No | RE | 11.06.2020 | ENC/TR01/PM/RE/0736 | Submission for Concrete Mix Design of Grade 30/20 from Tokyo Supermix - Trincomalee | 19.06.2020 | S-20-TR-1533/RE
768 | Culvert Drawing | 166 | RE | 11.06.2020 | ENC/TR01/PM/RE/0737 | Obstruction on the Culvert Construction due to the Water Pipes at the Culvert Locations on ETR166
769 | Crack Survey | 70 | RE | 12.06.2020 | ENC/TR01/PM/RE/0738 | Submission of Crack Survey Report from CH 0+000 to 0+200 km (ETR070) | 24.07.2020 | 1925
770 | EMC | 6 | RE | 12.06.2020 | ENC/TR01/PM/RE/0739 | Submission of Environmental Monitoring Checklist for ETR 006
771 | Quantity Changes | No | TL | 12.06.2020 | ENC/TR01/PM/TL/0740 | Quantity Changes in CTC Rev1 of TR1 Package | 29.06.2020 | S-20-1577/JR
772 | Shoulder Dimentions | 171 | TL | 12.06.2020 | ENC/TR01/PM/TL/0741 | Confirmation of Shoulder Dimensions of ETR 171 (A15) Road | 13.06.2020 | S-20-1453/JR
773 | Progress Report | No | RE | 12.06.2020 | ENC/TR01/PM/RE/0742 | Monthly Progress Report – 08 for the Month of May – 2020 | 23.06.2020 | S-20-TR-1591/RE
774 | Yard | No | RE | 12.06.2020 | ENC/TR01/PM/RE/0743 | Resubmission of Disposal Yard (Revision Layout) | 15.07.2020 | 1828
775 | VA | 57 | RE | 12.06.2020 | ENC/TR01/PM/RE/0744 | Resubmission of Vertical Profile Drawings from 0+000 to 0+621.51 Km (Revision - 03) on ETR057 | 16.06.2020 | S-20-TR-1530/RE
776 | Culvert Drawing | 59 | RE | 12.06.2020 | ENC/TR01/PM/RE/0745 | Submission of Reconstructions Box Culvert Drawing at CH 00+004Km (ETR059) | 10.07.2020 | 1780
777 | Culvert Drawing | 6 | RE | 12.06.2020 | ENC/TR01/PM/RE/0746 | Submission of Reconstructions Box Culvert Drawing at CH 00+555.8Km (ETR006) | 16.06.2020 | S-20-TR-1527/RE
778 | Culvert Drawing | 6 | RE | 12.06.2020 | ENC/TR01/PM/RE/0747 | Resubmission of Reconstructions Slab Culvert Drawing at CH 06+006.5Km (ETR006)
779 | Culvert Drawing | 166 | RE | 12.06.2020 | ENC/TR01/PM/RE/0748 | Resubmission of Pipe Culvert Drawing at CH 02+067.4Km (ETR166) | 03.07.2020 | 1729
780 | ICS | 16 | RE | 12.06.2020 | ENC/TR01/PM/RE/0749 | Submission of Initial Cross Section Drawing from 1+000 to 2+000 (ETR016) | 10.07.2020 | 1794 | Accepted
781 | Culvert Drawing | 70 | RE | 12.06.2020 | ENC/TR01/PM/RE/0750 | Submission of Reconstructions Box Culvert Drawing at CH 00+998.25Km (ETR070) | 02.07.2020 | 1704
782 | VA | 133 | RE | 12.06.2020 | ENC/TR01/PM/RE/0751 | Submission of Vertical Alignment Drawings from 0+000 to 1+072.72km (ETR133) | 27.06.2020 | S-20-TR-1641/RE
783 | VA | 54 | RE | 12.06.2020 | ENC/TR01/PM/RE/0752 | Submission of Vertical Alignment Drawings from 0+000 to 0+332.29km (ETR054) | 19.06.2020 | S-20-TR-1555/RE
784 | Unsuitable Soil | No | RE | 13.06.2020 | ENC/TR01/PM/RE/0753 | : Issues on Disposing the Excavated Unsuitable Soil on the Road ID ETR166 & Public Request to Dispose Excavated Unsuitable Soil on a Rural Road | 19.06.2020 | S-20-TR-1557/RE
785 | VA | 66 | RE | 13.06.2020 | ENC/TR01/PM/RE/0754 | Submission of Vertical Alignment Drawings from 0+000 to 0+566.799km (ETR066) | 03.07.2020 | 1737
786 | Crack Survey | 58 | RE | 13.06.2020 | ENC/TR01/PM/RE/0755 | Submission of Crack Survey Report from CH 0+000 to 0+110 km (ETR058) | 27.06.2020 | S-20-TR-1631/RE
787 | ICS | 16 | RE | 13.06.2020 | ENC/TR01/PM/RE/0756 | Submission of Initial Cross Section Drawing from 2+000 to 3+000 (ETR016) | 10.07.2020 | 1775 | Resubmit
788 | ICS | 55 | RE | 13.06.2020 | ENC/TR01/PM/RE/0757 | Submission of Initial Cross Section Drawing from 0+000 to 0+410 (ETR055) | 02.07.2020 | 1723 | Accepted
789 | Calibration | No | RE | 13.06.2020 | ENC/TR01/PM/RE/0758 | Submission of Calibration Reports for Edward and Christie Concrete Batching Plant at Sahayapuram, Muthur | 22.06.2020 | S-20-TR-1566/RE
790 | Source Approval | No | RE | 13.06.2020 | ENC/TR01/PM/RE/0759 | Resubmission for Source Approval of Admixtures & Curing Agent for Concreting from Finex Engineering | 24.06.2020 | S-20-TR-1592/RE
791 | Method Statement | No | RE | 15.06.2020 | ENC/TR01/PM/RE/0760 | Method Statement for the Operation of Stock Yards & Disposal Yards | 27.06.2020 | S-20-TR-1640/RE
792 | Contractor's Staff | No | TL | 15.06.2020 | ENC/TR01/PM/TL/0761 | Submission of Proposal for Contractor’s Staff (QAI - Mr. K.Vasanthan) | 20.06.2020 | S-20-1510/DTL
793 | Culvert Drawing | 6 | RE | 15.06.2020 | ENC/TR01/PM/RE/0762 | Submission of Reconstructions Box Culvert Drawing at CH 03+620.5Km (ETR006) | 02.07.2020 | 1709
794 | Culvert Drawing | 133 | RE | 15.06.2020 | ENC/TR01/PM/RE/0763 | Submission of Reconstructions Slab Culvert Drawing at CH 00+061.4Km (ETR133) | 19.06.2020 | S-20-TR-1538/RE
795 | Culvert Drawing | 133 | RE | 15.06.2020 | ENC/TR01/PM/RE/0764 | Submission of Reconstructions Slab Culvert Drawing at CH 00+285.4Km (ETR133) | 25.06.2020 | S-20-TR-1609/RE
796 | HA | 133 | RE | 15.06.2020 | ENC/TR01/PM/RE/0765 | Resubmission of Horizontal Alignment Drawing (Revision – 01) from 00+000 to 01+070.73 (ETR133)
797 | ICS | 54 | RE | 15.06.2020 | ENC/TR01/PM/RE/0766 | Submission of Initial Cross Section Drawing from 0+000 to 0+332 (ETR054) | 23.06.2020 | S-20-TR-1588/RE | Accepted
798 | Culvert Drawing | 133 | RE | 15.06.2020 | ENC/TR01/PM/RE/0767 | Submission of Reconstructions Slab Culvert Drawing at CH 0+058.16Km (ETR133) | 25.06.2020 | S-20-TR-1610/RE
799 | Culvert Drawing | 133 | RE | 15.06.2020 | ENC/TR01/PM/RE/0768 | Submission of Reconstructions Slab Culvert Drawing at CH 0+288.87Km (ETR133) | 25.06.2020 | S-20TR-1608/RE
800 | Culvert Drawing | 54 | RE | 15.06.2020 | ENC/TR01/PM/RE/0769 | Submission of Reconstructions Slab Culvert Drawing at CH 0+066.11Km (ETR054) | 19.06.2020 | S-20-TR-1539/RE
801 | Culvert Drawing | 54 | RE | 15.06.2020 | ENC/TR01/PM/RE/0770 | Submission of Reconstructions Slab Culvert Drawing at CH 0+163Km (ETR054) | 22.07.2020 | 1886
802 | ICS | 165 | RE | 15.06.2020 | ENC/TR01/PM/RE/0771 | Submission of Initial Cross Section Drawing from 0+000 to 1+360 (ETR165) | 10.07.2020 | 1788 | Accepted
803 | CEB Poles | 70 | RE | 15.06.2020 | ENC/TR01/PM/RE/0772 | Submitting the List of CEB Poles has to be Shifted on ETR070 | 16.07.2020 | 1843
804 | VA | 165 | RE | 16.06.2020 | ENC/TR01/PM/RE/0773 | Submission of Vertical Alignment Drawings from 0+000 to 1+359.870km (ETR165) | 10.07.2020 | 1783
805 | Trainee | No | RE | 16.06.2020 | ENC/TR01/PM/GEN/0774 | Regarding Provide In-Plant Training
806 | ICS | 57 | RE | 16.06.2020 | ENC/TR01/PM/RE/0775 | Submission of Initial Cross Section Drawings (ETR057) | 20.06.2020 | S-20-TR-1569/RE | Accepted
807 | ICS | 18 | RE | 16.06.2020 | ENC/TR01/PM/RE/0776 | Submission of Initial Cross Section Drawing from 0+000 to 1+000 (ETR018) | 13.07.2020 | 1808 | Accepted
808 | ICS | 18 | RE | 16.06.2020 | ENC/TR01/PM/RE/0777 | Submission of Initial Cross Section Drawing from 1+000 to 1+880 (ETR018) | 13.07.2020 | 1809 | Accepted
809 | Culvert Drawing | 54 | RE | 17.06.2020 | ENC/TR01/PM/RE/0778 | Submission of Reconstructions Pipe Culvert Drawing at CH 0+217Km (ETR054) | 22.07.2020 | 1886
810 | Progress Report | No | RE | 17.06.2020 | ENC/TR01/PM/RE/0779 | Submission of Monthly Progress Report No – 06 for the Month of March - 2020
811 | ICS | 67 | RE | 17.06.2020 | ENC/TR01/PM/RE/0780 | Submission of Initial Cross Section Drawing from 0+000 to 0+565km (ETR067) | 30.06.2020 | S-20-TR-1681/RE | Accepted
812 | Safety Audit | 6 | RE | 17.06.2020 | ENC/TR01/PM/RE/0781 | Submission of Road Safety Audit Report for ETR006 | 18.06.2020 | S-20-TR-1558/RE
813 | Road close | 70 | RE | 17.06.2020 | ENC/TR01/PM/RE/0782 | Request to Close the Road Temporarily on ETR070 at the Location CH 00+950 to 01+020 km | 22.06.2020 | S-20-TR-1578/RE
814 | Culvert Drawing | 6 | RE | 17.06.2020 | ENC/TR01/PM/RE/0783 | Resubmission of Culvert Construction Drawing of CH 1+572 – ETR006
815 | ICS | 133 | RE | 17.06.2020 | ENC/TR01/PM/RE/0784 | Submission of Initial Cross Section Drawings (ETR133 - Section 01 & Section 02) | 30.06.2020 | S-20-TR-1680/RE | Accepted
816 | Public Request | 130 | RE | 17.06.2020 | ENC/TR01/PM/RE/0785 | Public Requests – Mankala Boakku road (ETR 130) | 07.07.2020 | 1756
817 | Pavement Design | 171 | RE | 17.06.2020 | ENC/TR01/PM/RE/0786 | Submission of Pavement Design Report for ETR171 from CH 88+500 to 91+420Km | 26.06.2020 | S-20-TR-1614/RE
818 | DCS | 171 | RE | 17.06.2020 | ENC/TR01/PM/RE/0787 | Submission of Design Cross Section Drawings from CH 82+500 to 83+000 (ETR171) | 26.06.2020 | S-20-TR-1624/RE
819 | DCS | 171 | RE | 17.06.2020 | ENC/TR01/PM/RE/0788 | Submission of Design Cross Section Drawings from CH 83+000 to 83+200km (ETR171) | 26.06.2020 | S-20-TR-1624/RE
820 | DCS | 57 | RE | 17.06.2020 | ENC/TR01/PM/RE/0789 | Submission of Design Cross Section Drawings (ETR057) | 23.06.2020 | S-20-TR-1579/RE
821 | SSEMAP | No | TL | 18.06.2020 | ENC/TR01/PM/TL/0790 | Submission of Site Specific Environmental Management Action Plan (SSEMAP)
822 | ICS | 16 | RE | 18.06.2020 | ENC/TR01/PM/RE/0791 | Submission of Initial Cross Section Drawing from 3+000 to 4+000km (ETR016) | 10.07.2020 | 1793 | Accepted
823 | Yard | No | RE | 18.06.2020 | ENC/TR01/PM/GEN/0792 | Request for approval of Disposal Yard
824 | Culvert Drawing | 54 | RE | 18.06.2020 | ENC/TR01/PM/RE/0793 | Submission of Reconstructions Box Culvert Drawing at CH 00+327.5Km (ETR054) | 22.07.2020 | 1886
825 | Progress Report | No | RE | 19.06.2020 | ENC/TR01/PM/RE/0794 | Submission of Monthly Progress Report No-06 (Revision - 01) for the Month of April - 2020
826 | Culvert Drawing | 6 | RE | 19.06.2020 | ENC/TR01/PM/RE/0795 | Submission of Reconstructions Slab Culvert Drawing at CH 0+890Km (ETR006)
827 | Yard |  | GEN | 19.06.2020 | ENC/TR01/PM/GEN/0796 | Request for Approval of Disposal Yard
828 | EMC | 59 | RE | 19.06.2020 | ENC/TR01/PM/RE/0797 | Submission of Environmental Monitoring Checklist (EMC) ETR059
829 | Culvert Drawing | 54 | RE | 19.06.2020 | ENC/TR01/PM/RE/0798 | Resubmission of Reconstruction Pipe Culvert Drawing at CH 0+066.11Km (ETR054) | 22.07.2020 | 1886
830 | Culvert Drawing | 133 | RE | 20.06.2020 | ENC/TR01/PM/RE/0799 | Resubmission of Reconstruction Pipe Culvert Drawing at CH 00+061.4Km (ETR133) | 10.07.2020 | 1779
831 | Pavement Design | 132 | RE | 20.06.2020 | ENC/TR01/PM/RE/0800 | Resubmission of Pavement Design Report (Rev-01) for CH 0+000 to 0+510 km on the Road ID ETR132 | 14.07.2020 | 1821
832 | ICS | 170 | RE | 20.06.2020 | ENC/TR01/PM/RE/0801 | Submission of Initial Cross Section Drawing from 0+000 to 1+000km (ETR170) | 13.07.2020 | 1810 | Resubmit
833 | DCS | 70 | RE | 22.06.2020 | ENC/TR01/PM/RE/0802 | Submission of Design Cross Section Drawings from CH: 01+000 to 01+570 km (ETR070) | 02.07.2020 | 1719
834 | Method Statement | No | RE | 22.06.2020 | ENC/TR01/PM/RE/0803 | Submission of Method Statement for the Operation of Stock Yards & Disposal Yards | 27.06.2020 | S-20-TR-1640/RE
835 | Culvert Drawing | 133 | RE | 22.06.2020 | ENC/TR01/PM/RE/0804 | Submission of Culvert Construction Drawing at CH 00+261.2 – ETR133 | 10.07.2020 | 1782
836 | Culvert Drawing | 133 | RE | 22.06.2020 | ENC/TR01/PM/RE/0805 | Submission of Culvert Construction Drawing at CH 00+077.7 – ETR133 | 10.07.2020 | 1781
837 | Culvert Drawing | 70 | RE | 22.06.2020 | ENC/TR01/PM/RE/0807 | Submission of New Construction of Pipe Culvert Drawing at CH 1+129 on ETR070 | 02.07.2020 | 1707
838 | ICS | 170 | RE | 22.06.2020 | ENC/TR01/PM/RE/0806 | Submission of Initial Cross Section Drawing from 1+000 to 2+000km (ETR170) | 13.07.2020 | 1811 | Resubmit
839 | Method Statement | No | RE | 22.06.2020 | ENC/TR01/PM/RE/0808 | Submission of Method Statement for the Operation of Stock Yards & Disposal Yards | 10.07.2020 | 1751
840 | VA | 59 | RE | 23.06.2020 | ENC/TR01/PM/RE/0809 | Submission of Vertical Alignment Drawings from CH: 0+000 to 0+530.288km on Manatchenai Peruvely Central Road (ETR059) | 23.06.2020 | S-20-TR-1593/RE | Approved
841 | VA | 58 | RE | 23.06.2020 | ENC/TR01/PM/RE/0810 | Submission of Vertical Alignment Drawings from CH: 0+000 to 0+542.483Km on Cooperative Road, Iruthayapuram (ETR058) | 23.06.2020 | S-20-TR-1594/RE
842 | Road close | 58 | RE | 23.06.2020 | ENC/TR01/PM/RE/0811 | Request to Close the Road Temporarily on ETR058 at the Location CH 00+020 to 00+080 km | 26.06.2020 | S-20-TR-1629/RE
843 | VA | 127 | RE | 23.06.2020 | ENC/TR01/PM/RE/0812 | Resubmission of Vertical Alignment Drawings (Revision 01) from CH: 0+000 to 0+985km on ETR127 | 26.06.2020 | S-20-TR-1638/RE
844 | Asphalt Laying | 130 | RE | 23.06.2020 | ENC/TR01/PM/RE/0813 | Asphalt Laying Field Trail (Wearing Course Type-iii) Access Asphalt Plant Vavuniya on ETR130 | 25.06.2020 | S-20-TR-1620/RE
845 | DCS | 171 | RE | 23.06.2020 | ENC/TR01/PM/RE/0814 | Submission of Design Cross Section Drawings from CH 80+500 to 81+500km (ETR171)
846 | Safety Audit | No | RE | 23.06.2020 | ENC/TR01/PM/RE/0815 | Submission of Road Safety Audit Reports | 24.06.2020 | S-20-TR-1600/RE
847 | Culvert Drawing | 6 | RE | 23.06.2020 | ENC/TR01/PM/RE/0816 | Submission of Reconstruction Slab Culvert Drawing at CH 3+816.47 on ETR006
848 | Culvert Report | 54 | RE | 23.06.2020 | ENC/TR01/PM/RE/0817 | Resubmission of Culvert Conditional Report (Revision 01) for the Road ETR054 | 01.07.2020 | S-20-TR-1670/RE
849 | Culvert Report | 133 | RE | 23.06.2020 | ENC/TR01/PM/RE/0818 | Resubmission of Culvert Conditional Report (Revision 01) for the Road ETR133 | 01.07.2020 | S-20-TR-1671/RE
850 | EMC | 133 | RE | 23.06.2020 | ENC/TR01/PM/RE/0819 | Submission of Environmental Monitoring Checklist (EMC) ETR133
851 | EMC | 54 | RE | 23.06.2020 | ENC/TR01/PM/RE/0820 | Submission of Environmental Monitoring Checklist (EMC) ETR054
852 | Engineer's Staff | No | RE | 23.06.2020 | ENC/TR01/PM/RE/0821 | Submission of Operatives for the Engineer’s Staff (Mr. S. M. I. C. I. B. Sethunga - Survey Assistant) | 25.06.2020 | S-20-TR-1617/RE
853 | Engineer's Staff | No | RE | 23.06.2020 | ENC/TR01/PM/RE/0822 | Submission of Operatives for the Engineer’s Staff (Ms. A.A.Nilakshi – CAD Operator) | 25.06.2020 | S-20-TR-1618/RE
854 | Drain Schedule | 171 | RE | 23.06.2020 | ENC/TR01/PM/RE/0823 | Resubmission of Drain Schedule from CH 78+300 – 84+400 on Batticaloa Thirukondiyadimadu Trincomalee Road (ETR 171) | 03.07.2020 | 1725
855 | Pavement Design | 66 | RE | 24.06.2020 | ENC/TR01/PM/RE/0824 | Resubmission of Pavement Design Report for CH 0+000 to 0+500 km on the Road ID ETR066 | 01.07.2020 | S-20-TR-1696/RE
856 | SSEMAP | No | TL | 24.06.2020 | ENC/TR01/PM/TL/0825 | Submission of Site Specific Environmental Management Action Plan (SSEMAP)
857 | VA | 164 | RE | 24.06.2020 | ENC/TR01/PM/RE/0826 | Submission of Vertical Alignment Drawing from 0+000 - 1+480 km on ETR164 | 03.07.2020 | 1727
858 | Yard | No | GEN | 24.06.2020 | ENC/TR01/PM/RE/0827 | Request for Approval of Stock Yard
859 | Cost Estimation | 6 | RE | 24.06.2020 | ENC/TR01/PM/RE/0828 | Submission of Cost Estimate for Culvert By Pass at the location of Ch 4+795km on ETR 006 | 30.06.2020 | S-20-TR-1675/RE
860 | ICS | 51 | RE | 24.06.2020 | ENC/TR01/PM/RE/0829 | Submission of Initial Cross Section Drawing from 0+000 to 0+541km (ETR051) | 06.07.2020 | 1742 | Resubmit
861 | Culvert Drawing | 127 | RE | 24.06.2020 | ENC/TR01/PM/RE/0830 | Submission of Widening Box Culvert Drawing at CH 00+494.00 on ETR127 (Revision 01) | 18.07.2020 | 1864
862 | ICS | 66 | RE | 24.06.2020 | ENC/TR01/PM/RE/0831 | Resubmission of Initial Cross Section Drawing from 0+000 to 0+567km (ETR066) Revision - 01 | 23.07.2020 | 1905 | Accepted
863 | Progress Report | No | RE | 24.06.2020 | ENC/TR01/PM/RE/0832 | Resubmission of Monthly Progress Report No-08 (Revision - 01) for the Month of May - 2020 | 30.06.2020 | S-20-TR-1666/RE | Accepted
864 | ICS | 170 | RE | 24.06.2020 | ENC/TR01/PM/RE/0833 | Submission of Initial Cross Section Drawing from 2+000 to 3+000km (ETR170) | 23.07.2020 | 1904
865 | VA | 54 | RE | 24.06.2020 | ENC/TR01/PM/RE/0834 | Resubmission of Vertical Alignment Drawing from 00+000 to 00+332.294 (ETR054) | 02.07.2020 | 1698
866 | HA | 54 | RE | 24.06.2020 | ENC/TR01/PM/RE/0835 | Resubmission of Horizontal Alignment Drawing (Revision – 01) from 00+000 to 00+332.294 (ETR054) | 02.07.2020 | S-20-TR-1699/RE | Resubmit
867 | Source Approval | No | GEN | 24.06.2020 | ENC/TR01/PM/RE/0836 | Request to Remove Uneven Rock Particles from the Abundant Quarry at Kottiyarama Mula Maha Viharaya premises
868 | VA | 56 | RE | 25.06.2020 | ENC/TR01/PM/RE/0837 | Submission of Vertical Alignment Drawings from 0+000 to 0+530km (ETR056) | 23.07.2020 | 1897
869 | Culvert Drawing | 6 | RE | 25.06.2020 | ENC/TR01/PM/RE/0838 | Submission of Reconstructions Pipe Culvert Drawing at CH 2+192.74Km (ETR006)
870 | DCS | 171 | RE | 25.06.2020 | ENC/TR01/PM/RE/0839 | Resubmission of Design Cross Section Drawings (Revision 02) from CH 83+200 to 84+000km (ETR171)
871 | VA | 134 | RE | 24.06.2020 | ENC/TR01/PM/RE/0840 | Submission of Vertical Alignment Drawings from 0+000 to 1+121.989km (ETR134) | 23.07.2020 | 1898
872 | Crack Survey | 166 | RE | 26.06.2020 | ENC/TR01/PM/RE/0841 | Resubmission of Crack Survey Report from CH 2+640 to 2+960km (ETR166)
873 | Crack Survey | 166 | RE | 26.06.2020 | ENC/TR01/PM/RE/0842 | Resubmission of Crack Survey Report from CH 2+960 to 4+220 km (ETR166)
874 | Crack Survey | 127 | RE | 26.06.2020 | ENC/TR01/PM/RE/0843 | Resubmission of Crack Survey Report from CH 0+550 to 0+980 km (ETR0127)
875 | Crack Survey | 166 | RE | 26.06.2020 | ENC/TR01/PM/RE/0844 | Resubmission of Crack Survey Report from CH 1+860 to 2+640km (ETR166)
876 | DCS | 127 | RE | 26.06.2020 | ENC/TR01/PM/RE/0845 | Resubmission of Design Cross Section Drawings (Revision 01) from CH 0+003 to 0+984km (ETR127) | 10.07.2020 | 1791
877 | Crack Survey | 133 | RE | 26.06.2020 | ENC/TR01/PM/RE/0846 | Submission of Crack Survey Report (Volume 01) from CH 0+000 to 0+300km (ETR133)
878 | Calibration | No | RE | 26.06.2020 | ENC/TR01/PM/RE/0847 | Instrument Calibration for Auto Level WD 3030 & WS 014927 Report | 07.07.2020 | S-20-TR-1759/RE | Accepted
879 | Pavement Design | 6 | RE | 26.06.2020 | ENC/TR01/PM/RE/0848 | Resubmission of Pavement Design Report for CH 0+000 to 7+150 (ETR006)
880 | Cost Estimation | 6 | RE | 26.06.2020 | ENC/TR01/PM/RE/0849 | Submission of Cost Breakdown Temporary by-pass for Culvert at the location of Ch 0+436km on ETR 006 | 30.06.2020 | S-20-TR-1675/RE
881 | Cost Estimation | 6 | RE | 26.06.2020 | ENC/TR01/PM/RE/0850 | Submission of Cost Breakdown Temporary by-pass for Culvert at the location of Ch 0+507km on ETR 006 | 30.06.2020 | S-20-TR-1675/RE
882 | DCS | 57 | RE | 27.06.2020 | ENC/TR01/PM/RE/0851 | Resubmission of Design Cross Section Drawings (Revision 02) from CH 0+080 to 0+620km (ETR057) | 30.06.2020 | S-20-TR-1682/RE
883 | ICS | 170 | RE | 27.06.2020 | ENC/TR01/PM/RE/0852 | Submission of Initial Cross Section Drawing from 3+000 to 3+819km (ETR170) | 23.07.2020 | 1903 | Accepted
884 | DCS | 171 | RE | 29.06.2020 | ENC/TR01/PM/RE/0853 | Resubmission of Design Cross Section Drawings (Revision 02) from CH 84+000 to 84+600km (ETR171)
885 | DCS | 171 | RE | 29.06.2020 | ENC/TR01/PM/RE/0854 | Submission of Design Cross Section Drawings from CH 84+600 to 85+000 km (ETR171)
886 | HA | 16 | RE | 29.06.2020 | ENC/TR01/PM/RE/0855 | Submission of Horizontal Alignment Drawing for CH 1+330 – 1+510 km on ETR016 | 23.07.2020 | 1899 | Approved as noted
887 | Yard | No | RE | 28.06.2020 | ENC/TR01/PM/RE/0856 | Submission of Method Statement for the Operation of Stock Yards & Disposal Yards | 11.07.2020 | 1798
888 | Source Approval | No | RE | 28.06.2020 | ENC/TR01/PM/RE/0857 | Submission of Source Approval of Bitumen 60/70, Emulsion CRS1 & CSS1 and Cutback Bitumen MC-30 from GKUC International (Pvt) Lmt. | 30.06.2020 | S-20-TR-1690/RE
889 | Cost Estimation | 6 | RE | 29.06.2020 | ENC/TR01/PM/RE/0858 | Submission of Cost Breakdown Temporary by-pass for Culvert at the location of Ch 1+508km on ETR 006 | 11.07.2020 | 1773
890 | Crack Survey | 54 | RE | 29.06.2020 | ENC/TR01/PM/RE/0859 | Submission of Crack Survey Report from CH 0+000 to 0+385 km (ETR054)
891 | DCS | 6 | RE | 29.06.2020 | ENC/TR01/PM/RE/0860 | Submission of Design Cross Section Drawings from CH 0+000 to 1+000km (ETR006)
892 | DCS | 6 | RE | 29.06.2020 | ENC/TR01/PM/RE/0861 | Submission of Design Cross Section Drawings from CH 01+000 to 02+000km (ETR006)
893 | DCS | 6 | RE | 29.06.2020 | ENC/TR01/PM/RE/0862 | Submission of Design Cross Section Drawings from CH 02+000 to 03+000km (ETR006)
894 | DCS | 6 | RE | 29.06.2020 | ENC/TR01/PM/RE/0863 | Submission of Design Cross Section Drawings from CH 03+000 to 04+000km (ETR006)
895 | DCS | 6 | RE | 29.06.2020 | ENC/TR01/PM/RE/0864 | Submission of Design Cross Section Drawings from CH 04+000 to 05+000km (ETR006)
896 | Safety Audit | 16 | RE | 29.06.2020 | ENC/TR01/PM/RE/0865 | Submission of Road Safety Audit Report for ETR016 | 01.07.2020 | S-20-TR-1694/RE
897 | Crack Survey | 16 | RE | 29.06.2020 | ENC/TR01/PM/RE/0866 | Submission of Crack Survey Report from CH 0+000 to 1+100 km (ETR016)
898 | Yard | No | GEN | 29.06.2020 | ENC/TR01/PM/GEN/0867 | Request for Approval of Stock & Disposal Yard
899 | EMC | 16 | RE | 29.06.2020 | ENC/TR01/PM/RE/0868 | Submission of Environmental Monitoring Checklist (EMC) ETR016
900 | Yard | No | RE | 29.06.2020 | ENC/TR01/PM/RE/0869 | Submission of Method Statement for the Operation of Stock Yards & Disposal Yards | 15.07.2020 | 1831
901 | Yard | No | RE | 29.06.2020 | ENC/TR01/PM/RE/0870 | Submission of Method Statement for the Operation of Stock Yards & Disposal Yards | 02.07.2020 | 1700
902 | DCS | 171 | RE | 30.06.2020 | ENC/TR01/PM/RE/0871 | Submission of Design Cross Section Drawings from CH 81+500 to 82+500km (ETR171)
903 | VA | 171 | RE | 30.06.2020 | ENC/TR01/PM/RE/0872 | Submission of Vertical Alignment Drawings from 92+400 to 96+000km (ETR171) | 14.07.2020 | 1814 | Approved as noted
904 | ICS | 134 | RE | 30.06.2020 | ENC/TR01/PM/RE/0873 | Submission of Initial Cross Section Drawing from 0+000.75 to 1+122km (ETR134) | 10.07.2020 | 1792 | Accepted
905 | Culvert | 6 | RE | 30.06.2020 | ENC/TR01/PM/RE/0874 | Obstruction on the Culvert Construction due to the Water Pipes at the Culvert Locations on ETR006 | 02.07.2020 | S-20-1617/DTL
906 | Variation | 171 | RE | 30.06.2020 | ENC/TR01/PM/RE/0875 | Submission of Variation Order No. 02 for Construction of Water Pipe Crossing Across the BTT Road | 25.07.2020 | 1941 | Resubmit
907 | Crack Survey | 59 | RE | 01.07.2020 | ENC/TR01/PM/RE/0876 | Submission of Crack Survey Report from CH 0+000 to 0+202 km (ETR059)
908 | Monthly Work Program | No | TL | 01.07.2020 | ENC/TR01/PM/TL/0877 | Submission of Monthly Work Program - July 2020 | 10.07.2020 | 1778
909 | DCS | 58 | RE | 02.07.2020 | ENC/TR01/PM/RE/0878 | Resubmission of Design Cross Section Drawings (Revision 01) from CH 0+000 to 0+450km (ETR058) | 15.07.2020 | 1833
910 | Source Approval | No | RE | 02.07.2020 | ENC/TR01/PM/RE/0879 | Method Statement for Rectification of Honeycombs | 15.07.2020 | 1825
911 | Culvert Drawing | 133 | RE | 03.07.2020 | ENC/TR01/PM/RE/0880 | Resubmission of Reconstructions Slab Culvert Drawing at CH 0+288.87Km (ETR133) | 18.07.2020 | 1866
912 | DCS | 70 | RE | 02.07.2020 | ENC/TR01/PM/RE/0881 | Resubmission of Design Cross Section Drawings (ETR070) | 15.07.2020 | 1832
913 | Culvert Drawing | 134 | RE | 03.07.2020 | ENC/TR01/PM/RE/0882 | Submission of Reconstructions Pipe Culvert Drawing at CH 00+538.16Km (ETR134)
914 | Culvert Drawing | 134 | RE | 03.07.2020 | ENC/TR01/PM/RE/0883 | Submission of Reconstructions Pipe Culvert Drawing at CH 00+207.44Km (ETR134)
915 | EMC | 58 | RE | 03.07.2020 | ENC/TR01/PM/RE/0884 | Submission of Environmental Monitoring Checklist (Revision 01) for ETR 058 | 25.07.2020 | S-20-1761/JR
916 | Crack Survey | 132 | RE | 03.07.2020 | ENC/TR01/PM/RE/0885 | Submission of Crack Survey Report from CH 0+000 to 0+315 km (ETR132) | 28.07.2020 | 1929
917 | EMC | 6 | RE | 03.07.2020 | ENC/TR01/PM/RE/0886 | Submission of Environmental Monitoring Checklist (Revision 01) for ETR 006 | 25.07.2020 | S-20-1760/JR
918 | ICS | 171 | RE | 07.07.2020 | ENC/TR01/PM/RE/0887 | Submission of Initial Cross Section Drawing from 101+000 - 102+000 km (ETR171)
919 | ESO Progress | No | RE | 07.07.2020 | ENC/TR01/PM/RE/0888 | Monthly Environmental & Social Progress Reports for the Month of June–2020
920 | VA | 54 | RE | 07.07.2020 | ENC/TR01/PM/RE/0889 | Submission of Vertical Alignment Drawings from 0+000 to 0+332.29km (ETR054) | 14.07.2020 | 1820
921 | Field Lab | No | RE | 06.07.2020 | ENC/TR01/PM/RE/0890 | Field Laboratory - 02 at Muthur | 22.07.2020 | 1876
922 | Crack Survey | 51 | RE | 06.07.2020 | ENC/TR01/PM/RE/0891 | Submission of Crack Survey Report from CH 0+000 to 0+130 km (ETR051) | 27.07.2020 | 1957
923 | HA | 54 | RE | 06.07.2020 | ENC/TR01/PM/RE/0892 | Resubmission of Horizontal Alignment Drawing for CH 0+000 – 0+332.29 km on ETR054 | 14.07.2020 | 1822
924 | Yard | No | RE | 06.07.2020 | ENC/TR01/PM/RE/0893 | Request for Approval of Unsuitable Soil Dumping Yard
925 | Claim | No | TL | 06.07.2020 | ENC/TR01/PM/TL/0894 | Exceptionally Adverse Climatic Condition
926 | Claim | No | TL | 06.07.2020 | ENC/TR01/PM/RE/0895 | Extension of Time (EOT) Claim 2
927 | Initial Maintenance | No | RE | 06.07.2020 | ENC/TR01/PM/RE/0896 | Initial Maintenance Completed Roads | 15.07.2020 | 1840
928 | ICS | 171 | RE | 07.07.2020 | ENC/TR01/PM/RE/0897 | Submission of Initial Cross Section Drawing from 101+000 - 102+000 km (ETR171) | 23.07.2020 | 1902
929 | ESO Progress | No | RE | 07.07.2020 | ENC/TR01/PM/RE/0898 | Monthly Environmental & Social Progress Reports for the Month of June–2020
930 | Utility Details | 166 | RE | 07.07.2020 | ENC/TR01/PM/RE/0899 | Submission of Utility Details to be shifted in ETR166
931 | IPA | No | RE | 07.07.2020 | ENC/TR01/PM/RE/0900 | Application for Interim Payment Certificate - IPA 10 for June 2020 | 13.07.2020 | 1807
932 | Vechile | No | RE | 07.07.2020 | ENC/TR01/PM/RE/0901 | Temporary Replacement of Type 4 Vehicle – BII - 2094 | 10.07.2020 | 1772
933 | Culvert Drawing | 70 | RE | 06.07.2020 | ENC/TR01/PM/RE/0902 | Submission of Reconstructions Pipe Culvert Drawing at CH 1+129Km (ETR070)
934 | Source Approval | No | GEN | 07.07.2020 | ENC/TR01/PM/GEN/0903 | Material Testing – 16mm diameter Lanwa Steel for Reinforcement
935 | Source Approval | No | GEN | 07.07.2020 | ENC/TR01/PM/GEN/0904 | Testing of Water
936 | Variation | No | TL | 07.07.2020 | ENC/TR01/PM/TL/0905 | Variation No 03: Expenses Done for Preventive Measure of COVID-19 Virus | 21.07.2020 | 1879
937 | VA | 70 | RE | 07.07.2020 | ENC/TR01/PM/RE/0906 | Resubmission of Vertical Alignment Drawings (Revision 01) from CH: 1+070 to 1+170 km on ETR070
938 | Contractor's Staff | No | TL | 08.07.2020 | ENC/TR01/PM/RE/0907 | Submission of Proposal for Contractor’s Staff (Site Engineer) | 21.07.2020 | S-20-1721/DTL
939 | Public Request | 133 | RE | 08.07.2020 | ENC/TR01/PM/RE/0908 | Public Requests – Lingapuram School road (ETR 133)
940 | Yard | 6 | GEN | 08.07.2020 | ENC/TR01/PM/GEN/0909 | Request for Approval of Disposal Yard for the Road ID ETR006
941 | Culvert Drawing | 56 | RE | 06.07.2020 | ENC/TR01/PM/RE/0910 | Submission of Reconstructions Pipe Culvert Drawing at CH 00+522.77Km (ETR056)
942 | Crack Survey | 70 | RE | 09.07.2020 | ENC/TR01/PM/RE/0911 | Crack Survey
943 | ICS | 56 | RE | 10.07.2020 | ENC/TR01/PM/RE/0912 | Submission of Initial Cross Section Drawing from 0+000 to 0+500 km (ETR056) | 23.07.2020 | 1906 | Accepted
944 | VA | 166 | RE | 10.07.2020 | ENC/TR01/PM/RE/0913 | Resubmission of Vertical Alignment Drawings (Revision 01) from CH: 1+980 to 2+140 km on ETR166 | 24.07.2020 | 1928 | Approved as noted
945 | Culvert Drawing | 165 | RE | 10.07.2020 | ENC/TR01/PM/RE/0914 | Submission of Reconstruction Pipe Culvert Drawing at CH 00+959.7km (ETR165)
946 | Culvert Drawing | 165 | RE | 10.07.2020 | ENC/TR01/PM/RE/0915 | Submission of Reconstruction Pipe Culvert Drawing at CH 01+210km (ETR165) | 29.07.2020 | 1996
947 | VA | 66 | RE | 11.07.2020 | ENC/TR01/PM/RE/0916 | Resubmission of Vertical Alignment Drawings from CH: 0+000 to 0+566.799 km on ETR066 | 18.07.2020 | 1865
948 | Covid19 | No | TL | 11.07.2020 | ENC/TR01/PM/TL/0917 | Prevention of Performing Contractor’s Obligation with Curfew Prevailed & Corona-virus (COVID 19)
949 | ICS | 61 | RE | 12.07.2020 | ENC/TR01/PM/RE/0918 | Submission of Initial Cross Section Drawings from 0+000 to 0+443km (ETR061) | 18.07.2020 | 1861
950 | Source Approval | No | RE | 11.07.2020 | ENC/TR01/PM/RE/0919 | Submission of Source Approval of Bitumen 60/70, Emulsion CRS1 & CSS1 and Cutback Bitumen MC-30 from A.N.I Enterprises (Pvt) Ltd. | 16.07.2020 | 1850
951 | Source Approval | No | RE | 11.07.2020 | ENC/TR01/PM/RE/0920 | Submission of Source Approval of Road marking material from T.D.P Thermo-line | 15.07.2020 | 1836
952 | EMC | 51 | RE | 11.07.2020 | ENC/TR01/PM/RE/0921 | Submission of Environmental Monitoring Checklist for ETR051
953 | EMC | 132 | RE | 11.07.2020 | ENC/TR01/PM/RE/0922 | Submission of Environmental Monitoring Checklist (EMC) for ETR132
954 | EMC | 134 | RE | 11.07.2020 | ENC/TR01/PM/RE/0923 | Submission of Environmental Monitoring Checklist (EMC) for ETR134
955 | Culvert Drawing | 70 | RE | 12.07.2020 | ENC/TR01/PM/RE/0924 | Submission of Hydrological Report for the culvert at CH: 0+988 on ETR070 | 16.07.2020 | 1836
956 | Furniture | No | RE | 13.07.2020 | ENC/TR01/PM/RE/0925 | Provided Furniture and Equipment items for Type 2 House |  | TR01/CE/138 | Gentral file
957 | Culvert | 70 | RE | 13.07.2020 | ENC/TR01/PM/RE/0926 | Resubmission of the culvert at the location of CH: 0+988km on Ralkuly main road (ETR070) | 16.07.2020 | 1836
958 | Yard | No | GEN | 13.07.2020 | ENC/TR01/PM/GEN/0927 | Request to approve the Disposal Yard of Playground at Manalchenai
959 | DCS | 59 | RE | 13.07.2020 | ENC/TR01/PM/RE/0928 | Resubmission of Design Cross Section Drawings (Revision1) from CH 0+000 to 0+530 km (ETR059) | 24.07.2020 | 1924
960 | ESO Progress | No | TL | 13.07.2020 | ENC/TR01/PM/TL/0929 | Environmental and Social Monthly Progress Report for June 2020
961 | Yard | No | GEN | 13.07.2020 | ENC/TR01/PM/GEN/0930 | Request Disposal Yard
962 | Yard | No | RE | 14.07.2020 | ENC/TR01/PM/RE/0931 | Submission of Method Statement for the Operation of Stock Yards & Disposal Yards
963 | IPA | No | RE | 15.07.2020 | ENC/TR01/PM/RE/0932 | Interim Payment Application - 010 for the Month June 2020
964 | Covid19 | No | TL | 15.07.2020 | ENC/TR01/PM/TL/0933 | Prevention of Performing Contractor’s Obligation with Curfew Prevailed & Corona-virus (COVID 19) | 20.07.2020 | S-20-1714/JR
965 | Yard |  | GEN | 15.07.2020 | ENC/TR01/PM/GEN/0934 | Yard
966 | Culvert Drawing | 56 | RE | 15.07.2020 | ENC/TR01/PM/RE/0935 | Submission of Reconstruction Pipe Culvert Drawing at the location of CH 00+127.7km on ETR056
967 | Culvert Drawing | 166 | RE | 15.07.2020 | ENC/TR01/PM/RE/0936 | Submission of Widening Pipe Culvert Drawing at the location of CH 03+901.6km on ETR166 | 28.07.2020 | 1950
968 | Culvert Drawing | 133 | RE | 15.07.2020 | ENC/TR01/PM/RE/0937 | Submission of Reconstruction Box Culvert Drawing at the location of CH 00+480Km on ETR133 | 18.07.2020 | 1867
969 | VA | 16 | RE | 15.07.2020 | ENC/TR01/PM/RE/0938 | Resubmission of Vertical Alignment Drawing at the location CH 1+330 to 1+510 Km ETR016
970 | SSEMAP | No | TL | 15.07.2020 | ENC/TR01/PM/TL/0939 | Submission of Site Specific Enviromental Management Action Plan (SSEMAP)
971 | By Pass | 6 | RE | 15.07.2020 | ENC/TR01/PM/RE/0940 | Submission of Consent Letters from the Landowners to construct a temporary By pass for ETR006
972 | HA | 131 | RE | 15.07.2020 | ENC/TR01/PM/RE/0941 | Submission of Horizontal Alignment Drawing Section I CH 0+000 to 0+670.554 & Section II CH 0+000 to 0+265.638 km ETR131 | 17.07.2020 | 1854
973 | Crack Survey | 165 | RE | 15.07.2020 | ENC/TR01/PM/RE/0942 | Submission of Crack Survey CH.0+000 to 0+150Km ETR165 | 28.07.2020 | 1937
974 | Culvert Drawing | 165 | RE | 15.07.2020 | ENC/TR01/PM/RE/0943 | Submission of both side Widening Pipe Culvert at the location of CH 0+671.4 to ETR165
975 | ICS | 51 | RE | 15.07.2020 | ENC/TR01/PM/RE/0944 | Resbmission of Initial Cross Section Drawing (Revision 01) from 0+000 to 0+541km (ETR051) | 23.07.2020 | 1907 | Accepted
976 | Culvert Drawing |  | RE | 15.07.2020 | ENC/TR01/PM/RE/0945 | T junction | 18.07.2020 | 1869
977 | ICS | 16 | RE | 16.07.2020 | ENC/TR01/PM/RE/0946 | Resubmission of Initial Cross Section Drawing (Revision 1) from 2+000 to 3+000 Km ETR016 | 23.07.2020 | 1908 | Accepted
978 | ICS | 6 | RE | 16.07.2020 | ENC/TR01/PM/RE/0947 | Resubmission of Initial Cross Section Drawing (Revision 01) from 5+000 to 6+000 km (ETR006) | 23.07.2020 | 1910 | Accepted
979 | ICS | 6 | RE | 16.07.2020 | ENC/TR01/PM/RE/0948 | Resubmission of Initial Cross Section Drawing (Revision 01) from 6+000 to 7+000 km (ETR006)
980 | ICS | 6 | RE | 16.07.2020 | ENC/TR01/PM/RE/0949 | Resubmission of Initial Cross Section Drawing (Revision 01) from 7+000 to 7+147 km (ETR006) | 23.07.2020 | 1909
981 | Safety Audit | No | RE | 16.07.2020 | ENC/TR01/PM/RE/0950 | Submission of Road Safety Audit Reports | 21.07.2020 | 1880
982 | DCS | 58 | RE | 17.07.2020 | ENC/TR01/PM/RE/0951 | Resubmission of Design Cross Section Drawings (Revision2) on Cooperative Road, Iruthayapuram (ETR058) | 24.07.2020 | 1931
983 | DCS | 171 | RE | 17.07.2020 | ENC/TR01/PM/RE/0952 | Submission of Design Cross Section Drawings from CH 85+000 to 86+000 km on the Batticaloa Thirukondiyadimadu Trincomalee Road (ETR171)
984 | Payment | 166 | GEN | 17.07.2020 | ENC/TR01/PM/GEN/0953 | Payment to Shift NWS&DB Pipe Lines on Mavilaru Junction to Seruwila Main Road ETR166
985 | Crack Survey | 59 | RE | 17.07.2020 | ENC/TR01/PM/RE/0954 | Submission of Crack Survey Report (Volume-2) from CH 0+202 to 0+530 km on Manatchenai Peruvely Central Road, Periyavely (ETR 059)
986 | DCS | 171 | RE | 17.07.2020 | ENC/TR01/PM/RE/0955 | Resubmission of Design Cross Section Drawings from CH 80+500 to 81+500 km on the Batticaloa Thirukondiyadimadu Trincomalee Road (ETR171)
987 | T-Junction | 127 | RE | 17.07.2020 | ENC/TR01/PM/RE/0956 | Resubmission of T-Junction Design at the Location of CH. 0+642 km on Methagama Central Road, Somapura (ETR127) | 18.07.2020 | 1869
988 | Culvert Drawing | 165 | RE | 18.07.2020 | ENC/TR01/PM/RE/0957 | Submission of Both Side Widening Pipe Culvert Drawing at the location of CH 00+617km on Dehiwatte to 5th Speel Road (ETR165)
989 | Culvert Drawing | 133 | RE | 18.07.2020 | ENC/TR01/PM/RE/0958 | Submission of Reconstruction Box Culvert Drawing at the location of CH 00+482.4km on Lingapuram School Road (ETR133- Section02)
990 | Culvert Drawing | 59 | RE | 18.07.2020 | ENC/TR01/PM/RE/0959 | Resubmission of Reconstruction Box Culvert Drawing (Revision -01) at the location of CH 00+004km on Manatchenai Peruvely Central Road, Peruvely (ETR059) | 29.07.2020 | 1995
991 | Routine Maintenance | No | RE | 18.07.2020 | ENC/TR01/PM/RE/0960 | Routine Maintenance on Road ID ETR006, ETR055, ETR068, ETR069, ETR164 & ETR171
992 | Day Works | 171 | RE | 18.07.2020 | ENC/TR01/PM/RE/0961 | Request to Pay under “Day Works” for Trail Section on ETR171 from CH. 86+000 to 86+100
993 | Contractor's Staff | No | TL | 18.07.2020 | ENC/TR01/PM/TL/0962 | Submission of Proposal for Contractor’s Staff (Site Engineer) | 21.07.2020 | S-20-1722/DTL
994 | Pavement Design | 132 | RE | 18.07.2020 | ENC/TR01/PM/RE/0963 | Resubmission of Pavement Design Report (Rev-02) for CH 0+000 to 0+510 km on Mohaideen Jummah Mosque Road (ETR132) | 23.07.2020 | 1895
995 | Engineer's Staff | No | RE | 18.07.2020 | ENC/TR01/PM/RE/0964 | Submission of Operatives for the Engineer’s Staff (Ms. T. Kobika- Survey Assistant) | 21.07.2020 | 1884
996 | Progress Report | No | RE | 18.07.2020 | ENC/TR01/PM/RE/0965 | Submission of Monthly Progress Report No - 09 for the Month of June - 2020 | 29.07.2020 | 1986 | Resubmit
997 | DCS | 171 | RE | 20.07.2020 | ENC/TR01/PM/RE/0966 | Resubmission of Design Cross Section Drawings from CH 81+500 to 82+500 km on the Batticaloa Thirukondiyadimadu Trincomalee Road (ETR171)
998 | Meeting | 133 | RE | 20.07.2020 | ENC/TR01/PM/RE/0967 | Minutes of the Meeting Regarding Omitting of Culverts on Lingapuram School Road (ETR 133)
999 | T-Junction | 127 | RE | 20.07.2020 | ENC/TR01/PM/RE/0968 | Resubmission of T-Junction Design at the Location of CH. 0+720 km on Methagama Central Road, Somapura (ETR127)
1000 | Culvert Drawing | 166 | RE | 20.07.2020 | ENC/TR01/PM/RE/0969 | Resubmission of Reconstruction Box Culvert Drawing (Revision -01) at the location of CH 00+558km on Mavilaru Junction to Seruvila Main Road (ETR166) | 22.07.2020 | 1893
1001 | VA | 170 | RE | 20.07.2020 | ENC/TR01/PM/RE/0970 | Submission of Vertical Alignment Drawings from CH 0+000 to 3+860km on Sampoor soodakkudah Road (ETR170)
1002 | ICS | 53 | RE | 20.07.2020 | ENC/TR01/PM/RE/0971 | Submission of Initial Cross Section Drawing from CH 0+000 to 0+470km on Al-hambra School Road, Alli Nagar West, Alli Nagar East & lgbal Nagar (ETR053) | 28.07.2020 | 1973
1003 | ICS | 171 | RE | 20.07.2020 | ENC/TR01/PM/RE/0972 | Submission of Initial Cross Section Drawing from CH 102+000 to 103+000km on Batticaloa Thirukondiyadimadu Trincomalee [A15] (ETR171) | 28.07.2020 | 1972
1004 | ICS | 16 | RE | 20.07.2020 | ENC/TR01/PM/RE/0973 | Resubmission of Initial Cross Section Drawing from CH 1+330 to 1+510 km on Mawadichenai Road (ETR016) | 28.07.2020 | 1974
1005 | DCS | 16 | RE | 20.07.2020 | ENC/TR01/PM/RE/0974 | Submission of Design Cross Section Drawings from CH 0+000 to 1+000 km on Mawadichenai Road (ETR016)
1006 | Crack Survey | 58 | RE | 20.07.2020 | ENC/TR01/PM/RE/0975 | Submission of Crack Survey Report (Volume-2) from CH 0+110 to 0+510 km on Cooperative Road, Iruthayapuram (ETR 058)
1007 | Road close | 133 | RE | 20.07.2020 | ENC/TR01/PM/RE/0976 | Request to Close the Road Temporarily on ETR133 at the Location CH 00+070 to 00+085km | 21.07.2020 23.07.2020 | S-20-1716/DTL S-20-TR-1917/RE
1008 | Utility Details | 164 | RE | 20.07.2020 | ENC/TR01/PM/RE/0977 | Submission of Utility Details of SLT Posts to be shifted on Neelpola Junction to Muthur Road (ETR164)
1009 | Utility Details | 18 | RE | 20.07.2020 | ENC/TR01/PM/RE/0978 | Submission of Utility Details of SLT Posts to be shifted on D6 Road (ETR018)
1010 | Utility Details | 165 | RE | 20.07.2020 | ENC/TR01/PM/RE/0979 | Submission of Utility Details to be shifted on Dehiwatta to 5th Speel Road (ETR165)
1011 | Utility Details | 18 | RE | 20.07.2020 | ENC/TR01/PM/RE/0980 | Submitting the List of Utility Details on D6 Road (ETR018)
1012 | Utility Details | 164 | RE | 20.07.2020 | ENC/TR01/PM/RE/0981 | Submitting the List of Utility Details on D6 Road (ETR164)
1013 | Yard | No | GEN | 20.07.2020 | ENC/TR01/PM/GEN/0982 | Requesting Approval for Material transportation
1014 | Utility Details | 165 | RE | 20.07.2020 | ENC/TR01/PM/RE/0983 | Submitting the List of Utility Details on Dehiwatta to 5th Speel Road (ETR165)
1015 | Yard | No | GEN | 21.07.2020 | ENC/TR01/PM/GEN/0984 | Requesting Approval for Material transportation
1016 | VA | 6 | RE | 21.07.2020 | ENC/TR01/PM/RE/0985 | Resubmission of Vertical Alignment Drawings from CH: 0+000 to 3+900 km on Thopur Kaddaiparichan Iddimanthurai Road (ETR006)
1017 | Method Statement | No | RE | 21.07.2020 | ENC/TR01/PM/RE/0986 | Resubmission of Method Statement for Base Failure Section of Compactable/ suitable sub grade
1018 | DCS | 171 | RE | 21.07.2020 | ENC/TR01/PM/RE/0987 | Resubmission of Design Cross Section Drawings (Revision 01) from CH 82+500 to 83+000 km on the Batticaloa Thirukondiyadimadu Trincomalee Road (ETR171)
1019 | EMC | 164 | RE | 21.07.2020 | ENC/TR01/PM/RE/0988 | Submission of Environmental Monitoring Checklist (EMC) for Neelpola Junction to Muthur Road (ETR164)
1020 | EMC | 18 | RE | 21.07.2020 | ENC/TR01/PM/RE/0989 | Submission of Environmental Monitoring Checklist (EMC) for D6 Road (ETR018)
1021 | EMC | 165 | RE | 21.07.2020 | ENC/TR01/PM/RE/0990 | Submission of Environmental Monitoring Checklist (EMC) for Dehiwatta to 5th Speel Road (ETR165)
1022 | VA | 171 | RE | 21.07.2020 | ENC/TR01/PM/RE/0991 | Submission of Vertical Alignment Drawings from 88+500 to 92+400km on Batticaloa Thirukondiyadimadu Trincomalee Road (ETR171)
1023 | DCS | 16 | RE | 21.07.2020 | ENC/TR01/PM/RE/0992 | Submission of Design Cross Section Drawings from CH 1+520 to 2+000 km on Mawadichenai Road (ETR016)
1024 | VA | 171 | RE | 22.07.2020 | ENC/TR01/PM/RE/0993 | Submission of Vertical Alignment Drawings from CH 96+000 to 102+000km on Batticaloa Thirukondiyadimadu Trincomalee Road (ETR171)
1025 | Culvert Drawing | 166 | RE | 22.07.2020 | ENC/TR01/PM/RE/0994 | Submission of Box Culvert Reconstruction Drawing (Revision 02) at CH 0+558 (ETR166) | 24.07.2020 | 1923
1026 | Source Approval | No | RE | 22.07.2020 | ENC/TR01/PM/RE/0995 | Submission of Concrete Mix Design of Design of Grade 30/20
1027 | Source Approval | No | RE | 22.07.2020 | ENC/TR01/PM/RE/0996 | Submission of Product Quality Conformity Reports for Bituminous Material of Bitumix Site Supply
1028 | EMC | 130 | RE | 22.07.2020 | ENC/TR01/PM/RE/0997 | Submission of Environmental Monitoring Checklist (EMC) during Construction Stage for Mankala Bokku [calvert] Road, Arriyama Kerny (ETR130)
1029 | Source Approval | No | RE | 22.07.2020 | ENC/TR01/PM/RE/0998 | Resubmission for Source Approval of Curing Agent for Concreting brand of Chryso Lanka
1030 | Method Statement | No | RE | 23.07.2020 | ENC/TR01/PM/RE/0999 | Resubmission of Method Statement for Base Failure Section (Revision 01)
1031 | DCS | 171 | RE | 23.07.2020 | ENC/TR01/PM/RE/1000 | Resubmission of Design Cross Section Drawings (Revision 01) from CH 83+000 to 83+200 km on Batticaloa Thirukondiyadimadu Trincomalee Road (ETR171)
1032 | Trail Section | 171 | RE | 23.07.2020 | ENC/TR01/PM/RE/1001 | Request to Pay the Expenditure for the Trial section (86+000 to 86+100) under “Day Works” on ETR171
1033 | DCS | 70 | RE | 23.07.2020 | ENC/TR01/PM/RE/1002 | Resubmission of Design Cross Section Drawings (Revision 02) for ETR070
1034 | Base Failure | 171 | RE | 23.07.2020 | ENC/TR01/PM/RE/1003 | Submission of Base Identified Failure Sections on Batticaloa Thirukondiyadimadu Trincomalee Road (ETR171)
1035 | DCS | 164 | RE | 25.07.2020 | ENC/TR01/PM/RE/1004 | Submission of Design Cross Section Drawings from CH 0+010 to 0+500 km on Neelpola Junction to Muthur Road (ETR164)
1036 | DCS | 59 | RE | 25.07.2020 | ENC/TR01/PM/RE/1005 | Resubmission of Design Cross Section Drawings (Revision2) on Manatchenai Peruvely Central Road, Periyavely (ETR059)
1037 | Tree Removed | 164 | RE | 25.07.2020 | ENC/TR01/PM/RE/1006 | List of Trees to be removed on Neelpola Junction to Muthur Road (ETR164)
1038 | Field Lab | No | RE | 25.07.2020 | ENC/TR01/PM/RE/1007 | Field Laboratory - 02 at No 365, Barathipuram, Kiliveddy, Muthur
1039 | Yard | No | GEN | 28.07.2020 | ENC/TR01/PM/GEN/1008 | Request to Approve the Stock Yard
1040 | Crack Survey | 70 | RE | 27.07.2020 | ENC/TR01/PM/RE/1009 | Resubmission of Crack Survey Report (Volume -1) from CH 0+000 to 0+200km on Ralkuly Main road, Ralkuly (ETR070)
1041 | Crack Survey | 156 | RE | 27.07.2020 | ENC/TR01/PM/RE/1010 | Submission of Crack Survey Report from CH 0+000 to 0+190km on Neithal Nagar Main (Old Haber Road) Road (ETR156)
1042 | Method Statement | No | RE | 28.07.2020 | ENC/TR01/PM/RE/1011 | Submission of Method Statement for the “Prime Coat using Bituminous Emulsion Material (CSS-1)”
1043 | Road close | 133 | RE | 27.07.2020 | ENC/TR01/PM/RE/1012 | Request to Close the Road Temporarily on ETR133 (Section -II) at the Location CH 00+240km to 00+300km | 30.07.2020 | 2010
1044 | Road close | 133 | RE | 27.07.2020 | ENC/TR01/PM/RE/1013 | Request to Close the Road Temporarily on ETR133 (Section -I) at the Location CH 00+440km to 00+500km | 30.07.2020 | 2010
1045 | CEB | No | GEN | 27.07.2020 | ENC/TR01/PM/GEN/1014 | Requesting for a Three Phase Electricity Line
1046 | Work Program | No | TL | 27.07.2020 | ENC/TR01/PM/TL/1015 | Revised Work Program & Physical S-Curve
1047 | DCS | 70 | RE | 27.07.2020 | ENC/TR01/PM/RE/1016 | Resubmission of Design Cross Section Drawings (Revision 2) from CH 1+010 to 1+490 km on Ralkuly Main Road (ETR070)
1048 | Method Statement | No | RE | 27.07.2020 | ENC/TR01/PM/RE/1017 | Submission of Method Statement for the Operation of Stock Yards & Disposal Yards
1049 | DCS | 165 | RE | 27.07.2020 | ENC/TR01/PM/RE/1018 | Submission of Design Cross Section Drawings from CH 0+020 to 0+500 km on Dehiwatta to 5th Speel Road (ETR165)
1050 | DCS | 166 | RE | 27.07.2020 | ENC/TR01/PM/RE/1019 | Resubmission of Design Cross Section Drawings (Revision 1) from CH 4+000 to 4+250 km on Mavilaru Junction to Seruvila Main Road (ETR166)
1051 | Vechile | No | GEN | 28.07.2020 | ENC/TR01/PM/GEN/1020 | Requesting No Objection Letter for the Vehicle Release
1052 | Crack Survey | 54 | RE | 28.07.2020 | ENC/TR01/PM/RE/1021 | Submission of Crack Survey Report (Volume 2) from CH 0+385 to 0+465km on Al Hairiay School Road, Periya palam (ETR054)
1053 | Culvert Drawing | 166 | RE | 28.07.2020 | ENC/TR01/PM/RE/1022 | Resubmission of Widening Pipe Culvert Drawing at the location of CH 03+901.6km on Road ID ETR166
1054 | Culvert Drawing | 133 | RE | 28.07.2020 | ENC/TR01/PM/RE/1023 | Resubmission of Reconstruction Pipe Culvert Drawing (Rivision-01) at the location of CH 00+061.4km on Lingapuram School Road (ETR133- Section01)
1055 | DCS | 164 | RE | 28.07.2020 | ENC/TR01/PM/RE/1024 | Submission of Design Cross Section Drawings from CH 0+680 to 1+000 km on Neelpola Junction to Muthur Road (ETR164)
1056 | Variation | No | RE | 28.07.2020 | ENC/TR01/PM/RE/1025 | Submission of Variation No 03: Expenses Done for Preventive Measure of COVID-19 Virus
1057 | DCS | 165 | RE | 29.07.2020 | ENC/TR01/PM/RE/1026 | Submission of Design Cross Section Drawings from CH 0+500 to 1+000 km on Dehiwatta to 5th Speel Road (ETR165)
1058 | Yard | No | GEN | 29.07.2020 | ENC/TR01/PM/GEN/1027 | Request to Approve the Disposal Yard at Historical Kottiyarama Mula Maha Viharaya
1059 | App. Pavement Design | No | RE | 29.07.2020 | ENC/TR01/PM/RE/1028 | Submission of Approved Pavement Design Reports
1060 | App. DCS | No | RE | 29.07.2020 | ENC/TR01/PM/RE/1029 | Submission of Approved Design Cross Section Drawings
1061 | DCS | 164 | RE | 29.07.2020 | ENC/TR01/PM/RE/1030 | Submission of Design Cross Section Drawings from CH 1+000 to 1+470 km on Neelpola Junction to Muthur Road (ETR164)
1062 | Culvert Drawing | 165 | RE | 29.07.2020 | ENC/TR01/PM/RE/1031 | Submission of Both Side Widening Pipe Culvert Drawing at the location of CH 00+585.9km on Dehiwatte to 5th Speel Road (ETR165)
1063 | Work Program | No | TL | 30.07.2020 | ENC/TR01/PM/TL/1032 | Revised Work Program & Physical S-Curve (Rev - 04)
1064 | Crack Survey | 56 | RE | 30.07.2020 | ENC/TR01/PM/RE/1033 | Submission of Crack Survey Report from CH 0+000 to 0+440km on Vethatheevu Main Road Shafi Nagar (ETR056)
1065 | Yard | 171 | GEN | 30.07.2020 | ENC/TR01/PM/GEN/1034 | Request to Approve the Construction Material Stock Yard on ETR 171
1066 | Trainee | No | GEN | 31.07.2020 | ENC/TR01/PM/GEN/1035 | Confirmation Letter of Requesting Industrial Training by Mr. S. Vidurshan
1067 | Calibration | No | RE | 31.07.2020 | ENC/TR01/PM/RE/1036 | Submission of Surveying Instrument Calibration Certificates for Three Nos of Auto Level and a Total Station
1068 | Yard | 171 | GEN | 31.07.2020 | ENC/TR01/PM/GEN/1037 | Request to Approve the Construction Material Stock Yard on ETR 171
1069 | VA | 18 | RE | 31.07.2020 | ENC/TR01/PM/RE/1038 | Submission of Vertical Alignment Drawings from CH 0+000 to 1+873.094km on D6 Road (ETR018)
1070 | Vechile | No | RE | 31.07.2020 | ENC/TR01/PM/RE/1039 | Resupplying Type 4 Vehicle, BII - 2094
1071 | Shutdown | No | TL | 31.07.2020 | ENC/TR01/PM/TL/1040 | Notice of Site Shut Down due to forthcoming Parliamentary General Election – August, 2020
1072 | Asphalt Laying | No | RE | 31.07.2020 | ENC/TR01/PM/RE/1041 | Information for Asphalt Laying on Holidays 01st to 3rd August 2020
1073 | DCS | 165 | RE | 31.07.2020 | ENC/TR01/PM/RE/1042 | Submission of Design Cross Section Drawings from CH 1+000 to 1+360km on Dhiwatta to 5th Speel Road (ETR165)
1074 | Design Shoulder | 164 | RE | 31.07.2020 | ENC/TR01/PM/RE/1043 | Design Shoulder Width on ETR018 and ETR164
1075 | DGAB | No | TL | 01.08.2020 | ENC/TR01/PM/TL/1044 | Preparation of Existing Concrete Base to Receive DGAB Layer
1076 | ESO Progress | No | TL | 01.08.2020 | ENC/TR01/PM/TL/1045 | Monthly Environmental & Social Progress Reports for the Month of July–2020

## RE-PM (Com)
RESIDENT ENGINEER’S CORRESPONDENCES SUMMARY SHEET (UP TO 13.01.2020)
Letter no | Date | Letter no | Descripction | Replied Letter No | Remarks
S-9-TR-0001/RE | 30.08.2019 | S-9-TR-0001/RE | Daily work programme
S-9-TR-0002/RE | 30.08.2019 | S-9-TR-0002/RE | Nonconformity - Establishment of survey monuments
S-9-TR-0003/RE | 03.09.2019 | S-9-TR-0003/RE | Vehicle for the Engineer type -2 (WP PJ 7606)
S-9-TR-0011/RE | 06.09.2019 | S-9-TR-0011/RE | Vehicle for the Engineer type -2 (WP PJ 7601)
S-9-TR-0013/RE | 06.09.2019 | S-9-TR-0013/RE | Control Traverse Surveying (ETR171)
S-9-TR-0018/RE | 12.09.2019 | S-9-TR-0018/RE | Submission of Calibration Reports of the Equipement Provided at the Materials Laboratory
S-9-TR-0019/RE | 14.09.2019 | S-9-TR-0019/RE | Submission for format for Property Condition Survey
S-9-TR-0025/RE | 18.09.2019 | S-9-TR-0025/RE | Supervision Form Sheets
S-9-TR-0032/RE | 19.09.2019 | S-9-TR-0032/RE | Remedial Action for Survey Monuments Nonconformity
S-9-TR-0033/RE | 20.09.2019 | S-9-TR-0033/RE | Main Laboratory and Field Laboratory
S-9-TR-0034/RE | 20.09.2019 | S-9-TR-0034/RE | Vehicle for the Engineer type -2 (WP PJ 7605)
S-9-TR-0038/RE | 24.09.2019 | S-9-TR-0038/RE | Calibration Report of Survey Equipment
S-9-TR-0040/RE | 24.09.2019 | S-9-TR-0040/RE | Control Point Detail
S-9-TR-0042/RE | 26.09.2019 | S-9-TR-0042/RE | Provision of Operatives for the Engineer Staff - Laboratory Technicians
S-9-TR-0043/RE | 26.09.2019 | S-9-TR-0043/RE | Initial Maintenance of the iRoad
S-9-TR-0044/RE | 26.09.2019 | S-9-TR-0044/RE | Transect Walk Comparison Recording Format
S-9-TR-0045/RE | 26.09.2019 | S-9-TR-0045/RE | Non Conformity Record - NCR form
S-9-TR-0050/RE | 02.10.2019 | S-9-TR-0050/RE | Provide fully furnished house type 2
S-9-TR-0054/RE | 03.10.2019 | S-9-TR-0054/RE | Approval of GPS Report
S-9-TR-0055/RE | 03.10.2019 | S-9-TR-0055/RE | Approval of Secondary Survey Control and Levelling Detail Report (ETR171)
S-9-TR-0056/RE | 05.10.2019 | S-9-TR-0056/RE | Submission of Statement for Soil Invetigation
S-9-TR-0062/RE | 07.10.2019 | S-9-TR-0062/RE | Vehicle for the Engineer Type 4 (CP-BIE-0199)
S-9-TR-0064/RE | 12.10.2019 | S-9-TR-0064/RE | Vehicle for the Engineer Type 4 (BIE-8557,8576,8569)
S-9-TR-0067/RE | 15.10.2019 | S-9-TR-0067/RE | Submission of format for Material Approval
S-9-TR-0068/RE | 15.10.2019 | S-9-TR-0068/RE | Traffic Data for RDA roads
S-9-TR-0071/RE | 12.10.2019 | S-9-TR-0071/RE | Housing for the Employer
S-9-TR-0075/RE | 14.10.2019 | S-9-TR-0075/RE | Submission for Source Approval of Cold Mix Material at Edward and Christie Badalgama Plant
S-9-TR-0076/RE | 14.10.2019 | S-9-TR-0076/RE | Submission for Source Approval of ABC Material at Edward and Christie Badalgama Plant
S-9-TR-0078/RE | 15.10.2019 | S-9-TR-0078/RE | Approval of method statement for initial road maintenance
S-9-TR-0081/RE | 18.10.2019 | S-9-TR-0081/RE | Ssubmission of Activity Checklist for Social Aspects
S-9-TR-0082/RE | 18.10.2019 | S-9-TR-0082/RE | Provide fully furnished office type 2 (CE Office at Mutur)
S-9-TR-0086/RE | 18.10.2019 | S-9-TR-0086/RE | Submission of Proposal for Contractor's Staff
S-9-TR-0087/RE | 18.10.2019 | S-9-TR-0087/RE | Source approval for Reinforcement (Clause 4.9 of CoC)
S-9-TR-0092/RE | 19.10.2019 | S-9-TR-0092/RE | Source approval for Cement (Clause 4.9 of CoC)
S-9-TR-0093/RE | 18.10.2019 | S-9-TR-0093/RE | Approval of Secondary Survey Control and Levelling Detail Report (ETR171)
S-9-TR-0094/RE | 18.10.2019 | S-9-TR-0094/RE | Approval of Secondary Survey Control and Levelling Detail Report (ETR171)
S-9-TR-0096/RE | 23.10.2019 | S-9-TR-0096/RE | Crack Survey Method Statement & Crack Survey Format
S-9-TR-0101/RE | 19.10.2019 | S-9-TR-0101/RE | Submission of Format for Monthly Report
S-9-TR-0102/RE | 19.10.2019 | S-9-TR-0102/RE | Issues of site clearance for Land Mines in A15 Road
S-9-TR-0103/RE | 23.10.2019 | S-9-TR-0103/RE | Design Road Width-BTT RD (A15) from 48th Km to 108th Km
S-9-TR-0114/RE | 26.10.2019 | S-9-TR-0114/RE | Request to increase the cold mix thickness from 35mm to 50mm for the A15 Road
S-9-TR-0120/RE | 26.10.2019 | S-9-TR-0120/RE | Provision of Operatives for the Engineer Staff - Clerk
S-9-TR-0122/RE | 26.10.2019 | S-9-TR-0122/RE | Material Approval for ABC - Edward & Christie Metal Crusher Plant at Wadakada (Clause 4.9 of Coca)
S-9-TR-0123/RE | 26.10.2019 | S-9-TR-0123/RE | Material Approval for Initial Maintenance of Existing Road- Cold Mix
S-9-TR-0124/RE | 29.10.2019 | S-9-TR-0124/RE | Approval of Topography Survey Drawing from 78+240 to 82+500 km (ETR171)
S-9-TR-0131/RE | 01.11.2019 | S-9-TR-0131/RE | Issues of Site clearance for Land Mines along BTT Road (A15) at CH 81+800 km
S-9-TR-0132/RE | 01.11.2019 | S-9-TR-0132/RE | Request for Determination of Design Road Width
S-9-TR-0135/RE | 01.11.2019 | S-9-TR-0135/RE | Approval of Secondary Survey Control and Levelling Detail Report from CH 87+000 to CH 92+000 (ETR171)
S-9-TR-0136/RE | 01.11.2019 | S-9-TR-0136/RE | Approval of Secondary Survey Control and Levelling Detail Report from CH 92+000 to 96+000 (ETR171)
S-9-TR-0138/RE | 02.11.2019 | S-9-TR-0138/RE | Request for Stationary items-01
S-9-TR-0142/RE | 06.11.2019 | S-9-TR-0142/RE | Source Approval for Bitumen & Emulsion
S-9-TR-0147/RE | 06.11.2019 | S-9-TR-0147/RE | Provision of Operatives for the Engineer's Staff - Survey Assistant
S-9-TR-0153/RE | 08.11.2019 | S-9-TR-0153/RE | Weather Record for the Month of Sep & Oct 2019
S-9-TR-0154/RE | 08.11.2019 | S-9-TR-0154/RE | Provision of Operatives for the Engineer's Staff - Labour
S-9-TR-0162/RE | 13.11.2019 | S-9-TR-0162/RE | Request for Determination of Design Road Width
S-9-TR-0167/RE | 13.11.2019 | S-9-TR-0167/RE | Approval of GPS Report
S-9-TR-0169/RE | 13.11.2019 | S-9-TR-0169/RE | Interim Payment Application - 02 for the Month October 2019
S-9-TR-0171/RE | 13.11.2019 | S-9-TR-0171/RE | Temporary Site Shut down due to President Election
S-9-TR-0173/RE | 18.11.2019 | S-9-TR-0173/RE | Submission of Method Statement
S-9-TR-0175/RE | 13.11.2019 | S-9-TR-0175/RE | Submission of Project Name Board Bill:1A, Bill Item. 11 Pay item 118(1)
S-9-TR-0176/RE | 13.11.2019 | S-9-TR-0176/RE | Calibration Report of Survey Equipment
S-9-TR-0180/RE | 14.11.2019 | S-9-TR-0180/RE | Temporary Site Shut down due to President Election
S-9-TR-0181/RE | 14.11.2019 | S-9-TR-0181/RE | Provision of Operatives for the Engineer's Staff - Office Aid
S-9-TR-0182/RE | 14.11.2019 | S-9-TR-0182/RE | Vehicle Supply Type-2 for Engineer (PH-9072)
S-9-TR-0186/RE | 15.11.2019 | S-9-TR-0186/RE | Approval of Topography Survey Drawing from 82+500 to 88+070 km (ETR171)
S-9-TR-0187/RE | 20.11.2019 | S-9-TR-0187/RE | Starting and Ending point coordinates of the road number ETR 006
S-9-TR-0188/RE | 20.11.2019 | S-9-TR-0188/RE | Desgin Issues on the Road ID ETR-171, Batticaloa Thirukondiyadimadu Trincomalee Road (A15)
S-9-TR-0198/RE | 21.11.2019 | S-9-TR-0198/RE | Source approval for Bitumen & Emulsion - Bitulink Brand
S-9-TR-0202/RE | 22.11.2019 | S-9-TR-0202/RE | Vehicle Supply Type-5 for Engineer (PH-7056)
S-9-TR-0203/RE | 22.11.2019 | S-9-TR-0203/RE | Handing Over Type 02 Office
S-9-TR-0211/RE | 23.11.2019 | S-9-TR-0211/RE | Rejection of Secondary Survey Control and Leveling Detail Report from CH 94+000 to CH 100+000 (ETR171)
S-9-TR-0212/RE | 23.11.2019 | S-9-TR-0212/RE | Handing Over Type 02 House
S-9-TR-0216/RE | 26.11.2019 | S-9-TR-0216/RE | Approval of Topography Survey Drawing from 88+070 to 94+000 km (ETR171)
S-9-TR-0217/RE | 26.11.2019 | S-9-TR-0217/RE | Submission of Monthly Progress Report - October 2019
S-9-TR-0218/RE | 26.11.2019 | S-9-TR-0218/RE | Request for Stationary items-02
S-9-TR-0225/RE | 27.11.2019 | S-9-TR-0225/RE | Provision of Operatives for the Engineer's Staff - Assitant Quantity Surveyor
S-9-TR-0232/RE | 29.11.2019 | S-9-TR-0232/RE | Submission of Detailed Geometric Design (Horizontal Alignment) for Road ID ETR-171
S-9-TR-0236/RE | 29.11.2019 | S-9-TR-0236/RE | Source approval for Cement (Clause 4.9 of CoC)
S-9-TR-0237/RE | 29.11.2019 | S-9-TR-0237/RE | Provide Main Laboratory at Mutur
S-9-TR-0238/RE | 29.11.2019 | S-9-TR-0238/RE | Confirmation verbal instruction (CVI)-Engineers House Type 2 Mutur
S-9-TR-0242/RE | 02.12.2019 | S-9-TR-0242/RE | IPA No.02 - Interim Payment Certificate Minimum Amount Not Achieved (Cluase 14.6 of PCC - Part A)
S-9-TR-0253/RE | 03.12.2019 | S-9-TR-0253/RE | Submission for Source Approval of Captain Steel (Clause 4.9 of CoC)
S-9-TR-0254/RE | 07.12.2019 | S-9-TR-0254/RE | Source Approval for Hume Pipe (Clause 4.9 of CoC)
S-9-TR-0257/RE | 07.12.2019 | S-9-TR-0257/RE | Approval of Secondary Survey Control and Levelling Detail Report from CH 96+000 to CH 100+000 (ETR171)
S-9-TR-0261/RE | 09.12.2019 | S-9-TR-0261/RE | Source Approval of Sub Base & Embankment Material (Roy Barrow Pit)
S-9-TR-0262/RE | 09.12.2019 | S-9-TR-0262/RE | Source Approval of Sub Base & Embankment Material (Piyal Barrow Pit)
S-9-TR-0263/RE | 07.12.2019 | S-9-TR-0263/RE | Provision of Operatives for the Engineer's Staff - CAD Operator
S-9-TR-0266/RE | 07.12.2019 | S-9-TR-0266/RE | Submission of Method Statement for Soil Investigation
S-9-TR-0267/RE | 07.12.2019 | S-9-TR-0267/RE | Vehicle Supply Type-4 for Engineer (BII-2094)
S-9-TR-0269/RE | 07.12.2019 | S-9-TR-0269/RE | Submission of Samples of Typical Drawing
S-9-TR-0270/RE | 07.12.2019 | S-9-TR-0270/RE | Resubmission of Horizontal Alignment Drawing from CH 78+300 to CH 82+500
S-9-TR-0271/RE | 09.12.209 | S-9-TR-0271/RE | Postponement of Monthly Review Meeting No 02
S-9-TR-0272/RE | 09.12.2019 | S-9-TR-0272/RE | Appoinment of Operatives for the Engineer's Staff AQS
S-9-TR-0275/RE | 10.12.2019 | S-9-TR-0275/RE | Submission of Method Statement for Base Failure Section
S-9-TR-0278/RE | 10.12.2019 | S-9-TR-0278/RE | Condition of the BTT RD (A15) from 48th km to 108th km
S-9-TR-0282/RE | 10.12.2019 | S-9-TR-0282/RE | Submission of Horizontal Alignment Drawing from ETR 171 from CH 82+500 to CH 82+500
S-9-TR-0283/RE | 10.12.2019 | S-9-TR-0283/RE | Approval of Topography Survey Drawing from 94+000 to 96+000 km (ETR171)
S-9-TR-0286/RE | 14.12.2019 | S-9-TR-0286/RE | Requesting Sanitary and Cleaning items for Type 02 House
S-9-TR-0291/RE | 14.12.2019 | S-9-TR-0291/RE | Approval for Ready Mix Concrete (Tokyo Super Mix Trincomalee)
S-9-TR-0294/RE | 14.12.2019 | S-9-TR-0294/RE | Submission of Project Sign Board art work
S-9-TR-0295/RE | 14.12.2019 | S-9-TR-0295/RE | Request of Stationary Items for Type 2 Office (Laboratory)
S-9-TR-0296/RE | 14.12.2019 | S-9-TR-0296/RE | Newly Constructed Road by other Organization ETR133
S-9-TR-0298/RE | 16.12.2019 | S-9-TR-0298/RE | Approval of Topography Survey Drawing from 100+000 to 105+000 km (ETR171)
S-9-TR-0301/RE | 17.12.2019 | S-9-TR-0301/RE | Source Approval for ABC (Shan Crusher Plant at Mutur)
S-9-TR-0302/RE | 16.12.2019 | S-9-TR-0302/RE | Source Approval for Embankment Material Kumara Barrow Pit at Peeliyadi
S-9-TR-0303/RE | 17.12.2019 | S-9-TR-0303/RE | Source Approval for Course Aggregate 20mm (Clause 4.9 of CoC) Shan Crusher Plant at Pachchanur Shayapuram, Mutur
S-9-TR-0307/RE | 17.12.2019 | S-9-TR-0307/RE | Resubmission of Horizontal Alignment Drawing ETR 171 from CH 88+500 to CH 93+300
S-9-TR-0308/RE | 18.12.2019 | S-9-TR-0308/RE | Material Source Approval for Admixture Used for Concrete Works - Ecomix KA200, ConceraSA8799
S-9-TR-0309/RE | 18.12.2019 | S-9-TR-0309/RE | Source Approval of Sub Base & Embankment Matrial-Ganesh Barrow Pit
S-9-TR-0310/RE | 18.12.2019 | S-9-TR-0310/RE | Source Approval for river sand - Mahaweli River Alla Kantale (Cluse 4.9 of CoC)
S-9-TR-0313/RE | 18.12.2019 | S-9-TR-0313/RE | Initial Maintenance Completed Road
S-9-TR-0314/RE | 18.12.2019 | S-9-TR-0314/RE | Source Approval for Rubble (Parakrama Quarry)
S-9-TR-0315/RE | 19.12.2019 | S-9-TR-0315/RE | Approval of Secondary Survey Control and Leveling Detail Report from CH 0+000 to CH 4+220 (ETR166)
S-9-TR-0316/RE | 19.12.2019 | S-9-TR-0316/RE | Rejection of Secondary Survey Control and Leveling Detail Report from CH 0+000 to CH 7+170 (ETR006)
S-9-TR-0317/RE | 19.12.2019 | S-9-TR-0317/RE | Approval of Secondary Survey Control and Leveling Detail Report from CH 0+000 to CH 4+550 (ETR057)
S-9-TR-0318/RE | 19.12.2019 | S-9-TR-0318/RE | Approval of Secondary Survey Control and Leveling Details Report from CH 0+000 to CH 0+960 (ETR127)
S-9-TR-0319/RE | 19.12.2019 | S-9-TR-0319/RE | Approval of Secondary Survey Control and Leveling Details Report from CH 0+000 to CH 1+410 (ETR130)
S-9-TR-0327/RE | 20.12.2019 | S-9-TR-0327/RE | Monthly Progress Report Month of November 2019 | ENC/TR01/PM/RE/0145
S-9-TR-0331/RE | 21.12.2019 | S-9-TR-0331/RE | Culvert Condition Report (ETR171) | To be reply
S-9-TR-0333/RE | 21.12.2019 | S-9-TR-0333/RE | Invitation to Fortnight Meeting No.01
S-9-TR-0334/RE | 23.12.2019 | S-9-TR-0334/RE | Source Approval for ABC (Edward & Christy metal crusher - Wadakada) | To be reply
S-9-TR-0335/RE | 23.12.2019 | S-9-TR-0335/RE | Resubmission for Source Approval of Sub base & Embankment Material Piayal Barrow pit - Ilupankulam | To be reply
S-9-TR-0345/RE | 24.12.2019 | S-9-TR-0345/RE | Resubmission of Monthly Progress Report - Month of Octomber 2019 | To be reply
S-9-TR-0347/RE | 24.12.2019 | S-9-TR-0347/RE | Defect of the Implementation of the Crack Survey by the Contractors | To be reply
S-9-TR-0362/RE | 26.12.2019 | S-9-TR-0362/RE | Approval for Stock Yard & Disposal Yard | To be reply
S-9-TR-0367/RE | 28.12.2019 | S-9-TR-0367/RE | Approval of Topograpghy Survey Drawing from 96+000 to 100+000 (ETR171) | to be submit Pgotograpghy CD
S-9-TR-0369/RE | 28.12.2019 | S-9-TR-0369/RE | Submission of Crack Survey Report ETR 171
S-9-TR-0375/RE | 31.12.2019 | S-9-TR-0375/RE | Submission of Operatives for the Engineer's Staff - Lab Technician
S-9-TR-0377/RE | 31.12.2019 | S-9-TR-0377/RE | Maintenance of Road
S-9-TR-0383/RE | 01.01.2020 | S-9-TR-0383/RE | Changing of the time Schedule for the Fortnight Meeting | NNR
S-9-TR-0384/RE | 01.01.2020 | S-9-TR-0384/RE | Approval of Topograpghy Survey Drawing from 96+000 to 00+500 (ETR057)
S-9-TR-0390/RE | 01.01.2020 | S-9-TR-0390/RE | Resubmission of Horizontal Alignment Drawing from CH 88+500 to CH 92+400
S-9-TR-0397/RE | 03.01.2020 | S-9-TR-0397/RE | Site Observations on site visit ID ETR-171, 016, 069, & 068
S-9-TR-0398/RE | 03.01.2020 | S-9-TR-0398/RE | Rejection of Initial Cross Section Drawing from 78+300 to 79+000 (ETR171)
S-9-TR-0403/RE | 04.01.2020 | S-9-TR-0403/RE | Resubmission of Method Statement
S-9-TR-0404/RE | 04.01.2020 | S-9-TR-0404/RE | Request for Sanitary items for type 02 houese
S-9-TR-0409/RE | 14.01.2020 | S-9-TR-0409/RE | Resubmission for Approval of Readymix Concrete (Tokyo Super Mix) Ecomix and Concera Concrete admixture
S-9-TR-0412/RE | 06.01.2020 | S-9-TR-0412/RE | Approval of Topography Drawing from 0+000 to 0+960 (ETR127)
S-9-TR-0413/RE | 06.01.2020 | S-9-TR-0413/RE | Approval of Topography Drawing from 0+000 to 0+960 (ETR166)
S-9-TR-0415/RE | 07.01.2020 | S-9-TR-0415/RE | Confirmation of ownership of roads
S-9-TR-0416/RE | 07.01.2020 | S-9-TR-0416/RE | Road crossing along BTT road (ETR171)
S-9-TR-0420/RE | 08.01.2020 | S-9-TR-0420/RE | Provide fully Furnished house type1 - Employer |  | 129
S-9-TR-0425/RE | 08.01.2020 | S-9-TR-0425/RE | HIV - AIDS Awareness Programme
S-9-TR-0435/RE | 09.01.2020 | S-9-TR-0435/RE | Source Approval for ABC (EnC Crusher Plant at Wadakada)
S-9-TR-0440/RE | 09.01.2020 | S-9-TR-0440/RE | Design Road Width Town Section of BTT Road - ETR171
S-9-TR-0442/RE | 09.01.2020 | S-9-TR-0442/RE | Approval of Initial CS & Levelling Sheets for Road ID ETR171 (CH 78+300 to 79+000)
S-9-TR-0444/RE | 09.01.2020 | S-9-TR-0444/RE | Providing furniture and equipment for main laboratory
S-9-TR-0446/RE | 13.01.2020 | S-9-TR-0446/RE | Providing and maintaining Type 2 House
S-9-TR-0455/RE | 14.01.2020 | S-9-TR-0455/RE | Approval of Secondary Survey Control and Levelling Detail Report for ETR053 & ETR134
S-9-TR-0456/RE | 14.01.2020 | S-9-TR-0456/RE | Approval of Secondary Survey Control and Levelling Detail Report From CH 0+000 to 0+510 (ETR 132)
S-9-TR-0457/RE | 14.01.2020 | S-9-TR-0457/RE | Approval of Secondary Survey Control and Levelling Detail Report From CH 0+000 to 1+480 (ETR 070)
S-9-TR-0458/RE | 14.01.2020 | S-9-TR-0458/RE | Submission of Detailed Geometric Design (Horizontal Alignment) for Road ID ETR-171 from CH 92+400 to 96+000km
S-9-TR-0462/RE | 17.01.2020 | S-9-TR-0462/RE | Request for rockfilling under initial maintenance for the road ETR 166
S-9-TR-0463/RE | 17.01.2020 | S-9-TR-0463/RE | Draft Minutes of the Fornight Meeting No. 1 Held on 2nd Jan 2020
S-9-TR-0464/RE | 17.01.2020 | S-9-TR-0464/RE | Approval of Topography Survey Drawing from CH 105+300 to 108+519 (ETR171)
S-9-TR-0466/RE | 17.01.2020 | S-9-TR-0466/RE | Submission of Public Notice
S-9-TR-0467/RE | 17.01.2020 | S-9-TR-0467/RE | Monthly Progress Report 02 for the Month of November 2019 (Rev-2_
S-9-TR-0469/RE | 18.01.2020 | S-9-TR-0469/RE | Approval of Secondary Survey Control and Levelling Detail Report for ETR018 & ETR164
S-9-TR-0474/RE | 20.01.2020 | S-9-TR-0474/RE | Submission of monthly Test Summary & Weather chart
S-9-TR-0476/RE | 20.01.2020 | S-9-TR-0476/RE | Initial and Routine Maintanance of Exisiting Road
S-9-TR-0487/RE | 22.01.2020 | S-9-TR-0487/RE | Request for Sanitary items for type 02 - Febuary 2020
S-9-TR-0494/RE | 22.01.2020 | S-9-TR-0494/RE | Submission of Horizontal Alignment Drawing from CH 00+000 to CH 00+620 of ETR057 |  | Approved
S-9-TR-0495/RE | 13.01.2020 | S-9-TR-0495/RE | Request sanitary items and Cleanig
S-9-TR-0499/RE | 23.01.2020 | S-9-TR-0499/RE | Conditional Report of Existing Culverts on ETR057
S-9-TR-0501/RE | 23.01.2020 | S-9-TR-0501/RE | Final Minutes of the Fortnight Meeting No.1 Held on 02nd Jan 2020
S-9-TR-0507/RE | 24.01.2020 | S-9-TR-0507/RE | Pavement Design Report for Road ID ETR 057 from CH 0+000 to CH 1+620km
S-9-TR-0514/RE | 25.01.2020 | S-9-TR-0514/RE | Box Culvert Drawing 1-1 at CH 0+287 Road ID ETR 057
S-9-TR-0519/RE | 24.01.2020 | S-9-TR-0519/RE | Submission of Culvert Drawing 93-3 and 93-4 ETR 171
S-9-TR-0521/RE | 25.01.2020 | S-9-TR-0521/RE | Monthly Progress Report - 02 for the month of October 2019 Rev02
| 19.02.2020 | S-9-TR-0701/RE | Approved New Rates for Initial Maintanence - Trincomalee Districts

## TL to PM (Com)
TEAM LEADER’S CORRESPONDENCES SUMMARY SHEET (UP TO =date(today))
Date | Letter No | Descripction | Replied Letter No | Remarks
13.08.2019 | S-9-0066/JR | Submission of Initial Works Programme - Engineer's Review and Comments
11.09.2019 | S-9-198/JR | Engineer's Representative's New Main Office Address and Required System of Submissions and Correspondances
21.10.2019 | S-9-0354/JR | Instruction of Conduct Quality-Investigation of Road Sections Constructed by Others (PS & UC Roads)
03.10.2019 | S-9-0267/JR | Invitation to Kick-Off Meetings for the Above Contracts
01.11.2019 | S-9-0416/JR | Final Minutes of Kick-Off Meeting TR-Packages, Held on 11.10.2019
24.10.2019 | S-9-0373/JR | Instruction of Provide Pending Enviromental and Construction Permits
01.11.2019 | S-9-0398/JR | Submission of Contractor's Revision - 2 Works Programme & Cash Flow Engineer's Review & Comments
04.11.2019 | S-9-0275/JR | Instruction to Submit Breakdown of Lumpsum Prices (Cl.14.1.d GCC)
17.10.2019 | S-9-0328/JR | Draft Minutes of Kick-Off Meeting TR-Packages, Held on 11.10.2019
17.10.2019 | S-9-0337JR | Design Width of BTT RD (A15)
18.10.2019 | S-9-0345/JR | Clarification and Instruction on Road Sections Constructed by Others and Possession of Site Given for Additional Sections
21.10.2019 | S-9-0354/JR | Instruction to Conduct Quality-Investigation on Road Sections Constructed by Others (PS & UC Roads)
25.11.2019 | S-9-0518/JR | Draft Minutes of Kick-Off Meeting TR-Packages, Held on 11.11.2019
24.10.2019 | S-9-0373/JR | Instruction to Provide Pending Enviromental - and Construction Permits
01.11.2019 | S-9-0398/JR | Submission of Contructor's revision - 2 works program & Cash Flow Engineer's Review & Comments | ENC-HO/192/PO-TR1/009
25.11.2019 | S-9-0518/JR | Draft Minutes of Monthly Progress No. 01 Held on 11.11.2019
27.11.2019 | S-9-0536/JR | Submission of Contractor's Works Program (Revision 03) Engineer's Conditional Approval | ENC-HO/192/PO-TR1/011
01.12.2019 | S-9-0554/JR | Invitation to Monthly Progress Meetings (No.2)
02.12.2019 | S-9-0563/JR | Request for Contrctor's Quotation for Additional Items to be Provided as part of Intended Variation
02.12.2019 | S-9-0567/JR | Instruction Format Contractor's Monthly Report Social Safegurads
02.12.2019 | S-9-0572/JR | Final Minutes of Monthly Progress No. 01 Held on 11.11.2019
27.11.2019 | S-9-0448/JR | Invitation to 1st Monthly Progress Meeting Nov.2019
23.11.2019 | S-9-0510/JR | Employer's Expression of Dissatisfaction over slow progress of activities
09.12.2019 | S-9-0615/JR | Submission of Correspondences & Docs on Enviromental & Social Issues

## DTL to PM
TEAM LEADER’S CORRESPONDENCES SUMMARY SHEET (UP TO 26.11.2019 )
Date | Letter No | Descripction | Replied Letter No | Remarks
16.09.2019 | S-9-0220/DTL | Prerequisites to Source and Plant Approvals |  |  | 2020-08-19
24.09.2019 | S-9-0237/DTL | Engineer's Notificatios on Commencements Date, Sub-Cl.8.1 (GCC & PCC)
23.09.2019 | S-9-0230/DTL | Enviromental Safeguard Requirements in iRoad Contracts (Section 6.6 Employer Requirements)
14.08.2019 | S-9-0074/DTL | Contractor's Request for Approval of 13 Staff Assignments - Response
16.10.2019 | S-9-0321/DTL | Clearence for Land Mines in A15 Road
23.10.2019 | S-9-0357/DTL | Conditional Approval for Techinical and Financial Proposal for initial Road Maintence (Provisional Sum) | PM/TR1/iRoads/Gen/021
23.10.2019 | S-9-0362/DTL | Drawing Format
18.11.2019 | S-9-0484/DTL | 4 Nos. Proposed Staff Assignements - Response
09.01.2020 | S-9-0746/DTL | Final Minutes of Monthly Progress Meeting No.02 held on 13.12.2019